## TEMPLATE ES Solutions
Display | Display | Embedded | Display & Change to "Area" | Display & Change to "Sub Area" | Display & Change to "Title" | Display | TBC leaning on Embedded but do we lose searchability | Display | Display | Embedded | Embedded | Embedded | Embedded
Engineered Safety is about engineering out risk and engineering in health at every stage of the project lifecycle. This is achieved through working closely with our designers, clients and suppliers, and employing a modern method of construction approach.
Project | ID | Date raised | Project Scope | Discipline | Filterable key word | Status | Brief Description | Relevant FSRs | Health benefit | Current Action | Action due | Main Contact Name | Comments
Byford Rail Extension | BRE001 | 2024-08-11 | Linewide | Civil | Drainage | Concept | Challenge Spec to use precast drainage headwalls instead of insitu headwalls formwork fixing, steel tying and concrete placement activities | FSR Excavation FSR Formwork & Falsework FSR Cranes and Lifting | Eliminate manual task of forming & reo install for in situ pours. | Tim McLaughlin to obtain further information required on Client appetite to approve. | 2024-12-12 | Tim Mclaughlin
Byford Rail Extension | BRE002 | 2024-08-20 | Stations | Station structures | Platform walls | In Progress | Platform walls change from precast with insitu cantilevering slab to full precast Z shape panel. Panels designed to be self supporting during backfill and in a way that eliminates the need stitch pours. Results in less temporary works requirements and increased programme effeciency. | FSR Formwork & Falsework | Eliminate manual task of forming & reo install for in situ pours, also drilling & fitting precast props. Simplifies crane install. | Proposal supported to progress and implement as trial for Area 2 to be championed by Fred Flintstone | 2025-02-12 | Fred Flintstone | Opportunity supported for further implimnentation and allocated to Fred Flintstone for further work
Byford Rail Extension | BRE003 | 2024-11-01 | Linewide | Track | Rail - noise walls | Unfeasable | Expanding rail damper quantites to reduce noise walls along the alignment | FSR Piling FSR Cranes and Lifting |  | Sally thompson to add to project Lessons learnt register | 2025-02-12 | Sally Thompson | Reviewed idea but implimentation at this stage in the project will be cost prohibitive. To be added to lessons learnt for future projects
Byford Rail Extension | BRE004 | 2025-01-01 | Viaduct | Piling | Piles | Implemented | Large reduction in pile break back as piles were overpoured and excess concrete removed while wet rather than traditional breaking back / cropping | FSR Cranes and Lifting FSR Excavation FSR Plant and Equipment | Eliminate manual handling, hearing & vibration due to manually breaking back concrete. | George Jetson to prepare slides and share with ES forum. | NA | George Jetson | ES share slide prepared & saved in ES folder. Traditional cropping & Breakback involves drilling, breaking, pinch points, dust, lifting. Manual handling
Byford Rail Extension | BRE005 | 2025-01-01 | Viaduct | Structures | Scaffolding | Identified | Design and third party cert for viaduct access scaffolding to allow the towers to be cranable - reduces WAH for re assembling (tho high risk for lifting) | FSR Working at Height |  | Table at Monthly Project ES review meeting | 2025-01-14 | Joe bloggs | Suggestion in prestart
Examples in grey Cells can be deleted.

## Master ES Solutions
Display | Display | Embedded | Display & Change to "Area" | Display & Change to "Sub Area" | Display & Change to "Title" | Display | TBC leaning on Embedded but do we lose searchability | Display | Display | Embedded | Embedded | Embedded | Embedded
Engineered Safety is about engineering out risk and engineering in health at every stage of the project lifecycle. This is achieved through working closely with our designers, clients and suppliers, and employing a modern method of construction approach.
Project | ID | Date raised | Project Scope | Discipline | Filterable key word | Status | Brief Description | Relevant FSRs | Health benefit | Current Action | Action due | Main Contact Name | Comments
Byford Rail Extension | BRE001 | 2024-08-18 | Viaduct | Structures | Precast | Actualised | Precast viaduct structure Drastically reduces risks of working at height | FSR Working at Height | Elimination of fall hazards by removing the need for formwork and steel fixing at elevation, shifting these tasks to ground level. | Capture methodology and safety benefits in the project for future works. |  | Michael Spencer
Byford Rail Extension | BRE002 | 2024-08-18 | Sitewide | Civil | Drainage | Actualised | Installation of permanent drainage as early as possible in the project to reduce exposure to possible contaminants during a flood event with temporary drainage | Reduced exposure to contaminated water FSR Work On, Over Or Adjacent to Water | Permanent infrastructure has higher hydraulic capacity than temporary systems, preventing the spread of and contact with waterborne contaminants (e.g., site runoff, silt, or chemicals) during flood events. | Record the sequence benefit in the project foru future works. |  | Michael Spencer
Byford Rail Extension | BRE003 | 2024-08-18 | Precast | Structures | Concrete Mix | Actualised | Introduction of high flow concrete mixes. This enables a higher class concrete finish straight out of the mould. This eliminates the repetitive tasks of patching and sanding concrete and also minimises exposure to dust during the sanding back of products. | Reduced exposure to concrete dust | High-flow mixes achieve a smooth finish without mechanical abrasion, removing the need for sanding and grinding which generates harmful Respirable Crystalline Silica (RCS) dust. | Document the mix design and finish quality results in the to standardise for future elements. |  | Michael Spencer
Byford Rail Extension | BRE004 | 2024-08-18 | Stations | Structures | Modularisation | Actualised | Offsite modularisation of station buildings reduce working at heights, cranes & lifting time (compared to stick built) and simops in busy congested areas | FSR Working at Height FSR Cranes and Lifting | Shifting assembly to an offsite factory environment significantly reduces man-hours spent at height and working around suspended loads. Also minimizes site congestion (SIMOPS), reducing plant-pedestrian interface risks. | Record productivity and safety metrics (e.g., reduction in site hours) in the Lessons Learnt register to support modularisation in future designs. |  | Michael Spencer
Byford Rail Extension | BRE005 | 2024-08-18 | Site wide | Structures | Precast | Actualised | Precast headstocks and beams have cast ins to enable handrail to be preinstalled prior to install | FSR Working at Height | Installing handrails at ground level (prior to lifting) removes the critical risk of workers having to access the beam at height to fix edge protection. | Ensure lifting plans account for the additional weight/dimensions of the handrails and record for future work. |  | Michael Spencer
Byford Rail Extension | BRE006 | 2024-08-18 | Viaduct | Structures | Scaffolding | Actualised | Design and third party cert for viaduct access scaffolding to allow the towers to be cranable - reduces WAH for re assembling (tho high risk for lifting) | FSR Working at Height | Designing scaffolding towers to be lifted as a single unit eliminates the hazardous manual task of dismantling and reassembling scaffolding components at height when moving between locations. | Ensure the specific lifting study and third-party certification are archived. Document the trade-off between reduced WAH and lifting risks |  | Michael Spencer
Byford Rail Extension | BRE007 | 2024-08-18 | Sitewide | Digital/construction | Digital | Actualised | Visual method statements / sequencing - Videos, 4d sequening in model, slide packs with step by step. | FSR Chain of Responsibility | Visuals overcome language and literacy barriers, ensuring the workforce fully understands the sequence. 4D sequencing identifies spatial clashes and pinch points virtually before they become physical hazards on site. | Mandate visual outputs for all High Risk Construction Work (HRCW) reviews and store in the project document management system. |  | Michael Spencer | Multiple uses from explanations to craft crew on site, visualising planning works with subcontractors etc.
Byford Rail Extension | BRE008 | 2024-08-18 | Linewide | Track | Design | Actualised | Narrow gauge guard rail sleeper design - removed the requirement for load bearing walls on viaduct approaches and wungong brook | FSR Formwork FSR Piling FSR Cranes and Lifting | Removing load-bearing walls eliminates the entire sequence of high-risk works: it removes the need for piling (ground risk), formwork erection (manual handling), and heavy lifting operations associated with wall construction. | Ensure "As-Built" drawings reflect the sleeper design change and document the significant reduction in piling and concrete scope in the register. |  | Lee Mclaughlin
Byford Rail Extension | BRE009 | 2024-08-18 | Linewide | Track | Design | Actualised | Expanding rail damper quantites to reduce noise walls along the alignment | FSR Piling FSR Cranes and Lifting | Treating noise at the source (track level) removes the need for building large physical noise walls, thereby eliminating the high-risk piling foundations and heavy lifting of concrete wall panels associated with them. | Verify final noise model compliance and record the reduction in construction footprint/risk in the Lessons Learnt register. |  | Lee Mclaughlin
Byford Rail Extension | BRE010 | 2024-08-18 | Linewide | Track | Plant | Actualised | Re-use of recovered turnouts to shunt rolling stock across tracks avoids a requirement to crane machines across - temporary crossovers | FSR Cranes and Lifting | Using turnouts to drive plant/machinery across tracks completely removes the need to lift heavy equipment over the rail corridor, preventing potential dropped load incidents. | Document the logistics plan in the Lessons Learnt register, highlighting the safety value of reusing recovered assets for temporary works. |  | Lee Mclaughlin
Byford Rail Extension | BRE011 | 2024-08-18 | Linewide | Track | Material | Actualised | automated ballast box reduce exposure to noise/dust?? Fixed to loader & operated from cab. Walking floors feeding ballast. Less line of fire , dust exposure, manual handling, uneven surfaces… | FSR Plant and Equipment FSR Railway Operations | Operating from the cab removes workers from the "line of fire," preventing crush injuries. Eliminates manual handling strain, reduces exposure to silica dust/noise, and removes slip/trip hazards on uneven ballast. | Document the equipment specifications and safety benefits in the Lessons Learnt register for future track works. |  | Lee Mclaughlin
Byford Rail Extension | BRE012 | 2024-08-18 | Linewide | OLE | Plant | Actualised | Movax & hammer attachment to 36t excavator to install CHS piles for OLE - rather than bored piles. Excavation, cages, concrete, bla bla piling lifting | FSR Piling FSR Plant and Equipment FSR Cranes and Lifting | Driven piles eliminate the risk of falls into open boreholes. Eliminates steel cage fabrication, concrete pumping, and the associated heavy lifting/manual handling. Removes exposure to wet concrete (burns) and silica dust. | Update the piling methodology in the project management plan and record the efficiency/safety gains in the Lessons Learnt register. |  | Lee Mclaughlin
Byford Rail Extension | BRE013 | 2024-08-18 | Linewide | Track | Methodology | Actualised | FBW yards making LWR reduce exposure to in situ welds, weld flash, burns, grinding, manual handling | FSR Plant and Equipment FSR Railway Operations | Shifting to automated yard welding eliminates the high risks of field welding: specifically exposure to weld flash/fumes, burns from molten metal, manual grinding dust, and the heavy manual handling of welding kits. | Document the reduction in field weld counts and associated injury reduction in the Lessons Learnt register. |  | Lee Mclaughlin
Byford Rail Extension | BRE014 | 2024-08-18 | Viaduct | Piling | Methodology | Actualised | Large reduction in pile break back as piles were overpoured and excess concrete removed while wet rather than traditional breaking back / cropping | FSR Cranes and Lifting FSR Excavation FSR Plant and Equipment | Removing concrete while it is still wet eliminates the need for high-intensity mechanical breaking (jackhammering). This removes worker exposure to Hand-Arm Vibration Syndrome (HAVS), dangerous noise levels, and respirable silica dust. | Record the specific technique used (e.g., vacuum or mechanical scoop) in the Lessons Learnt register to promote "Green Cropping" on future piling works. |  | Sean Doherty / Simon Poggioli | Traditional cropping & Breakback involves drilling, breaking, pinch points, dust, lifting. Manual handling
Byford Rail Extension | BRE015 | 2024-08-18 | Viaduct | Structures | Scaffolding | Actualised | Use of scissor lifts to access headstocks remove scaffolding each column location | FSR Scaffolding | Replacing static scaffolding with Mobile Elevating Work Platforms (MEWPs) eliminates the high-risk manual tasks of erecting and dismantling scaffold towers, significantly reducing manual handling and exposure to height. | Ensure all operators hold valid MEWP licenses and record the reduction in temporary works hours in the Lessons Learnt register. |  | Sean Doherty / Simon Poggioli | Traditional Scaffolfing - Manual handling, work at heightsrepetitive climbing up and down stairs.
Byford Rail Extension | BRE016 | 2024-08-18 | Viaduct | Structures | Methodology | Actualised | Rubber bearing under beams instead of grout pads - working at heights | FSR Working at Height FSR Formwork & Falsework | Rubber bearings are "dry placed," removing the need to install formwork, mix grout, and pour at height, significantly reducing fall risk and manual handling. | Document the design change in the Lessons Learnt register. |  | Sean Doherty / Simon Poggioli | Single rubber bearing places on top of headstock from EWP. As opposed to fixing & forming a grout pad (manual handling) mixing and placing grout (dust, chemicals exposure)
Byford Rail Extension | BRE017 | 2024-08-18 | Viaduct | Structures | Precast | Actualised | Sequence of precast deck plank install specific to progressively create secure deck with fall restraint controlling the risk of falling from open edge. Reduced working from EWP to install planks. Edge protection from beams at both ends and bolt down edge protection pre installed on the first plank. | FSR Working at Height | The sequence ensures workers are always behind a physical barrier or on a secured deck, reducing reliance on personal fall arrest systems and EWPs. | Standardise this installation sequence in the SWMS for future deck works. |  | Sean Doherty / Simon Poggioli | Installing precast planks fully from EWP involves possiblity of strains from manouvering the planksby leaning out of the EWP basket.
Byford Rail Extension | BRE018 | 2024-08-18 | Viaduct | Structures | Precast | Actualised | Precast column design - Reduced risks associated with In situ reinforcement, formwork in situ pouring. Reduced risk of rework fitting together | FSR Working at Height FSR Formwork & Falsework FSR Crane and Lifting | Shifts steel fixing and shuttering from vertical alignment at height to horizontal fabrication on the ground. Reduces duration of work at elevation. | Record the reduction in site hours and rework rates in the Lessons Learnt register. |  | Sean Doherty / Simon Poggioli | Precast column lifted straight onto starters and tolerances built into the system for fittment. All installed with EWP. No long term working at height to stick build reo then crane formwork and pour in situ at height with boom pumps. Noise, vibration
Byford Rail Extension | BRE019 | 2024-08-18 | Viaduct | Structures | Precast | Actualised | For precast plank in situ stitches, the reo was preloaded and secured into the plank stitch at ground level prior to lifting plank into position. This allowed the bars to be slid into final position and tied off ready for pour. | FSR Working at Height FSR Crane and Lifting | the time workers spend leaning over open voids to install steel. Moves the dexterity-heavy task to a safe ground-level environment. | Capture the methodology in the steel fixing work pack. |  | Sean Doherty / Simon Poggioli | Reduced need to crane big bundles of reo up onto vuaduct then separate bars and manually handle to stitch location to place. Drastically improve ease of installing long bars in congested area reducing cuts, pinches stress on fixers trying to squeeze bars into place.
Byford Rail Extension | BRE020 | 2024-08-18 | Viaduct | Structures | Modularisation | Opportunity | Inclusion of modular cranable stairs to give access up and over the horizontal temp works megashore props (mounted at chest height)along the viaduct. This engineered in health removes the need to crouch underneath each prop as people traverse along the viaduct during construction. | Improves accessability and people done have to crouch under obstacles | Eliminates the need for repetitive crouching and crawling under heavy falsework, preventing back strain and head strike hazards. | Ensure stair modules are cataloged for reuse on future projects with similar propping. |  | Sean Doherty / Simon Poggioli
Byford Rail Extension | BRE021 | 2024-08-18 | Viaduct | Structures | Management | Actualised | Based on lessons learnt from recent Working at heights PC1 incidents, a robust process for managing working at heights was compiled, peer reviewed and introduced. Work at heights induction, Works planning of colour coded exclusion zones, Detailed review of methodologies, Deck access sheets, W@H Marshal etc.. | FSR Working at height Control of risks of dropped objects | Provides a multi-layered defense against falls and dropped objects through stricter administrative controls, better visualization of hazards, and dedicated supervision. | Conduct a post-implementation review to measure the effectiveness of the new protocols. |  | Sean Doherty / Simon Poggioli | ES Forum specifically requested this as the main topic of presentation.
Byford Rail Extension | BRE022 | 2024-08-18 | Viaduct | Structures | Material | Actualised | Increased planks width by 33% from 2.4m to over 3m. This reduced the number of crane lifts by 33% and | FSR Cranes and lifting Reduced manual handling | Fewer lifts mean 33% less time where workers are exposed to suspended loads. Also reduces the total linear meters of joint grouting (manual handling). | Document the design efficiency and lifting reduction in the Lessons Learnt register. |  | Sean Doherty / Simon Poggioli | Bigger panels mean less lifts (less rigging, less manually handling heavy panels into place, less opportunity for pinches/muscle strains. Less in situ stitches
Byford Rail Extension | BRE023 | 2024-08-18 | Viaduct | Structures | Methodology | Actualised | Foldable handrails preinstalled in beams at ground lvl - work at heights | FSR Working at height Control of risks of dropped objects | Edge protection is active immediately upon installation, removing the critical risk period where workers would typically install rails at height. Prevents dropped objects during rail fixing. | Verify the lifting lifting plan accounts for the pre-installed rail weight. |  | Sean Doherty / Simon Poggioli | Having the handrails with the ability to fold flat enabled them to be installed prior to transporting and installing. When folded, there is no risk of fouling rigging etc. Then wien lifted into position, they can be stood up and
Byford Rail Extension | BRE024 | 2024-08-18 | Viaduct | Structures | Digital | Actualised | 3d model all reo to reduce fitment issues on site - bending, cutting less surprises allowed for preloading, sequencing engineered planning | FSR Chain of Responsibility | Eliminates the need for ad-hoc bending and cutting of steel on site, reducing manual handling strain and the risk of lacerations or pinch points. | Archive the 3D models and clash detection reports as evidence of Safety by Design. |  | Sean Doherty / Simon Poggioli
Byford Rail Extension | BRE025 | 2024-08-18 | Viaduct | Structures | Plant | Actualised | 1 temp crane pad to allow unlimited movements for larger crawler crane and minimise multiple smaller crane setups. Minimise risk temp works & underground services. | FSR Utilities and Services | Reduces the frequency of high-risk crane mobilization/demobilization. Protecting underground services from repeated ground pressure changes. | Document the pad design and service location verification in the project records. |  | Sean Doherty / Simon Poggioli
Byford Rail Extension | BRE026 | 2024-08-18 | Viaduct | Structures | Plant | Actualised | Temp services lighting & water to viaduct makes area safer in low light and easier access to water - dust, less movements with trums of water etc. | FSR Utilities and Services | Good lighting reduces trip hazards. Piped water eliminates the manual handling of water drums and ensures dust suppression is always available (silicosis prevention). | Ensure maintenance schedule for temporary services is active. |  | Sean Doherty / Simon Poggioli
Byford Rail Extension | BRE027 | 2024-08-18 | Viaduct | Structures | Methodology | Actualised | coordination & design of temp & perm cast ins to eliminate post fixing - manual handling, hammer drilling, noise, dust etc… | FSR Plant and Equipment | Removes the need for hammer drilling into concrete, eliminating exposure to silica dust and noise. | Record the reduction in post-drill anchors in the Lessons Learnt register. |  | Sean Doherty / Simon Poggioli
Byford Rail Extension | BRE028 | 2024-08-18 | Viaduct | Structures | Design | Actualised | monopile design reduces pilecaps, - excavation, form pour | FSR Piling FSR Excavation | Completely removes the risks associated with deep excavation (collapse/entrapment) and heavy piling rig operations. | Highlight this major risk reduction in the project design review. |  | Sean Doherty / Simon Poggioli
Byford Rail Extension | BRE029 | 2024-08-18 | Viaduct | Structures | Methodology | Actualised | DE to plan & coordinate simops for planning… removed stresses & risks of congestion in workfronts | FSR Chain of Responsibility | Systematically manages congestion to prevent plant-on-plant or plant-on-pedestrian collisions in tight workspaces. | Maintain daily coordination meeting records. |  | Sean Doherty / Simon Poggioli
Byford Rail Extension | BRE030 | 2024-08-18 | Wungong Rail bridge | Structures | Methodology | Actualised | Early engagenment of temp works allowed In depth analysis & iterations of temp works design to use permanent works substructure for efficient & safer solution - wedge jacks & hardwood for stabilisation | FSR Formwork & Falsework | Replaces ad-hoc propping with engineered solutions using permanent structures, reducing the risk of temporary works collapse. | Validate the temporary works design certificate. |  | Mo Abu Abdu
Byford Rail Extension | BRE031 | 2024-08-18 | Wungong Rail bridge | Structures | Digital | Actualised | Prior detailed survey of precast Beams planks incl ferrules & projecting bars & 3d modelling for clash detection reduced clashes on site. Less reworks bending bars, cutting concrete & reduced risks of pinch points/muscle strains. | FSR Precast and Tilt up Concrete | Prevents on-site clashes that require dangerous remedial work (cutting concrete/bending bars), reducing pinch points and muscle strains. | Share the clash detection success rate in the quality report. |  | Mo Abu Abdu
Byford Rail Extension | BRE032 | 2024-08-18 | Wungong Rail bridge | Structures | Methodology | Actualised | rationalising of the plank plank waterprroofing detail to reduce products being applied under conjested reinforcement areas. Less pinches/cuts strains. Less time working in crouched positions. | FSR Chain of Responsibility | Reduces the time workers must spend in crouched, awkward positions within tight steel cages, preventing back strain and cuts. | Update standard details for future waterproofing scopes. |  | Mo Abu Abdu
Byford Rail Extension | BRE033 | 2024-08-18 | Wungong both bridge | Structures | Methodology | Actualised | Installed temp retaining wall at interface at brook to provide flat working platform during construction. This was paired with perm style fence to protect workforce from the stresses of accidently encroaching on the exclusion zone of the heritage area brook. | FSR Excavation | Prevents workers or plant from sliding into the water/heritage area and provides a stable surface for machinery. | Ensure removal plan is in place upon completion. |  | Mo Abu Abdu
Byford Rail Extension | BRE034 | 2024-08-18 | Wungong both bridge | Structures | Scaffolding | Actualised | Temp works scaffold bridge giving easy access over the brook rather than having restricted access having to travel around the road to access each site. | FSR Scaffolding | Segregates workers from live traffic (road) and prevents slips/falls associated with crossing the brook on uneven terrain. | Inspect scaffold tags weekly to ensure compliance. |  | Mo Abu Abdu
Byford Rail Extension | BRE035 | 2024-08-18 | Eleventh Rd Bridge | Structures | Modularisation | Actualised | Modularised falsework system built at ground level (reduced Working at heights) single system serving column support and also deck falsework for sill beam pours. Sized to allow for material storage and also construction loads. - Less trips up & down stairs. Less lifts of material up and down with cranes. Penetrations (controlled) in deck allowed Column forms & reo be installed through it - work at height. Mesh barriers controlling dropped objects. All done in 1 operation reduced time the "high risk" otems were open for.. | FSR Formwork & Falsework FSR Working at Heights | Ground assembly minimizes height exposure. Integrated material storage reduces trips and the number of crane lifts required for materials. | Document the cycle time and safety benefits for future falsework planning. |  | Mo Abu Abdu
Byford Rail Extension | BRE036 | 2024-08-18 | Eleventh | Structures | Modularisation | Actualised | Prefab of column reo at ground level and lifted into position as single lift. Temp works allowed for prefab of cage , and use of sacrificial column form (wrap R95 column former) Lightweight - reduced manual handling & muscle strains - easy to handle Also reduced stripping time (stanley knofe to split open) | FSR Working at Heights FSR Crane and Lifting | Shifts steel fixing from vertical work at height to horizontal ground work. Lightweight forms reduce manual handling strain and "Stanley knife" stripping risks. | Update the SWMS to reflect the single-lift methodology and lightweight formwork requirements. |  | Mo Abu Abdu
Byford Rail Extension | BRE038 | 2024-08-18 | Wungong both bridge | Structures | Methodology | Actualised | Water leak tests over enviro heritage brook | FSR Work On, Over Or Adjacent to Water | Prevents contamination of the heritage brook and ensures no water ingress affects the structural integrity near the water body. | Archive test results and environmental monitoring records. |  | Mo Abu Abdu
Byford Rail Extension | BRE039 | 2024-08-18 | Eleventh | Structures | Modularisation | Actualised | Screens being modularised - fabricated offsite & lift into place - less w@H manual handling | FSR Working at Heights FSR Crane and Lifting | Reduces the duration of work at heights for screen installation and minimizes manual handling of individual components. | Document the lifting plan for the modular screens in the construction management plan. |  | Mo Abu Abdu
Byford Rail Extension | BRE040 | 2024-08-18 | Eleventh Rd Bridge | Structures | Material | Actualised | MSE walls with screening- worked with suppliers & transport providers to use the max height single panels. Reduced the number of secondary stacked panels to be installed. | FSR Working at Heights FSR Crane and Lifting | Makes stack panel installation easier and quicker, reducing the time riggers spend positioning heavy loads. | Standardise top lifters for all future MSE panel installations. |  | Mo Abu Abdu
Byford Rail Extension | BRE041 | 2024-08-18 | Eleventh Rd Bridge | Structures | Precast | Actualised | MSE walls screen panels. Lessons learnt from previous jobs using top lifters in lieu of face lifters to make stack panel install easier & quicker | FSR Crane and Lifting FSR Precast and Tilt up Concrete | Top lifters allow panels to hang perfectly vertical (plumb), making stacking on top of each other significantly easier. This reduces the need for manual handling to guide the load and keeps hands away from pinch points between panels. | Update the Lifting Permit requirements to mandate top lifters for all stackable panels. |  | Mo Abu Abdu
Byford Rail Extension | BRE042 | 2024-08-18 | Eleventh Rd Bridge | Structures | Design | Actualised | MSE walls coordinated design with interfacing services and included blockouts in the precast panels to bridge sercices - elimate need fo rin situ bridging slabs - all the risks | FSR Formwork & Falsework FSR Utilities and Services | Removes the need to construct small, awkward in-situ bridging slabs over live services. This eliminates the associated formwork fabrication, steel tying, and concrete pouring in congested zones. | Archive the coordinated design drawings showing the service interfaces. |  | Mo Abu Abdu
Byford Rail Extension | BRE043 | 2024-08-18 | Eleventh | Structures | Design | Actualised | Rationalised and reduced number of piles in abutments 12 nos to 11 | FSR Piling | Reduces the overall risk exposure associated with piling rig operations and heavy machinery movements. | Update the foundation layout drawings to reflect the reduction. |  | Mo Abu Abdu
Byford Rail Extension | BRE044 | 2024-08-18 | Eleventh | Structures | Methodology | Actualised | CHS columns were proposed to have rubber filling to create void. Introduced structural spacers to guarantee airgap and eliminate rubber packing. - reduce producing and handling of shredded rubber & working at heights/dropped objects/manual handling. | FSR Working at Heights | Eliminates the need for workers to manually pack rubber at height, preventing potential dropped objects and manual handling strain. | Record the spacer specification in the procurement register. |  | Mo Abu Abdu
Byford Rail Extension | BRE045 | 2024-08-18 | Eleventh Rd Bridge | Structures | Methodology | Actualised | adjusted works sequencing around beam installation. Allowed dual cranes lifts. Reducing time of activity and giving a more controlled lifts with reduced manual handling of rigging gear. Southern deflection works pushed to later point to eliminate interface with public/live traffic | FSR Cranes and Lifting | Provides more controlled lifts and reduces manual handling of rigging gear by optimizing the center of gravity management. | Review the dual lift plan with the crane supervisor. |  | Mo Abu Abdu
Byford Rail Extension | BRE046 | 2024-08-18 | Eleventh | Structures | Material | Actualised | Cog bars on pile starter bars swapped out for griptech mechanical splice solution. Reduced manual handling, strains, pinches from installing heavy cogged bars. | FSR Plant and Equipment | Removes the manual handling and pinch risks associated with installing heavy cogged bars. | Ensure the splicing equipment is certified and operators are trained. |  | Mo Abu Abdu
Byford Rail Extension | BRE047 | 2024-08-18 | Eleventh | Structures | Material | Actualised | Cog bars on sill beam swapped out for BT headed anchors. Reduced manual handling, strains, pinches from installinf heavy cogged bars. Also enabled above mentioned smart deck temp works | FSR Plant and Equipment | Reduces manual handling strains and pinch points from installing heavy cogged reinforcement bars. | Update the reinforcement schedule to specify BT anchors. |  | Mo Abu Abdu
Byford Rail Extension | BRE048 | 2024-08-18 | Larson Rd Pedestrian Bridge | Structures | Design | Actualised | 32 piles omitted from design through working with size of footings & embeddment of walls. | FSR Piling FSR Excavation | Completely removes the safety risks associated with drilling, concreting, and spoiling for 32 piles. | Highlight the quantity reduction in the project efficiency report. |  | Mo Abu Abdu
Byford Rail Extension | BRE049 | 2024-08-18 | All South Structures | Structures | Precast | Actualised | Coordinated all temp & perm works ferrules into precast - eliminate post fixing. | FSR Plant and Equipment | Eliminates the need for post-fixing anchors, reducing exposure to drilling vibration, noise, and dust. | Check ferrule locations during the pre-pour inspection. |  | Mo Abu Abdu
Byford Rail Extension | BRE050 | 2024-08-18 | Larson Rd Pedestrian Bridge | Structures | Modularisation | Actualised | standardisation of pier sizes to use existing steel form with inbuilt walkways & edge protection - | FSR Working at Heights FSR Formwork & Falsework | Provides safe, integrated access for workers during pouring and inspection, removing the need for separate scaffold towers. | Maintain the steel forms to ensure walkways remain compliant. |  | Mo Abu Abdu
Byford Rail Extension | BRE051 | 2024-08-18 | Byford | Stations | Precast | Actualised | Platform walls changed from precast with insitu cantilevering slab to full precast Z shape panel. Panels were designed to be self supporting during backfill and in a way that did not require stitch pours. This resulted in less temporary works requirements and increased programme effeciency. | FSR Formwork & Falsework FSR Precast and Tilt up Concrete | Replacing the in-situ cantilever slab eliminates the need for complex formwork erection and steel fixing at the platform edge. Self-supporting panels remove the reliance on temporary propping during backfill, reducing the risk of temporary works failure or collapse. | Ensure the Z-panel design and backfilling methodology is captured in the project Lessons Learnt register for future station builds. |  | Daryl Henderson
Byford Rail Extension | BRE052 | 2024-08-18 |  | Stations | Modularisation | Actualised | prefab buildings at armadale - Brick slips - | FSR Working at Heights | Moves bricklaying work from height to a controlled factory environment. | Verify the lifting points on the prefab modules. |  | Daryl Henderson
Byford Rail Extension | BRE053 | 2024-08-18 | Armadale | Stations | Precast | Actualised | Passenger access chairs designed as precast columns and flights. Removal of falsework design and temporary works requirements in favour of crane lifting. Flights to come with handrail preinstalled. Overall reduction in working at heights. | FSR Working at Heights FSR Crane and Lifting | Removes falsework design and temporary works requirements; lifting pre-assembled stairs reduces time spent working at height. | Ensure the lifting study accounts for the pre-installed handrails. |  | Daryl Henderson
Byford Rail Extension | BRE054 | 2024-08-18 |  | Stations | Material | Actualised | blockwork changed to prefab steel wall framing - manual handling | FSR Working at Heights | Replaces heavy manual block laying at height with lighter steel frame installation, reducing fatigue and fall risks. | Update the architectural specification to reflect steel framing. |  | Daryl Henderson
Byford Rail Extension | BRE055 | 2024-08-18 |  | Stations | Modularisation | Actualised | Mondularising canopy sections | FSR Working at Heights | Reduces the number of personnel involved in overhead work and shortens the duration of high-risk activities. | Coordinate delivery logistics to minimize site storage time. |  | Daryl Henderson
Byford Rail Extension | BRE056 | 2024-08-18 | Armadale | Stations | Modularisation | Actualised | Design of modularised uni-strut style support frame for Armstrong V-P500 baffle ceiling. Reduction in persons involved in and durations of working at heights. Reduction in plant within congested area. Programme optimization ie: reduction in duration of drop zones allows greater productivity at lower level. | FSR Working at Heights FSR Plant and Equipment | Prefabrication significantly cuts the number of personnel and duration required at height. Reducing plant requirements in congested areas lowers the risk of plant-pedestrian collisions and dropped objects. | Record the specific schedule savings (drop zone duration reduction) in the Lessons Learnt register. |  | Daryl Henderson
Byford Rail Extension | BRE057 | 2024-08-18 |  | Stations | Modularisation | Actualised | Viaduct fins modularise | FSR Working at Heights | Reduces the need for complex access systems and prolonged work on the viaduct edge. | Monitor the installation process for lessons learnt. |  | Daryl Henderson
Byford Rail Extension | BRE058 | 2024-08-18 |  | Stations | Material | Actualised | eliminated stone cladding to replace with lighter weight GRC | FSR Crane and Lifting | GRC is significantly lighter than stone, reducing lifting risks and manual handling load during final positioning. | Confirm GRC panel weights for the lifting plan. |  | Daryl Henderson
Byford Rail Extension | BRE059 | 2024-08-18 | Armadale | Stations | Modularisation | Actualised | Structural steel liftcores prefabricated as single uint c/w ventilation louvres and roof/housing installed and crane lifted into place. Reduction in persons involved in and durations of working at heights. | FSR Working at Heights FSR Crane and Lifting | Drastically reduces personnel involvement in vertical shaft work and eliminates multiple lifting operations. | Ensure the shaft tolerance matches the prefab core dimensions. |  | Daryl Henderson
Byford Rail Extension | BRE060 | 2024-08-18 |  | Stations | Modularisation | Actualised | Eastern wind wall prefab +I68:J101& lift in. | FSR Working at Heights FSR Crane and Lifting | Reduces total man-hours spent working on exposed edges and minimizes the number of small component lifts. | Review lifting plan for modular sections. |  | Daryl Henderson
Byford Rail Extension | BRE061 | 2024-08-18 |  | Stations | Digital | Actualised | How are we surveying? Pre fitting reflectors? | FSR Working at Heights FSR Plant and Equipment | Removes need for surveyors to access structure at height or work near operating plant to install targets. | Validate accuracy of pre-fitted targets. |  | Daryl Henderson
Byford Rail Extension | BRE062 | 2024-08-18 | Armadale | Stations | Modularisation | Actualised | Construction of prefabricated buildings to be on hydraulic jacks/stilts removing any requirement for crane lifting onto tranport. Reduction in high risk activity and reduction in persons involved in high risk activities. | FSR Crane and Lifting | Eliminates high-risk crane lifts to load buildings onto transport; removes riggers from crush zones. | Verify SWMS for hydraulic jacking. |  | Daryl Henderson
Byford Rail Extension | BRE063 | 2024-08-18 | Both Stations | Stations | Design | Actualised | Specification dispensation sought to reduce typical in-ground footing depth from >2m below FFL to below ground slab (and platform level) slab. Reduction in excavation depth and temporary works. | FSR Excavation | Reduces excavation depth, minimizing trench collapse risk and need for complex shoring. | Archive approved dispensation. |  | Daryl Henderson
Byford Rail Extension | BRE064 | 2024-08-18 | Both Stations | Stations | Design | Actualised | Design review and optimisation of services routes to utilise common trenches were possible and reduce excavation depths. | FSR Excavation FSR Utilities and Services | Reduces total excavation footprint and lowers risk of striking unmapped underground services. | Update Combined Services Drawing. |  | Daryl Henderson
Byford Rail Extension | BRE065 | 2024-08-18 | Sitewide | Civil | Design | Actualised | Rationalisation & Removal of Retaining walls by introduction of steeper treated batters, RCB culvert & RCP crossings | FSR Formwork & Falsework FSR Excavation | Eliminates vertical wall construction, removing associated formwork, steel fixing, and concrete hazards. | Monitor batter stability. |  | Aaron Godfrey
Byford Rail Extension | BRE066 | 2024-08-18 | Sitewide | OLE | Design | Actualised | Placement of OLE structures over 3m from track creates clear zone for construction of track works. | FSR Railway Operations FSR Plant and Equipment | Allows works to proceed without entering the rail danger zone, reducing plant-train interface risks. | Confirm clearance in As-Builts. |  | Kevin O'Meara
Byford Rail Extension | BRE067 | 2024-08-18 | Sitewide | OLE | Methodology | Actualised | Quick Release hitches on OLE Tag Lines which allows riggers to unhook the load from the ground | FSR Working at Heights FSR Crane and Lifting | Eliminates need for riggers to climb or use EWPs to detach rigging from vertical members. | Train crew on hitch usage. |  | Lee Mclaughlin
Byford Rail Extension | BRE068 | 2024-08-18 | Sitewide | Track | Methodology | Actualised | Design of temp site flash but welding yards. Rail raised and platforms at each step of welding process for ease of grinding, welding inspecting. | FSR Railway Operations | Improves ergonomics by allowing welding/inspection at waist height, reducing fatigue/strain. | Conduct ergonomic assessment. |  | Kev O'Meara
Byford Rail Extension | BRE069 | 2024-08-18 | Sitewide | Track | Plant | Actualised | LOR designed Track Jigs are lighter weight than traditional Iron Horse system - Reduced risk in manual handling | FSR Plant and Equipment | Reduces manual handling load during track construction and minimizes crush risks. | Add to equipment register. |  | Kevin O'Meara
Byford Rail Extension | BRE070 | 2024-08-18 | Sitewide | Track | Material | Actualised | Re use of sleepers reduce need to cast more also risk of exposure to heavy haulage | FSR Plant and Equipment | Reduces heavy haulage traffic entering site, lowering vehicle-pedestrian collision risk. | Document sustainability savings. |  | Kevin O'Meara
Byford Rail Extension | BRE071 | 2024-08-18 | Sitewide | Track | Precast | Actualised | Fixed buffer stops in sidings opposed to earth mounds. Fabricated off site rather than machine work | FSR Plant and Equipment | Eliminates need for heavy earthmoving machinery to construct mounds on site. | Verify design compliance. |  | Kevin O'Meara
Byford Rail Extension | BRE072 | 2024-08-18 | Sitewide | Track | Material | Actualised | Introductionof fibre reinforced track slab reduce steelfixing risks etc… | FSR Plant and Equipment | Eliminates manual handling of steel fixing and trip hazards on mesh during pours. | Check fibre mix consistency. |  | Kevin O'Meara
Byford Rail Extension | BRE073 | 2024-08-18 | Sitewide | Civil | Design | Actualised | Reduced embankment fill quantity by optimising design levels. | FSR Plant and Equipment | Reduces truck/trailer movements on site, lowering traffic management risks. |  |  | Brenton Talbot
Byford Rail Extension | BRE074 | 2024-08-18 | Sitewide | Civil | Plant | Actualised | Procured an engineered MSE strap carrier to reduce manual handling | FSR Plant and Equipment | Reduces grip fatigue and strain for workers installing reinforcement straps. | Induction on tool usage. |  | Brenton Talbot
Byford Rail Extension | BRE075 | 2024-08-18 | Sitewide | Civil | Drainage | Actualised | Numerous instances of drainage being redesigned away from underground services | FSR Utilities and Services | Prevents utility strikes and eliminates high-risk potholing near live assets. | Update clash detection report. |  | Brenton Talbot
Byford Rail Extension | BRE076 | 2024-08-18 | Sitewide | Civil | Precast | Actualised | Precast L-wall panel design to reduce FRP time on site. | FSR Formwork & Falsework | Reduces site time for steel/formwork, minimizing exposure to concrete hazards. | Approve precast design change. |  | Brenton Talbot
Byford Rail Extension | BRE077 | 2024-08-18 | Sitewide | Civil | Management | Actualised | Developed traffic staging to maximise closures to minimise traffic interface. | FSR Traffic Management | Segregates workforce from live traffic, eliminating risk of errant vehicles entering work zone. | Archive Traffic Management Plans. |  | Brenton Talbot
Byford Rail Extension | BRE078 | 2024-08-18 | Sitewide | Civil | Piles | Actualised | Noise wall design used a driven CHS pile installed by an excavator which avoid the need for piling rigs | FSR Piling FSR Plant and Equipment | Removes need for heavy piling rigs and eliminates open borehole hazards. | Verify pile installation records. |  | Brenton Talbot
Byford Rail Extension | BRE079 | 2024-08-18 | Sitewide | Civil | Rail - noise walls | Actualised | Noise wall design uses plastic noise wall panels which are mostly installed from the ground by hand, elimenating the need for cranes required when using concrete panels. | FSR Cranes and Lifting | Eliminates crane usage for install and reduces manual handling weight vs concrete. | Review wind loading specs. |  | Brenton Talbot
Byford Rail Extension | BRE080 | 2024-08-18 | Sitewide | Civil | Digital | Actualised | Majority of machines using GPS machine control models to significantly reduce surveyors on ground (manual handle with pegs in heat and rain) and adding service so they know where underground services are to avoid striking | FSR Plant and Equipment | Removes surveyors from plant operating zones; prevents utility strikes via digital avoidance. | Verify GPS model updates. |  | Josh Collins
Byford Rail Extension | BRE081 | 2024-08-18 | Sitewide | Civil | Precast | Actualised | Replaced small insitu headwalls with precast to reduce formwork fixing, steel tying and concrete placement activities | FSR Formwork & Falsework | Reduces formwork fixing, steel tying, and concrete placement activities in trenches. | Standardise headwall details. |  | Josh Collins
Byford Rail Extension | BRE082 | 2024-08-18 | Sitewide | Civil | Management | Actualised | General scope reduction and refinement of design to reduce overall manhours required to complete works | FSR Chain of Responsibility | Reducing total work hours directly correlates to a reduction in overall injury exposure. | Track manhour reduction data. |  | Josh Collins
Byford Rail Extension | BRE083 | 2024-08-18 | Sitewide | Civil | Methodology | Actualised | PSP and DCP correlations approved to reduce the amount of nuclear density testing that the technican is exposed to and reduces 20kg MMDD samples that the technican needs to dig and load onto his ute | FSR Excavation | Reduces radiation exposure risk and manual handling of 20kg soil samples. | Update testing inspection plan. |  | Josh Collins
Byford Rail Extension | BRE084 | 2024-08-18 | Sitewide | Civil | Management | Actualised | Got ballast reuse approved which allowed for more cut to fill onsite with a dozer, instead of loading out the material for disposal, which would introduce more truck movements and onsite congestion | FSR Traffic Management | Avoids loading out material for disposal, reducing truck movements and congestion. | Monitor material quality. |  | Josh Collins
Byford Rail Extension | BRE085 | 2024-08-18 | Sitewide | Sitewide | Methodology | Opportunity | Review of project incident actions to pull out Actualised and opportunity items | FSR Chain of Responsibility | Ensures lessons from past incidents are formally integrated into current safety practices. | Distribute review findings. |  | Ryan McGurk
Byford Rail Extension | BRE086 | 2024-08-18 | Sitewide | Sitewide | Methodology | Opportunity | Real time silica monitoring | FSR Chain of Responsibility | Provides immediate alerts to hazardous dust levels, allowing instant respiratory protection. | Calibrate monitoring units. |  | Ryan McGurk
Byford Rail Extension | BRE087 | 2024-08-18 | Sitewide | Sitewide | Methodology | Opportunity | Preference to greencut concrete rather than scabbling to reduce exposure to vibration, dust, noise | FSR Plant and Equipment | Eliminates vibration, noise, and silica dust generation from mechanical scabbling. | Update concrete finishing spec. |  | Ryan McGurk
Byford Rail Extension | BRE088 | 2024-08-18 | Sitewide | Sitewide | Plant | Opportunity | Specialist tamper operators are straining to enter/exit tampers. Opportunity for step set / lift? Engineer in Health | FSR Plant and Equipment | Reduces musculoskeletal strain and slip/fall risks for operators climbing into large machinery. | Retrofit steps to tampers. |  | Ryan McGurk
Byford Rail Extension | BRE089 | 2024-08-18 | Sitewide | Sitewide | Methodology | Opportunity | Improved access for rock pitchers. | FSR Excavation | Prevents slips, trips, and falls on uneven terrain for workers placing rock protection. | Inspect access routes weekly. |  | Ryan McGurk
Byford Rail Extension | BRE090 | 2024-08-18 | Sitewide | Sitewide | Management | Opportunity | Ideas sessions with supervision. | FSR Chain of Responsibility | Increases safety engagement and captures frontline knowledge for hazard identification. | Schedule monthly sessions. |  | Ryan McGurk
Byford Rail Extension | BRE091 | 2024-08-18 | Sitewide | Quality | Management | Opportunity | Increased focus on quality first time eliminates rework and reduces unnecessary exposure to high risk works. | FSR Chain of Responsibility | Prevents unnecessary re-exposure to high-risk works caused by fixing defects. | Track rework metrics. |  | John Forde
Byford Rail Extension | BRE092 | 2024-08-18 | Armadale | Stations | Modularisation | Actualised | Armadale Station entry ceiling mural. Converrt design to introduce a modularised false ceiling with artwork painted & lights installed at ground level | Improved health by eliminating artist neck strains painting on ceilings. FSR working at height | Eliminates neck strains from painting overhead and fall risks associated with working at height. | Approve lifitng plan for ceiling |  | Tony Barberis
Byford Rail Extension | BRE093 | 2024-08-18 | Sitewide | Structures | Plant | Opportunity | Use of Vita load navigator rigging equipment to improve load Manouverability and stability in wind (Refer to Demo that took place on FBA project) | improved health by reducing strains from tag lines & line of fire injury from unplanned load movement. FSR Cranes & Lifting, FSR Working at Height, FSR Precast and Tilt up Concrete, FSR formwork & Falsework | Eliminates need for tag lines, reducing strain and keeping riggers away from the load line of fire. | Train riggers on device. |  | Michael Spencer
EBTA | EBTA001 | 2025-11-05 | NEL-STH-NSA-5100-CRF-REP-0002 | DESIGN REPORT - B072 – 5100/5200 Power and Comms | Design | Completed | ITS Roadside cabinet moved Off Freeway to SUP where possible to provide safety to maintenance person. Efforts were made to ensure cabinets were located behind noise walls where possible. E.g., Behind Noise wall - RCB – W-002 - West DB2 - RCB-W-003 - RCB-W-012 - RCA-9930 E.g., Behind Retaining wall. - RCB-W-004 - RCA-9902 - RCA-9943 - RCBW-028-P - RCA-9940 - West DB6 – Shared DB Access to provide via SUP. A Maintenance Bay/vehicle hardstand has been provided to within 100m from ITS cabinets as per PRS requirement. This approach will minimize interactions with live traffic and create safe work areas. | FSR Traffic Management FSR Utilities and Services | Completely separates maintenance personnel from live freeway traffic. Creates a safe, hard-stand working area accessible via the SUP rather than the highway shoulder. | Verify maintenance vehicle access to hardstands. |  | Matthijs Klinkert
EBTA | EBTA002 | 2025-11-05 | NEL-STH-NSA-5100-CRF-REP-0002 | DESIGN REPORT - B072 – 5100/5200 Power and Comms | Design | Completed | Optimizing support infrastructure by grouping devices together to minimise services and to enable multiple devices to be accessed from a single point. - Optimizing number pole by combining AP and RPT with CCTV. - Combining PMC on CCTV pole - Mounting LUMS onto SUP bridge BS106 - This cabinet will allow for the supplying both DTP ITS, Project Co ITS and DTP Lighting with separate metering systems E.g., West DB6 | FSR Working at Heights FSR Traffic Management | Reducing the total number of poles and assets directly reduces the frequency of future maintenance interventions required at height and near traffic. | Update asset register with grouped assets. |  | Matthijs Klinkert
EBTA | EBTA003 | 2025-11-05 | NEL-STH-NSA-5100-CRF-REP-0002 | DESIGN REPORT - B072 – 5100/5200 Power and Comms | Modularisation | Completed | Prewiring of ITS Roadside cabinet and Pole mounted cabinet before installation off-site under a controlled environment. This will allow a secure and accessible location to be provided for pre-wired cabling (i.e., cables installed prior to gantry erection) to be connected to the wider cabling. This will eliminate risks associated with working; in challenging terrain, in extreme weather and in proximity to live traffic for this task. | FSR General Electrical Safety FSR Traffic Management | Eliminates the risks associated with performing complex electrical wiring in challenging terrain, extreme weather, or whilst exposed to live traffic noise and distractions. | Inspect pre-wire quality prior to delivery. |  | Matthijs Klinkert
EBTA | EBTA004 | 2025-11-05 | NEL-STH-NSA-5603-SBR-REP-0001 | Design Report – B101 - Koonung Creek Bebo Arch Assessment at Thompsons Rd | Design | Implemented | Need for protection structure is completely removed with design optimization on additional fill above the existing Bebo. | FSR Formwork & Falsework FSR Excavation | Removing the protection structure eliminates the hazards associated with its construction, including formwork erection, steel fixing, and concrete pouring near the existing arch. | Archive the design change note. |  | Matthijs Klinkert
EBTA | EBTA005 | 2025-11-05 | NEL-STH-NSA-5603-SBR-REP-0001 | Design Report – B101 - Koonung Creek Bebo Arch Assessment at Thompsons Rd | Design | Implemented | Removal of Bebo extension north of Thompson Road due to optimization in design at Thompsons Road exit ramp. | FSR Precast and Tilt up Concrete FSR Cranes and Lifting | Eliminates the need to lift and install heavy precast arch segments (Bebo), removing the associated crush risks and high-risk crane operations. | Update the structural layout drawings. |  | Matthijs Klinkert
EBTA | EBTA006 | 2025-11-05 | NEL-STH-NSA-5200-CNW-REP-0001 | Design Report - B068 5100 / 5200 NOISE WALLS OFF STRUCTURE WEST ZONE | Modularisation | Complete | Modularisation of Noise Walls – design for fabrication (precast concrete) or assembly (weathered steel) of modules off-site under a controlled environment to eliminate risks associated with working: in challenging terrain, at heights/near free edges, in extreme weather and in proximity to live traffic for this task. This would also allow greater control over transportation logistics and programming deliveries away from peak traffic periods and minimise exposure to traffic-related hazards | FSR Working at Heights FSR Traffic Management | Shift work from the field to a factory eliminates exposure to challenging terrain, free edges (fall risk), extreme weather, and live traffic hazards. | Review transport logistics for modules. |  | Matthijs Klinkert
EBTA | EBTA007 | 2025-11-05 | NEL-STH-NSA-5200-CNW-REP-0001 | Design Report - B068 5100 / 5200 NOISE WALLS OFF STRUCTURE WEST ZONE | Piles | Complete | Increased Spacing of Posts/Piles – in prioritising the adoption of post-and-panel walls, a key decision was made to optimise structural spacing and reduce quantity of piles across the project. This is done to minimise the risk of striking critical underground utilities with high risk of causing serious injury or fatality. It also allows for flexibility in designing for clash mitigation and greatly reduces labour time in constructing each wall | FSR Piling FSR Utilities and Services | Reducing the number of piles directly minimizes the statistical probability of striking critical underground utilities (high fatality risk). Also reduces total drilling time and exposure to piling hazards. | Verify utility clearance for revised pile locations. |  | Matthijs Klinkert
EBTA | EBTA008 | 2025-11-05 | NEL-STH-NSA-5200-CNW-REP-0001 | Design Report - B068 5100 / 5200 NOISE WALLS OFF STRUCTURE WEST ZONE | Design | Complete | Removing embedded posts in foundation design - the foundation design process had ruled out embedded steel posts in lieu of bolted baseplate connections to top of piles. This was done to mitigate the temporary works required to stabilise each post during the curing window while the concrete reached design compressive strength. Temporary props generally lengthen construction programmes and pose a risk of decoupling due to accidental impact, especially in zones of work with significant space constraints | FSR Formwork & Falsework | Removes the need for temporary bracing to hold posts while concrete cures. This eliminates the risk of props being accidentally knocked out or failing in congested workspaces. | Standardise baseplate connection details. |  | Matthijs Klinkert
EBTA | EBTA009 | 2025-11-05 | NEL-STH-NSA-5200-CNW-REP-0001 | Design Report - B068 5100 / 5200 NOISE WALLS OFF STRUCTURE WEST ZONE | Methodology | Complete | Minimising reliance on stitch cast walls – in the same logic as BTA-B068-ES03, the stitch cast walls relied on temporary works to stabilise the precast wall while the concrete stitching element is in the curing window. This type of wall provides the most flexibility for spaceproofing and is therefore often located at zones with the most challenging space constraints and increased risk of accidental decoupling for stabilising props. | FSR Formwork & Falsework FSR Precast and Tilt up Concrete | Stitch cast walls are often in tight spaces where props are vulnerable to impact. Minimising them reduces the risk of heavy precast elements falling due to prop failure or accidental decoupling. | Approve precast layout changes. |  | Matthijs Klinkert
EBTA | EBTA010 | 2025-11-05 | NEL-STH-NSA-5200-CNW-REP-0001 | Design Report - B068 5100 / 5200 NOISE WALLS OFF STRUCTURE WEST ZONE | Design | Voided | Realignment of noise walls at heights – a segment of noise walls along Koonung Creek Reserve (CNW220-223) are located atop a hill. They were shifted closer to the boundary line and the appropriate permits submitted to work beyond the boundary, which creates a space buffer, and minimise working time, along the live edge | FSR Working at Heights FSR Excavation | Moving the alignment creates a safe physical buffer zone, significantly minimizing the time workers must spend working directly along the "live edge" of the hill (fall hazard). | Archive boundary permits. |  | Matthijs Klinkert
EBTA | EBTA011 | 2025-11-05 | NEL-STH-NSA-5200-CNW-REP-0001 | Design Report - B068 5100 / 5200 NOISE WALLS OFF STRUCTURE WEST ZONE | Methodology | Complete | Construction methodology prioritising access from parkland – mostly along the westbound mainline, all construction zones were set up to prioritise access from parkland to avoid working along live traffic | FSR Traffic Management FSR Plant and Equipment | Completely eliminates the interface between the construction workforce and high-speed live traffic. Reduces the risk of errant vehicle strikes by keeping plant access off the main road. | Verify TMP implementation. |  | Matthijs Klinkert
EBTA | EBTA012 | 2025-11-05 | NEL-STH-NSA-5200-CNW-REP-0001 | Design Report - B068 5100 / 5200 NOISE WALLS OFF STRUCTURE WEST ZONE | Precast | Complete | Minimising lifting frequency in precast post-and-panel design – a design directive was issued to prioritise full height panel design (omitting horizontal joints) to reduce risks associated with heavy lifting and suspended loads, by minimising the frequency of such panel lifting. This was identified as a key opportunity since precast panels are the heaviest material of the post-and-panel wall designs | FSR Crane and Lifting FSR Precast and Tilt up Concrete | Fewer panels means fewer crane lifts. This directly reduces the frequency and duration that workers are exposed to the risks of suspended loads and heavy dropped objects. | Update lifting schedule. |  | Matthijs Klinkert
EBTA | EBTA013 | 2025-11-05 | NEL-STH-NSA-5200-CNW-REP-0001 | Design Report - B068 5100 / 5200 NOISE WALLS OFF STRUCTURE WEST ZONE | Design | Complete | Repurposing existing Noise Walls – where possible, the design team has prioritised the retention of existing noise walls that satisfy NV1/NV15 requirements to reduce overall site work associated with demolition. | FSR Plant and Equipment FSR Excavation | Eliminates the high-risk activity of mechanical demolition. This significantly reduces worker exposure to silica dust, hazardous noise levels, and the risks of interacting with heavy excavators/breakers. | Update asset register to reflect retained walls. |  | Matthijs Klinkert
EBTA | EBTA014 | 2025-11-05 | NEL-STH-NSA-5200-CNW-REP-0001 | Design Report - B068 5100 / 5200 NOISE WALLS OFF STRUCTURE WEST ZONE | Design | Complete (SNW018) / Voided (CNW230) | Omitting low-value Noise Walls – where possible, the design team has pushed for omitting noise walls proposed at TOC to reduce overall site work that provides relatively low value. Noise attenuation would be deemed achievable by other means (i.e. off-reserve treatments). | FSR Working at Heights FSR Traffic Management | Completely removes the construction footprint in these areas. By eliminating the asset, the project eliminates 100% of the associated traffic interface, lifting, and height risks for those specific zones. | Verify completion of off-reserve treatments. |  | Matthijs Klinkert
EBTA | EBTA015 | 2025-11-05 | NEL-STH-NSA-5200-CNW-REP-0001 | Design Report - B068 5100 / 5200 NOISE WALLS OFF STRUCTURE WEST ZONE | Design | Complete | Reducing Excess Height – an optimisation exercise was carried out through the design program to minimise the excess height built-in to design at TOC. Data obtained through physical testing was fed back to the simulation model and provided an outcome where Noise Walls could reduce up to 5m in height. This directive was aimed at reducing cost and Construction risks, overall reducing the duration of on-site labour and exposure to various hazards during works. | FSR Working at Heights FSR Cranes and Lifting | Lowering walls by up to 5m drastically reduces the risks associated with working at extreme heights. It also reduces the "sail area" of panels during lifting, improving stability in windy conditions. | Archive physical test results vs simulation data. |  | Matthijs Klinkert
EBTA | EBTA016 | 2025-11-05 | NEL-STH-NSA-5100-CUW-REP-0002 | Design Report - B146 - Utilities - W077 Temporary Works | Design | 2023-09-18 | NEL-STH-NSA-5100-CTW-MIN-0003 Safety-in-Design Workshop Minutes for Yarra Valley Water Water Relocations - B133 Doncaster Pressure Reducing Station & B146 W077 Temporary Relocation | FSR Utilities and Services FSR Excavation | Formal workshop ensures all utility-specific hazards (high pressure water, deep excavation) are identified by the asset owner and designers before construction begins, preventing catastrophic service strikes. | Archive workshop minutes. |  | Matthijs Klinkert
EBTA | EBTA017 | 2025-11-05 | NEL-STH-NSA-5100-CTW-REP-0015 | Design Report - E018-5100-0014 - BULLEEN INTERCHANGE - BULLEEN ROAD - THOMPSONS ROAD STAGE B3.0B TEMPORARY TRAFFIC SIGNALS |  |  | There is no table specifically with columns 'Number', 'Item', 'Status', and 'Design Stage' related to engineered safety methods in the given images. However, Section 9 'Safety in Design' provides an Engineered Safety section with the following content: "9.1 SiD Context SiD workshops will be undertaken for the civil 2D alignment throughout the detailed design phase for the different design packages. All SiD risks, proposed mitigation, residual risks and nominated 'owners' of those risks will be identified and captured for all design packages with registers included in the design report for each individual design package having risks relating to the design package in accordance with Eastern BTA Design Management Plan. 9.2 SiD Methodology The temporary works and constructability will be considered throughout the design process in the preparation of design solution with formal and informal meetings with Eastern BTA and through the design review process. It is expected that any major constructability constraints will be communicated as early as identified to allow for consideration in design. It is also expected that Eastern BTA will provide input during the formal design review process to ensure that the design accommodates any specific temporary works or staging requirements. In addition, the preliminary design is also reviewed by the VicRoads Signal Services as Subject Matter Experts and VicRoads Region teams from a Road Safety Perspective. 9.3 SiD Outcomes Outcomes from the SiD and DTP preliminary design review will be documented in the detailed design report if applicable." |  |  |  |  | Matthijs Klinkert
EBTA | EBTA018 | 2025-11-05 | NEL-STH-NSA-5200-SRW-REP-0001 | Design Report - B066 – 5200 Retaining Walls & Reinforced Earth Walls West | Precast | Complete | Minimise frequency of precast lifting – The team has designed the panel widths of each precast wall type to achieve a maximum of approximately 20t units. This optimises the lifting frequency for precast walls while avoiding employing heavy duty cranes. The goal is to reduce exposure of site personnel hazards of lifting heavy loads and eliminate the risks associated to working with heavy machinery. | FSR Crane and Lifting FSR Precast and Tilt up Concrete | Finding the "sweet spot" of ~20t units reduces the total number of lifts (frequency) without requiring excessively large cranes that introduce ground pressure and logistic risks. directly reduces personnel exposure to suspended loads. | Monitor crane utilization rates. |  | Matthijs Klinkert
EBTA | EBTA019 | 2025-11-05 | NEL-STH-NSA-5200-SRW-REP-0001 | Design Report - B066 – 5200 Retaining Walls & Reinforced Earth Walls West | Piles | Complete | Minimise risk of striking critical utilities by omitting piled foundations – where appropriate, the design team has opted for the shallow foundations of the “L-wall” type or mechanically stabilised earth walls to minimise the risk of striking critical/hazardous utilities | FSR Utilities and Services FSR Piling | Shallow foundations completely remove the need for deep drilling, eliminating the catastrophic risk of striking deep, unmapped, or critical utility mains. | Verify as-built foundation depths. |  | Matthijs Klinkert
EBTA | EBTA020 | 2025-11-05 | NEL-STH-NSA-5200-SRW-REP-0001 | Design Report - B066 – 5200 Retaining Walls & Reinforced Earth Walls West | Design | Complete | Integration of Noise Walls to minimise piling – to achieve similar outcomes as per BTA-B066-ES02-03 in reduced piling and working time on-site, the design team has prioritised, if appropriate, a design where noise walls are supported on retaining walls | FSR Piling FSR Working at Heights | Integrating the noise wall into the retaining wall eliminates a separate piling work front, reducing total site congestion, plant movements, and piling hazards. | Update structural interface drawings. |  | Matthijs Klinkert
EBTA | EBTA021 | 2025-11-05 | NEL-STH-NSA-5200-SRW-REP-0001 | Design Report - B066 – 5200 Retaining Walls & Reinforced Earth Walls West | Design | Complete | Prioritising alternate means of retention -where appropriate, the use of earthworks solutions was prioritised as a retention system over wall structures to reduce working time on-site. This has been actioned, collectively since TDC, for SRW212, 219, 023-25 (west), SRW28,32,36,46B,46D (east) | FSR Formwork & Falsework FSR Excavation | Earthworks batters eliminate the need for temporary propping, steel fixing, formwork, and lifting operations associated with building concrete retaining walls. | Monitor batter stability during wet weather. |  | Matthijs Klinkert
EBTA | EBTA022 | 2025-11-05 | NEL-STH-NSA-5200-SRW-REP-0001 | Design Report - B066 – 5200 Retaining Walls & Reinforced Earth Walls West | Design | Complete | Minimising risk of damaging critical/hazardous utilities – where possible, the design team has prioritised orienting the L-walls in “reverse” direction to minimise imposed loads on existing utilities, as for SRW200-3G | FSR Utilities and Services FSR Excavation | Reversing the wall footing directs the load away from sensitive underground assets, preventing pipe collapse or rupture which could lead to explosion, flooding, or environmental contamination. | Verify as-built clearance from utilities. |  | Matthijs Klinkert
EBTA | EBTA023 | 2025-11-05 | NEL-STH-NSA-5700-BDT-REP-0001 | DESIGN REPORT - B107 - DONCASTER PARK AND RIDE | Methodology | Adopted | The utilisation of the anti-throw mesh can be incorporated early into construction to provide both edge protection & in instances replace temporary catch screens. | FSR Working at Heights FSR Dropped Objects | Using the permanent mesh as temporary protection eliminates the need to install and dismantle separate temporary screens, reducing total man-hours at height and dropped object risks. | Update installation sequence in SWMS. |  | Matthijs Klinkert
EBTA | EBTA024 | 2025-11-05 | NEL-STH-NSA-5700-BDT-REP-0001 | DESIGN REPORT - B107 - DONCASTER PARK AND RIDE | Modularisation | Adopted | Prefabricated stairs with capability to have temporary treads to avoid the use of stair towers, scaffolds and the like to be used as both temporary & permanent. Relevant FSRs: Formwork and Falsework Controls: Engineering Controls | FSR Formwork & Falsework FSR Scaffolding FSR Working at Heights | Provides a robust, engineered access route immediately, removing the risks associated with erecting, inspecting, and maintaining temporary scaffold towers. | Inspect temporary treads weekly. |  | Matthijs Klinkert
EBTA | EBTA025 | 2025-11-05 | NEL-STH-NSA-5700-BDT-REP-0001 | DESIGN REPORT - B107 - DONCASTER PARK AND RIDE | Design | Adopted | Optimisation of rainwater tank size and design to minimise confined space risk and potential asbestos excavation Relevant FSRs: Excavation, Confined Space, Asbestos Controls: Engineering Controls | FSR Confined Space FSR Excavation FSR Hazardous Materials | Reducing the tank depth/size eliminates the need for deep excavation in contaminated ground (asbestos) and reduces the classification or depth of confined space entry required for maintenance. | Archive asbestos clearance certificates. |  | Matthijs Klinkert
EBTA | EBTA026 | 2025-11-05 | NEL-STH-NSA-5700-BDT-REP-0001 | DESIGN REPORT - B107 - DONCASTER PARK AND RIDE | Design | Adopted | Optimisation of pile cap design to minimise potential asbestos excavation and to minimise risk of fall from height / engulfment Relevant FSRs: Excavation, Asbestos, Confined Space Controls: Engineering Controls | FSR Excavation FSR Confined Space FSR Hazardous Materials | Reducing excavation volume minimizes potential exposure to asbestos in the soil. Shallower excavations also reduce the risks of engulfment (trench collapse) and falls from height into the pit. | Archive asbestos clearance certificates. |  | Matthijs Klinkert
EBTA | EBTA027 | 2025-11-05 | NEL-STH-NSA-5700-BDT-REP-0001 | DESIGN REPORT - B107 - DONCASTER PARK AND RIDE | Design | Adopted | Staff and Passenger building moved further away from Hender Street to reduce risk of working adjacent to HV overhead wires Relevant FSRs: General Electrical, Utilities and Services, Cranes and Lifting Controls: Engineering Controls | FSR General Electrical Safety FSR Utilities and Services FSR Crane and Lifting | Increasing the physical separation from High Voltage (HV) wires significantly reduces the risk of arcing or accidental contact during crane lifts and construction activities. | Verify No-Go Zone (NGZ) distances on site. |  | Matthijs Klinkert
EBTA | EBTA028 | 2025-11-05 | NEL-STH-NSA-5700-BDT-REP-0001 | DESIGN REPORT - B107 - DONCASTER PARK AND RIDE | Management | Adopted | Rationalisation of PID / CHP / QTEM / CVM / FPD devices on site in consultation with DTP to reduce amount of manual handling on site. Relevant FSRs: Manual Handling Controls: (Partial) Elimination | FSR Manual Handling FSR General Electrical Safety | Reducing the number of devices directly eliminates the manual handling required for their installation and future maintenance, as well as reducing electrical commissioning risks. | Update asset register with reduced quantities. |  | Matthijs Klinkert
EBTA | EBTA029 | 2025-11-05 | NEL-STH-NSA-5700-BDT-REP-0001 | DESIGN REPORT - B107 - DONCASTER PARK AND RIDE | Design | Adopted | Carpark slab falls updated to drain away from the centre of the building to eliminate risk of water entering heavy mechanical equipment e.g. lift wells Relevant FSRs: General Electrical Safety Controls: Elimination | FSR General Electrical Safety FSR Plant and Equipment | Preventing water ingress into heavy mechanical equipment areas (like lift wells) eliminates the risk of electrical shorts, equipment failure, and slip hazards in maintenance zones. | Check slab levels during pre-pour survey. |  | Matthijs Klinkert
EBTA | EBTA030 | 2025-11-05 | NEL-STH-NSA-5700-BDT-REP-0001 | DESIGN REPORT - B107 - DONCASTER PARK AND RIDE | Design | Adopted | Lowered roof pitch for Staff and Passenger Facilities Building as much as possible to increase distance of the building roof from the overhead power lines Relevant FSRs: Working at Heights, Crane and Lifting, General Electrical Safety, Utilities and Services Controls: (Partial) Elimination | FSR General Electrical Safety FSR Working at Heights FSR Utilities and Services | Maximizing the physical distance (air gap) to high-voltage lines reduces the potential for arc flash or accidental contact during roof construction and future maintenance. | Verify as-built roof levels against NGZ. |  | Matthijs Klinkert
EBTA | EBTA031 | 2025-11-05 | NEL-STH-NSA-5700-BDT-REP-0001 | DESIGN REPORT - B107 - DONCASTER PARK AND RIDE | Design | Adopted | Stair core A raft solution to be investigated to minimise excavation through asbestos contaminated materials Relevant FSRs: Excavation, Asbestos Controls: (Partial) Elimination | FSR Excavation | Raft slabs require significantly shallower earthworks compared to deep footings or piles, minimizing the disturbance of asbestos-laden soil and worker exposure. | Archive soil contamination reports. |  | Matthijs Klinkert
EBTA | EBTA032 | 2025-11-05 | NEL-STH-NSA-5700-BDT-REP-0001 | DESIGN REPORT - B107 - DONCASTER PARK AND RIDE | Material | Adopted | Lightweight facade above canopy on passenger building to facilitate ease of construction and lifting Relevant FSRs: Lifting Controls: Substitution | FSR Crane and Lifting FSR Manual Handling | Replacing heavy cladding with lightweight materials reduces the load on cranes/hoists and lowers the physical strain on workers manually positioning panels at height. | Confirm facade weight in lifting plan. |  | Matthijs Klinkert
EBTA | EBTA033 | 2025-11-05 | NEL-STH-NSA-5700-BDT-REP-0001 | DESIGN REPORT - B107 - DONCASTER PARK AND RIDE | Piles | Adopted | CFA piles adopted to reduce risk of pile collapse Relevant FSRs: Piling Controls: Substitution | FSR Piling FSR Excavation | CFA piling supports the borehole continuously during drilling and concreting, eliminating the risk of open boreholes collapsing in unstable ground conditions. | Monitor concrete pressure during pour. |  | Matthijs Klinkert
EBTA | EBTA034 | 2025-11-05 | NEL-STH-NSA-5900-BSV-REP-0001 | DESIGN REPORT - B214 - 5900 - INCIDENT RESPONSE BUILDING SITES | Modularisation | implemented | The site shed building has been proposed as a pre-fabricated building to limit the amount of assembly and construction that needs to be done on site. This will reduce the construction time frame that personnel are exposed to site risks. | FSR Working at Heights FSR Plant and Equipment | Moving construction off-site significantly reduces the total duration personnel are exposed to general site hazards (noise, dust, plant movement) and high-risk assembly tasks. | Confirm delivery and lifting plan for modules. |  | Matthijs Klinkert
EBTA | EBTA035 | 2025-11-05 | NEL-STH-NSA-5900-BSV-REP-0001 | DESIGN REPORT - B214 - 5900 - INCIDENT RESPONSE BUILDING SITES | Design | implemented | The sunshade utilises a simple sail structure rather than a more complex pergola type structure. This reduces the amount of structure that needs to be built and avoids lifting of any beams which would otherwise be required to support the pergola roof. | FSR Crane and Lifting FSR Working at Heights | Eliminates the need to construct a heavy frame and avoids the high-risk lifting of structural beams required to support a solid roof/pergola. | Verify sail tensioning specifications. |  | Matthijs Klinkert
EBTA | EBTA036 | 2025-11-05 | NEL-STH-NSA-5100-CUS-REP-0002 | DESIGN REPORT - B125 - UTILITIES – SEWER – BULLEEN ROAD YEM08A-4 |  |  | A specific constructability and potential health risk challenge has been identified regarding flow management of the live sewers. The proposal is that risk will be controlled by undertaking the works during low flow times. The Water Authorities will be consulted to assist in determining when low flow periods are, this is likely to require night working. |  |  |  |  | Matthijs Klinkert
EBTA | EBTA037 | 2025-11-05 | NEL-STH-NSA-5300-CNW-REP-0001 | DESIGN REPORT - B083 – 5300/5400/5500 NOISE WALLS - EAST | Modularisation | Complete | Modularisation of Noise Walls – design for fabrication (precast concrete) or assembly (weathered steel) of modules off-site under a controlled environment to eliminate risks associated with working; in challenging terrain, at heights/near free edges, in extreme weather and in proximity to live traffic for this task. | FSR Traffic Management FSR Working at Heights | Eliminates the risks associated with working in challenging terrain, near free edges, in extreme weather, or in close proximity to live traffic. | Review transport logistics for modules. |  | Matthijs Klinkert
EBTA | EBTA038 | 2025-11-05 | NEL-STH-NSA-5300-CNW-REP-0001 | DESIGN REPORT - B083 – 5300/5400/5500 NOISE WALLS - EAST | Piles | Complete | Increased Spacing of Posts/Piles – in prioritising the adoption of post-and-panel walls, a key decision was made to optimise structural spacing and reduce quantity of piles across the project. This is done to minimise the risk of striking critical underground utilities with high risk of causing serious injury or fatality. It also allows for flexibility in designing for clash mitigation and greatly reduces labour time in constructing each wall. | FSR Piling FSR Utilities and Services | Minimises the statistical risk of striking critical underground utilities (high fatality risk) by reducing the number of ground penetrations. Also reduces total labour time in piling zones. | Verify utility clearance for revised locations. |  | Matthijs Klinkert
EBTA | EBTA039 | 2025-11-05 | NEL-STH-NSA-5300-CNW-REP-0001 | DESIGN REPORT - B083 – 5300/5400/5500 NOISE WALLS - EAST | Design | Complete | Removing embedded posts in foundation design – the foundation design process had ruled out embedded steel posts in lieu of bolted baseplate connections to top of piles. This was done to mitigate the temporary works required to stabilise each post during the curing window while the concrete reached design compressive strength. | FSR Formwork & Falsework | Mitigates the need to stabilise posts with temporary props during the concrete curing window. Reduces the risk of props decoupling due to accidental impact in constrained spaces. | Standardise baseplate connection details. |  | Matthijs Klinkert
EBTA | EBTA040 | 2025-11-05 | NEL-STH-NSA-5300-CNW-REP-0001 | DESIGN REPORT - B083 – 5300/5400/5500 NOISE WALLS - EAST | Methodology | Complete | Minimising reliance on stitch cast walls – in the same logic as BTA-B083-ES03, the stitch cast walls relied on temporary works to stabilise the precast wall while the concrete stitching element is in the curing window. This type of wall provides the most flexibility for space proofing and is therefore often located at zones with the most challenging space constraints and increased risk of accidental decoupling for stabilising props. | FSR Formwork & Falsework FSR Precast and Tilt up Concrete | Stitch cast walls require props in tight spaces where they are vulnerable to collision. Reducing them minimises the risk of accidental decoupling and wall failure during construction. | Approve precast layout changes. |  | Matthijs Klinkert
EBTA | EBTA041 | 2025-11-05 | NEL-STH-NSA-5300-CNW-REP-0001 | DESIGN REPORT - B083 – 5300/5400/5500 NOISE WALLS - EAST | Design | Ongoing | Realignment of noise walls at heights – a noise wall immediately south-east of Doncaster Rd (CNW354) is located atop a steep hill. The design objective is to explore alternative options that eliminate the significant hazards of working at heights, under a constrained space and near a live edge. | FSR Working at Heights FSR Excavation | Exploring alternative options eliminates the significant hazards of working at heights on a "live edge" (steep hill) within a constrained construction footprint. | Confirm alignment change in model. |  | Matthijs Klinkert
EBTA | EBTA042 | 2025-11-05 | NEL-STH-NSA-5300-CNW-REP-0001 | DESIGN REPORT - B083 – 5300/5400/5500 NOISE WALLS - EAST | Methodology | Complete | Construction methodology prioritising access from parkland – mostly along the westbound mainline, all construction zones were set up to prioritise access from parkland to avoid working along live traffic. | FSR Traffic Management FSR Plant and Equipment | Completely eliminates the interface between the construction workforce and high-speed live traffic. Reduces the risk of vehicle strikes by keeping plant access off the main road. | Verify access point signage is compliant. |  | Matthijs Klinkert
EBTA | EBTA043 | 2025-11-05 | NEL-STH-NSA-5300-CNW-REP-0001 | DESIGN REPORT - B083 – 5300/5400/5500 NOISE WALLS - EAST | Precast | Complete | Minimising lifting frequency in precast post-and-panel design – a design directive was issued to prioritise full height panel design (omitting horizontal joints) to reduce risks associated with heavy lifting and suspended loads, by minimising the frequency of such panel lifting. | FSR Crane and Lifting FSR Precast and Tilt up Concrete | Fewer panels means fewer crane lifts. This directly reduces the frequency and duration that workers are exposed to the risks of suspended loads. | Review lifting plans for panel counts. |  | Matthijs Klinkert
EBTA | EBTA044 | 2025-11-05 | NEL-STH-NSA-5300-CNW-REP-0001 | DESIGN REPORT - B083 – 5300/5400/5500 NOISE WALLS - EAST | Design | Complete | Repurposing existing Noise Walls – where possible, the design team has prioritised the retention of existing noise walls that satisfy NV1/NV15 requirements to reduce overall site work associated with demolition and to reduce complexity of site works when interfacing with retaining walls. | FSR Plant and Equipment FSR Excavation | Eliminates high-risk mechanical demolition activities, significantly reducing worker exposure to silica dust, noise, and heavy plant interaction. | Conduct condition assessment of retained walls. |  | Matthijs Klinkert
EBTA | EBTA045 | 2025-11-05 | NEL-STH-NSA-5300-CNW-REP-0001 | DESIGN REPORT - B083 – 5300/5400/5500 NOISE WALLS - EAST | Design | Complete | Omitting low-value Noise Walls – where possible, the design team has pushed for omitting noise walls proposed at TOC to reduce overall site work that provides relatively low value. Noise attenuation would be deemed achievable by other means (i.e. – off-reserve treatments). This is currently under investigation for CNW306A. | FSR Working at Heights FSR Traffic Management | Completely removes the construction footprint in these areas, eliminating 100% of the associated traffic interface and height risks. | Monitor investigation status for CNW306A. |  | Matthijs Klinkert
EBTA | EBTA046 | 2025-11-05 | NEL-STH-NSA-5300-CNW-REP-0001 | DESIGN REPORT - B083 – 5300/5400/5500 NOISE WALLS - EAST | Design | Complete | Reducing Excess Height – an optimisation exercise was carried out through the design program to minimise the excess height built-in to design at TOC. Data obtained through physical testing was fed back to the simulation model and provided an outcome where Noise Walls could reduce up to 5 m in height. | FSR Working at Heights FSR Crane and Lifting | Lowering wall height by up to 5m significantly reduces the risks associated with working at extreme heights. It also reduces the wind load ("sail area") on panels during lifting, improving crane stability. | Archive physical test results vs simulation data. |  | Matthijs Klinkert
EBTA | EBTA047 | 2025-11-05 | NEL-STH-NSA-5900-STG-REP-0005 | DESIGN REPORT - ZONE 5900 - B210 - VALDA WETLANDS AND MISCELLANEOUS STRUCTURES | Precast | completed | Precast culverts and debris poles have been adopted to minimise the need for formwork and cast in situ elements. | FSR Formwork & Falsework FSR Excavation | Eliminates the need for workers to enter excavations to erect formwork or tie steel. Moves the construction of these elements to a safe, controlled factory environment. | Verify delivery schedule for precast units. |  | Matthijs Klinkert
EBTA | EBTA048 | 2025-11-05 | NEL-STH-NSA-5900-STG-REP-0005 | DESIGN REPORT - ZONE 5900 - B210 - VALDA WETLANDS AND MISCELLANEOUS STRUCTURES | Design | completed | Fixings from cantilever steel beams have been designed to be top mounted (cast in ferrules rather than post installed bolts) to less on-sit construction effort. | FSR Plant and Equipment | Cast-in ferrules eliminate the need for overhead hammer drilling. This removes risks related to silica dust exposure, noise, vibration (HAVS), and shoulder strain. | Inspect ferrule placement pre-pour. |  | Matthijs Klinkert
EBTA | EBTA049 | 2025-11-05 | NEL-STH-NSA-5900-STG-REP-0005 | DESIGN REPORT - ZONE 5900 - B210 - VALDA WETLANDS AND MISCELLANEOUS STRUCTURES | Design | completed | Debris poles located at safe distances from OH electrical cables to minimise the risk to construction workers and maintenance personnel. | FSR General Electrical Safety FSR Utilities and Services | Designing the poles outside of the electrical No-Go Zone ensures that cranes and piling rigs can operate safely without risk of arcing or contacting live high-voltage wires. | Confirm NGZ distances on site. |  | Matthijs Klinkert
EBTA | EBTA050 | 2025-11-05 | NEL-STH-NSA-5900-STG-REP-0005 | DESIGN REPORT - ZONE 5900 - B210 - VALDA WETLANDS AND MISCELLANEOUS STRUCTURES | Design | completed | Starter bars have been shortened to minimise the trips and falls risks during construction. | FSR Formwork & Falsework FSR Working at Heights | Reducing the length of protruding rebar significantly lowers the tripping hazard for workers walking on the deck and reduces the severity of potential impalement injuries. | Verify rebar scheduling. |  | Matthijs Klinkert
EBTA | EBTA051 | 2025-11-05 | NEL-STH-NSA-5900-STG-REP-0005 | DESIGN REPORT - ZONE 5900 - B210 - VALDA WETLANDS AND MISCELLANEOUS STRUCTURES | Design | completed | Timber shields have a step to delineate the secondary path for maintenance vehicles. | FSR Traffic Management FSR Plant and Equipment | Clear delineation of vehicle paths ensures maintenance vehicles remain on stable, designated ground, preventing interaction with pedestrians or off-path hazards. | Inspect shield installation. |  | Matthijs Klinkert
EBTA | EBTA052 | 2025-11-05 | NEL-STH-NSA-5900-STG-REP-0005 | DESIGN REPORT - ZONE 5900 - B210 - VALDA WETLANDS AND MISCELLANEOUS STRUCTURES | Design | completed | Departure for debris load on balustrade has been proposed to utilise standard ENCAT balustrade and avoid the need for a custom-made balustrade. | FSR Working at Heights | Adopting a standard, pre-engineered system avoids the risks associated with on-site fabrication or the installation of unproven custom heavy steelwork at height. | Approve design departure. |  | Matthijs Klinkert
EBTA | EBTA053 | 2025-11-05 | NEL-STH-NSA-5900-STG-REP-0005 | DESIGN REPORT - ZONE 5900 - B210 - VALDA WETLANDS AND MISCELLANEOUS STRUCTURES | Design | completed | Grout injection opening for the last culvert legs connecting to base slab will be detailed to allow the construction to inject grout outside the crown unit, the relevant detail and construction sequence will be modified in FD | FSR Confined Space FSR Precast and Tilt up Concrete | Moving the injection point to the exterior eliminates the need for workers to enter the culvert (a potential confined space) to perform grouting, removing entrapment risks. | Update Final Design (FD) drawings. |  | Matthijs Klinkert
EBTA | EBTA054 | 2025-11-05 | NEL-STH-NSA-5123-SBS-REP-0001 | DESIGN REPORT - B052 – BS108 – SUP FROM LAND BRIDGE (PORTAL) | Design | Adopted | Provide bolted splice connections to remove the need for on-site welding. Relevant FSRs: N/A Controls: Engineering Controls |  | Bolted connections completely eliminate "Hot Works" (welding). This removes fire risks and exposure to toxic welding fumes and UV radiation for the workforce. | Verify bolt torque specifications. |  | Matthijs Klinkert
EBTA | EBTA055 | 2025-11-05 | NEL-STH-NSA-5123-SBS-REP-0001 | DESIGN REPORT - B052 – BS108 – SUP FROM LAND BRIDGE (PORTAL) | Material | Adopted | Use permanent formwork with panels kerb to remove the need for cast in place deck form, while minimising mass for major bridge lift. Furthermore, utilise light weight GRP deck form such as Permadec in lieu of Transfloor. Reduce risk level for lifting precast deck panels. Relevant FSRs: Cranes and Lifting Controls: Engineering Controls | FSR Crane and Lifting | GRP is significantly lighter than concrete/steel decking. This reduces the suspended load weight for cranes and minimises physical strain during installation. | Confirm GRP material certification. |  | Matthijs Klinkert
EBTA | EBTA056 | 2025-11-05 | NEL-STH-NSA-5123-SBS-REP-0001 | DESIGN REPORT - B052 – BS108 – SUP FROM LAND BRIDGE (PORTAL) | Methodology | Adopted | Develop detailed construction staging and lifting sequence to provide respective Contractor’s ability to safely plan out associated works in a significant level of detail, thus minimising chance for errors in high risk work environment. Relevant FSRs: Cranes and Lifting Controls: Administrative Controls | FSR Crane and Lifting | providing a prescriptive, step-by-step sequence reduces the cognitive load on the crew, minimizing the chance for human error during complex lifts. | Review lift plan with work crew. |  | Matthijs Klinkert
EBTA | EBTA057 | 2025-11-05 | NEL-STH-NSA-5123-SBS-REP-0001 | DESIGN REPORT - B052 – BS108 – SUP FROM LAND BRIDGE (PORTAL) | Design | Adopted | Integrating temporary works with permanent works designs, thus ensuring global and local capacity and stability checks have been accounted for in a single design package. Clear load tables and diagrams are included primarily where elements are integral (ie. welded lifting points, temporary bracing elements, etc). Relevant FSRs: Cranes and Lifting Controls: Engineering Controls | FSR Crane and Lifting | Ensures the structure is stable at every intermediate stage of construction, not just the final state. Prevents collapse due to temporary instability. | Archive design verification certificate. |  | Matthijs Klinkert
EBTA | EBTA058 | 2025-11-05 | NEL-STH-NSA-5123-SBS-REP-0001 | DESIGN REPORT - B052 – BS108 – SUP FROM LAND BRIDGE (PORTAL) | Piles | Adopted | Pile reinforcement protruding straight without cogs to enable pile cropping or similar in lieu of manual jack hammering for pile break back. Manual jack hammering causes adverse harm to individual performing works, as well as creates significant dust and debris, of which pile cropping (or similar) alleviates. Relevant FSRs: Demolition Controls: Engineering Controls | FSR Demolition | Mechanical cropping removes the need for manual jack hammering, eliminating operator exposure to Hand-Arm Vibration Syndrome (HAVS), dangerous silica dust, and excessive noise. | Verify reinforcement schedule |  | Matthijs Klinkert
EBTA | EBTA059 | 2025-11-05 | NEL-STH-NSA-5123-SBS-REP-0001 | DESIGN REPORT - B052 – BS108 – SUP FROM LAND BRIDGE (PORTAL) | Design | Adopted | Addition of access hatches in superstructure to allow for internal maintenance. Internal areas are mostly free of bracing to allow easier access within. Relevant FSRs: N/A Controls: Engineering Controls |  | Clear internal paths without bracing obstructions significantly reduce physical strain on maintenance workers and allow for faster, safer emergency extraction if required. | Verify hatch dimensions against rescue requirements. |  | Matthijs Klinkert
EBTA | EBTA060 | 2025-11-05 | NEL-STH-NSA-5123-SBS-REP-0001 | DESIGN REPORT - B052 – BS108 – SUP FROM LAND BRIDGE (PORTAL) | Modularisation | Adopted | Module widths reduced to allow efficient transport to site. On site field splice locations chosen to facilitate this reduction in width. Relevant FSRs: Cranes & Lifting Controls: Engineering Controls | FSR Crane and Lifting | Reducing module size limits the need for high-risk "oversize" road transport and ensures loads are within safer capacity margins for site cranes. | Approve transport logistics plan. |  | Matthijs Klinkert
EBTA | EBTA061 | 2025-11-05 | NEL-STH-NSA-5123-SBS-REP-0001 | DESIGN REPORT - B052 – BS108 – SUP FROM LAND BRIDGE (PORTAL) | Design | Adopted | Alignment and pier placement avoids existing sewer asset and providing appropriate clearance to respective asset. Reduces risk of striking major sewer line. Relevant FSRs: Utilities Controls: Engineering Controls | FSR Utilities and Services | Strategic placement prevents the catastrophic risk of striking a major sewer line, avoiding biological hazards, trench flooding, and environmental contamination. | Verify as-built clearance from sewer. |  | Matthijs Klinkert
EBTA | EBTA062 | 2025-11-05 | NEL-STH-NSA-5200-CRW-REP-0002 | DESIGN REPORT - B062 - 5200B MAINLINE AND RAMPS ALIGNMENTS & CIVILS | Methodology | Implemented | Construction staging implemented to separate works around live traffic with a temporary diversion of traffic at Thompsons Road and Bulleen Road to remove the risk in the area with the bridge deck complete prior to opening to traffic. | FSR Traffic Management | Completing the bridge deck prior to traffic opening completely removes the interface between workers and live traffic, eliminating vehicle strike risks during critical heavy works. | Archive Traffic Management Plans (TMPs). |  | Matthijs Klinkert
EBTA | EBTA063 | 2025-11-05 | NEL-STH-NSA-5200-CRW-REP-0002 | DESIGN REPORT - B062 - 5200B MAINLINE AND RAMPS ALIGNMENTS & CIVILS | Methodology | Implemented | Construction staging has been investigated and will be implemented by the Worksite Traffic Management Plan to delineate and minimise the duration/extent of high-risk activities working near live traffic with proposed temporary barrier works and associated signage. | FSR Traffic Management | Physical barriers provide a crash-rated separation, while minimising duration reduces the statistical probability of a traffic-related incident occurring. | Audit barrier installation compliance. |  | Matthijs Klinkert
EBTA | EBTA064 | 2025-11-05 | NEL-STH-NSA-5606-SBR-REP-0001 | Design Report - B104 - BR605 – Koonung Creek Culvert Near Sweyn Street | Design | Adopted | Removal of piling within the creek. The original TAN B design was a pile and plank structure which has now been changed to a pre-cast crown unit system on base slab. We achieved the below through this approach: Avoiding having a piling rig on unstable ground; Avoid providing access for large piling rigs; Avoids lifting in of large pile reinforcement cages. | FSR Piling FSR Plant and Equipment FSR Crane and Lifting | Eliminates the high risk of piling rig instability/tipping on soft ground. Also removes the need to lift heavy reinforcement cages and access for large machinery in restricted areas. | Verify bearing capacity for base slab. |  | Matthijs Klinkert
EBTA | EBTA065 | 2025-11-05 | NEL-STH-NSA-5606-SBR-REP-0001 | Design Report - B104 - BR605 – Koonung Creek Culvert Near Sweyn Street | Precast | Adopted | The crown units at the bends were originally proposed to be cast in-situ, which would result in tall formwork structures and tall reinforcement cages which would need to be supported. We have designed these out by working with the subcontractor to provide these as custom precast units. | FSR Formwork & Falsework FSR Working at Heights FSR Precast and Tilt up Concrete | Eliminates the need to erect and support tall formwork structures and rebar cages, removing fall hazards and the risk of temporary works collapse or blowout. | Inspect precast unit quality. |  | Matthijs Klinkert
EBTA | EBTA066 | 2025-11-05 | NEL-STH-NSA-5606-SBR-REP-0001 | Design Report - B104 - BR605 – Koonung Creek Culvert Near Sweyn Street | Design | Implemented | The 3-cell culvert design from DD has been reduced to a 2-cell design. This reduces the number of construction activities as the structure is smaller overall and it reduces the time workers need to be within the creek where they are subject to flood risk. The 2 cell design also allows more of the temporary excavation to be battered out rather than soil nailed or rock bolted. This 2 cell structure is an overall safer design to build with less construction activities that reduces overall risk. | FSR Excavation FSR Work On, Over Or Adjacent to Water | Smaller footprint allows excavation to be battered back, eliminating the need for high-risk soil nailing or rock bolting. Also reduces worker exposure time to flood risks in the creek. | Verify batter stability on site. |  | Matthijs Klinkert
EBTA | EBTA067 | 2025-11-05 | NEL-STH-NSA-5900-CTM-REP-0001 | DESIGN REPORT - B037 – PROJECT WIDE TRAFFIC MODELLING REPORT | Design | Under Investigation | Pedestrian Countdown Timer. Discussions with NELP and DTP for the use of pedestrian countdown timer was investigated to reduce the likelihood for pedestrians stored in an exposed environment at Bulleen / Thompsons Road intersection. Per the VicRoads Supplements to AS1742.14:2014 cl2.4(d), this has been proposed to DTP for consideration and acceptance for use. | FSR Traffic Management | Reduces the likelihood of pedestrians being "stored" or stranded in an exposed environment on the roadway, minimising their exposure to live traffic risks. | Monitor DTP acceptance status. |  | Matthijs Klinkert
EBTA | EBTA068 | 2025-11-05 | NEL-STH-NSA-5300-CRF-REP-0002 | Design Report - B087 5300/5400/5500 Power and Comms | Design | Completed | ITS Roadside cabinet moved Off Freeway to SUP where possible to provide safety to maintenance person. Efforts were made to ensure cabinets were located behind noise walls where possible. e.g., Cabinet Behind Noise wall and retaining wall. Multiple specific cabinets are listed. Access to be provide via SUP. A Maintenance Bay/vehicle hardstand have been provided to within 100m from ITS cabinets as per PRS requirement. This approach will minimize interactions with live traffic and to create safe work areas. | FSR Traffic Management FSR Utilities and Services | Minimizes interaction with live traffic and creates safe, hard-stand work areas accessible via the SUP (within 100m of cabinet). | Confirm maintenance access routes. |  | Matthijs Klinkert
EBTA | EBTA069 | 2025-11-05 | NEL-STH-NSA-5300-CRF-REP-0002 | Design Report - B087 5300/5400/5500 Power and Comms | Design | Completed | Optimising support infrastructure by grouping devices together to minimise services and to enable multiple devices to be accessed from a single point. Includes optimising number pole by combining AP and RPT with CCTV, combining PMC on CCTV pole, and use of Type 4 DB cabinet to supply both DTP ITS and DTP Lighting from a common MEN connection. | FSR General Electrical Safety FSR Utilities and Services | Consolidating devices onto fewer poles reduces the frequency of future maintenance interventions required at height and near traffic. | Update electrical asset drawings. |  | Matthijs Klinkert
EBTA | EBTA070 | 2025-11-05 | NEL-STH-NSA-5300-CRF-REP-0002 | Design Report - B087 5300/5400/5500 Power and Comms | Modularisation | Completed | Prewiring of ITS Roadside cabinet and Pole mounted cabinet before installation off-site under a controlled environment to allow a secure and accessible location for pre-wired cabling, eliminating risk of working in challenging terrain, extreme weather, and proximity to live traffic for this task. | FSR General Electrical Safety FSR Traffic Management | Eliminates the risks associated with performing complex electrical work in challenging terrain, extreme weather, or whilst exposed to live traffic noise and distractions. | Inspect pre-wire quality prior to delivery. |  | Matthijs Klinkert
EBTA | EBTA071 | 2025-11-05 | NEL-STH-NSA-5200-CUS-REP-0002 | DESIGN REPORT - B206 – UTILITIES – SEWER BAS01, S074, S076, ESS01, ESS02, ESS03 | Modularisation | Implemented | Introduction of GRP factory formed maintenance structure to reduce working time at depth and in confined space | FSR Confined Space FSR Excavation | Significantly reduces the working time required at depth and within confined spaces during installation, as the unit arrives pre-built. | Confirm GRP structural certification. |  | Matthijs Klinkert
EBTA | EBTA072 | 2025-11-05 | NEL-STH-NSA-5200-CUS-REP-0002 | DESIGN REPORT - B206 – UTILITIES – SEWER BAS01, S074, S076, ESS01, ESS02, ESS03 | Methodology | Implemented | Adoption of pipe jacking installation technique to reduce the areas of open trenching minimising hazards to road users, pedestrians, local residents, and construction workers. Pipe jacking also reduces the risks of trench collapse and requirement of traffic management. | FSR Excavation FSR Traffic Management | Eliminates the risk of trench collapse (engulfment) and reduces the need for traffic management/road closures, protecting both workers and the public. | Monitor ground settlement readings. |  | Matthijs Klinkert
EBTA | EBTA073 | 2025-11-05 | NEL-STH-NSA-5200-CTW-REP-0003 | B207 TEMPORARY KOONUNG CREEK DIVERSION CHANNEL - DESIGN REPORT | Methodology | Implemented | The temporary creek realignment proposed within this Design Package is located north of the proposed permanent creek realignment. As such, the distance provided between the two locations allows for works to be performed simultaneously. | FSR Work On, Over Or Adjacent to Water FSR Plant and Equipment | Creating adequate physical distance between the two creek alignments prevents plant congestion and allows safe simultaneous operations (SIMOPS). | Review SIMOPS management plan. |  | Matthijs Klinkert
EBTA | EBTA074 | 2025-11-05 | NEL-STH-NSA-5200-CTW-REP-0003 | B207 TEMPORARY KOONUNG CREEK DIVERSION CHANNEL - DESIGN REPORT | Methodology | Implemented | As the temporary creek realignment interfaces with the existing alignment of the Koonung Creek at two locations near both the upstream and downstream end, construction sequencing can allow the majority of the works to be completed away from a live creek environment. | FSR Work On, Over Or Adjacent to Water | Working "offline" isolates the workforce from water flow hazards, eliminating the risk of drowning, waterborne contamination, or equipment loss during potential flash flooding events. | Monitor weather forecasts during tie-in works. |  | Matthijs Klinkert
EBTA | EBTA075 | 2025-11-05 | NEL-STH-NSA-5513-SBS-REP-0001 | DESIGN REPORT - B096 – BS503 – DONCASTER ROAD SUP UNDERPASS | Methodology | Implemented | Construction staging implemented to separate works around live traffic with a temporary diversion of traffic at Doncaster Road and at exit ramp from westbound Eastern Freeway to remove the risk in the area. Relevant FSRs: Traffic Management. Controls: Elimination. | FSR Traffic Management | The diversion physically removes the interface between the live carriageway and the construction zone, eliminating the risk of high-speed vehicle incursions into the workspace. | Audit Traffic Management Plan (TMP) compliance. |  | Matthijs Klinkert
EBTA | EBTA076 | 2025-11-05 | NEL-STH-NSA-5513-SBS-REP-0001 | DESIGN REPORT - B096 – BS503 – DONCASTER ROAD SUP UNDERPASS | Precast | Implemented | Precast concrete girders are used prior to deck construction to reduce the risk of working from height. Relevant FSRs: Working at Heights, Cranes and Lifting. Controls: Engineering controls, Elimination. | FSR Working at Heights FSR Crane and Lifting | Precast elements provide an immediate safe working platform, drastically reducing the duration workers spend installing formwork and reinforcement over voids or traffic. | Verify girder installation SWMS. |  | Matthijs Klinkert
EBTA | EBTA077 | 2025-11-05 | NEL-STH-NSA-5513-SBS-REP-0001 | DESIGN REPORT - B096 – BS503 – DONCASTER ROAD SUP UNDERPASS | Design | Implemented | Wingwall 2 changed from having sloped pilecap to horizontal pilecap to enhance constructability and safety. Relevant FSRs: Piling. Controls: Engineering controls, Elimination. | FSR Piling FSR Formwork & Falsework | Horizontal caps eliminate the need for complex, sloped formwork (which is prone to failure/blowout) and provide a flat, stable footing for workers during steel fixing and concreting. | Update structural drawings. |  | Matthijs Klinkert
EBTA | EBTA078 | 2025-11-05 | NEL-STH-NSA-5513-SBS-REP-0001 | DESIGN REPORT - B096 – BS503 – DONCASTER ROAD SUP UNDERPASS | Design | Implemented | Wingwall 1 and wingwall 2 are extended to achieve 1:3 embankment slope behind and in front of the wingwall, making the embankment safer for maintenance activity. Relevant FSRs: Working at Heights. Controls: Engineering controls. | FSR Working at Heights | Creating a 1:3 slope makes the embankment walkable and stable, significantly improving safety for maintenance crews compared to steeper, harder-to-access slopes. | Verify as-built slope survey. |  | Matthijs Klinkert
EBTA | EBTA079 | 2025-11-05 | NEL-STH-NSA-5513-SBS-REP-0001 | DESIGN REPORT - B096 – BS503 – DONCASTER ROAD SUP UNDERPASS | Design | Implemented | Optimisation of deck and shotcrete reinforcement to reduce manual handling on site. Relevant FSRs: Manual Handling. Controls: Elimination. | FSR Formwork & Falsework | Optimizing the rebar design (e.g., spacing, bar sizes) directly eliminates excessive physical strain and repetitive movement injuries for steel fixers. | Verify reinforcement schedule. |  | Matthijs Klinkert
EBTA | EBTA080 | 2025-11-05 | NEL-STH-NSA-5400-CTW-REP-0002 | Design Report – E018-5400-0004 – DONCASTER ROAD – ELGAR ROAD / BELMORE ROAD – TEMPORARY TRAFFIC SIGNALS |  |  | There is no table with columns 'Number', 'Item', 'Status', and 'Design Stage' present in the provided images. However, there is an Engineered Safety (Safety in Design, SiD) section, which notes that SiD workshops are undertaken during the design phase, all risks are identified and captured in risk registers, temporary works and constructability are considered, risks are reviewed by key stakeholders, and outcomes are documented in the detailed design report if applicable. |  |  |  |  | Matthijs Klinkert
EBTA | EBTA081 | 2025-11-05 | NEL-STH-NSA-5300-CUS-REP-0002 | Design Report - Utilities - Sewer 092, S097, S102, S103, S104, S106, S108 & S111 |  |  | No specific engineered safety initiatives have been identified for this package. However, the package has been developed using Engineered Safety Principals, with engagement from the construction team and asset owners throughout design development and constructability reviews. Fatal and Severe Risks (FSR) for the construction phase have been identified and control measures for issues such as excavations, working at heights, crane and lifting, plant and equipment, traffic management, confined space, formwork & falsework, and utilities & services have been included. Additionally, risks associated with live sewers will be managed by scheduling works during low flow times based on consultation with Water Authorities. |  |  |  |  | Matthijs Klinkert
EBTA | EBTA082 | 2025-11-05 | NEL-STH-NSA-5602-SBR-REP-0001 | DESIGN REPORT - B100 – BR601 – NEL OVER KOONUNG CREEK | Design | Implemented | Construction staging has been investigated and the alignment of Koonung Creek has been moved south to avoid the existing culvert under Bulleen Road, removing the need of staged construction managing the temporary diversion of Koonung Creek during delivery of the works. | FSR Work On, Over Or Adjacent to Water FSR Excavation | Avoiding the existing culvert eliminates the high-risk interface with live water flow and deep excavation near the roadway, preventing potential flooding or collapse. | Verify new alignment survey. |  | Matthijs Klinkert
EBTA | EBTA083 | 2025-11-05 | NEL-STH-NSA-5602-SBR-REP-0001 | DESIGN REPORT - B100 – BR601 – NEL OVER KOONUNG CREEK | Precast | Implemented | Precast concrete planks have been adopted for the superstructure to remove the need for temporary formwork to support the bridge deck slab during construction. | FSR Formwork & Falsework FSR Working at Heights | Removes the high-risk activity of erecting, certifying, and dismantling temporary falsework supports at height. | Inspect plank seating quality. |  | Matthijs Klinkert
EBTA | EBTA084 | 2025-11-05 | NEL-STH-NSA-5602-SBR-REP-0001 | DESIGN REPORT - B100 – BR601 – NEL OVER KOONUNG CREEK | Methodology | Implemented | Construction staging implemented to separate works around live road traffic with a temporary diversion of traffic at Thompsons Road and Bulleen Road to remove the risk in the area with the bridge deck complete prior to opening to traffic. | FSR Traffic Management | Completing the bridge deck prior to traffic opening completely removes the risk of vehicle interaction/strikes during the most intensive construction phase. | Audit traffic barrier setup. |  | Matthijs Klinkert
EBTA | EBTA085 | 2025-11-05 | NEL-STH-NSA-5602-SBR-REP-0001 | DESIGN REPORT - B100 – BR601 – NEL OVER KOONUNG CREEK | Design | Implemented | The blade wall at each abutment (proposed at the PD stage) has been changed to a capping beam with a shotcrete wall below. This has assisted in implementing lessons learned from previous projects, i.e. reduced excavation depths (6m vs 3m), reduced impact to adjacent structures and less temporary works. | FSR Excavation FSR Formwork & Falsework | Halving the excavation depth (6m vs 3m) drastically reduces the risk of trench collapse and minimizes the scale of temporary earth retention systems required. | Verify shotcrete thickness. |  | Matthijs Klinkert
EBTA | EBTA086 | 2025-11-05 | NEL-STH-NSA-5602-SBR-REP-0001 | DESIGN REPORT - B100 – BR601 – NEL OVER KOONUNG CREEK | Methodology | Implemented | A top-down construction method has been adopted to reduce the amount of work required at heights. | FSR Working at Heights | By building "top-down," the permanent structure creates its own safe working platform as it progresses, significantly reducing the need for temporary access scaffolds and work from ladders. | Approve top-down method statement. |  | Matthijs Klinkert
EBTA | EBTA087 | 2025-11-05 | NEL-STH-NSA-5602-SBR-REP-0001 | DESIGN REPORT - B100 – BR601 – NEL OVER KOONUNG CREEK | Methodology | Implemented | The construction staging has been revised to include an initial excavation prior to the installation of the planks to reduce the risk of excavation plant colliding with the planks during the first stage of excavation for the shotcrete walls. | FSR Excavation FSR Plant and Equipment | Ensures adequate headroom for excavators, eliminating the risk of the boom striking the new bridge deck, which could cause structural failure or equipment rollover. | Update staging plans in construction program. |  | Matthijs Klinkert
EBTA | EBTA088 | 2025-11-05 | NEL-STH-NSA-5602-SBR-REP-0001 | DESIGN REPORT - B100 – BR601 – NEL OVER KOONUNG CREEK | Design | Implemented | A wingwall has been added to provide safe maintenance access around BR120 Pier 3. | FSR Working at Heights | Provides a level, engineered platform for inspectors, eliminating the risk of slips and falls associated with navigating steep, un-benched embankments around bridge piers. | Verify handrail requirements for wingwall. |  | Matthijs Klinkert
EBTA | EBTA089 | 2025-11-05 | NEL-STH-NSA-5400-CTW-REP-0003 | Design Report – E018-5400-0005 – ELGAR ROAD PHASE 2 – TEMPORARY TRAFFIC SIGNALS |  |  | There is no table with the columns 'Number', 'Item', 'Status', and 'Design Stage' visible in the provided images. However, the 'Safety in Design' (SiD) section describes the engineered safety methodology. It states that SiD workshops are undertaken for design packages, with risks, mitigation, and responsibilities captured in registers included in the design report. Temporary works and constructability are considered, involving input from various stakeholders, including VicRoads Signal Services and Region teams, from a Road Safety Perspective. Detailed outcomes from SiD and design reviews are to be documented in the detailed design report if applicable. |  |  |  |  | Matthijs Klinkert
EBTA | EBTA090 | 2025-11-05 | NEL-STH-NSA-5407-SBR-REP-0001 | DESIGN REPORT - B093-BR402 – ELGAR ROAD BRIDGE | Design | Adopted | Adopting maintenance-free ground anchors to eliminate risks associated with potential future maintenance operations | FSR Piling FSR Excavation | Removes the need for future maintenance crews to access the site and use high-pressure hydraulic stressing equipment, eliminating burst/failure risks and ground disturbance. | Archive anchor durability specs. |  | Matthijs Klinkert
EBTA | EBTA091 | 2025-11-05 | NEL-STH-NSA-5407-SBR-REP-0001 | DESIGN REPORT - B093-BR402 – ELGAR ROAD BRIDGE | Design | Adopted | Implementing a service walkway along the south abutment to allow for safe inspection and replacement of bridge barriers | FSR Working at Heights FSR Traffic Management | Provides a dedicated, secure platform for inspectors, preventing falls and separating personnel from live traffic or steep embankments during barrier checks. | Verify handrail compliance on walkway. |  | Matthijs Klinkert
EBTA | EBTA092 | 2025-11-05 | NEL-STH-NSA-5407-SBR-REP-0001 | DESIGN REPORT - B093-BR402 – ELGAR ROAD BRIDGE | Material | Adopted | Implementation of fibre reinforced concrete for the infill between the back of the fascia panel and front of shotcrete wall. This removes safety risks associated with placing and tying traditional rebar to the shotcrete wall at heights and in confined spaces. | FSR Working at Heights FSR Confined Space FSR Formwork & Falsework | Eliminates the manual handling and awkward postures required to tie steel in a tight gap (confined space) at height, reducing musculoskeletal injury risks. | Approve mix design for fibre concrete. |  | Matthijs Klinkert
EBTA | EBTA093 | 2025-11-05 | NEL-STH-NSA-5200-CTW-REP-0002 | DESIGN REPORT - B201 TEMPORARY SUP PACKAGE 5 - KAMPMAN STREET (CRN-12302) | Design | Complete | User safety – signs and lines to assist way-finding. Desirable grades with clearance to obstacles selected. Pram ramps provided to highlight pedestrian crossing locations | FSR Traffic Management | Clear wayfinding and pram ramps predict pedestrian behavior, reducing the likelihood of slips, trips, falls, and accidental entry into vehicle paths. | Audit signage installation. |  | Matthijs Klinkert
EBTA | EBTA094 | 2025-11-05 | NEL-STH-NSA-5200-CTW-REP-0002 | DESIGN REPORT - B201 TEMPORARY SUP PACKAGE 5 - KAMPMAN STREET (CRN-12302) | Design | Complete | Utility avoidance – 3D utilities model used in coordination with SUP design model to avoid risk of clashes and associated fatal and severe risks. | FSR Utilities and Services FSR Excavation | Virtual clash detection identifies conflicts before breaking ground, preventing catastrophic strikes on gas, power, or water assets which carry high fatality risks. | Update utility model with potholing data. |  | Matthijs Klinkert
EBTA | EBTA095 | 2025-11-05 | NEL-STH-NSA-5500-CTW-REP-0003 | DESIGN REPORT - B115 – DONCASTER ROAD INTERCHANGE – TEMPORARY WORKS STAGE 1.1 DESIGN | Design | Implemented | Digital engineering tools (iTwin) have been used to avoid clashes with other design elements, avoiding the potential need for change during construction. | FSR Plant and Equipment FSR Excavation | Prevents "clash on site" scenarios which often force ad-hoc, unplanned, and high-risk rework or demolition activities involving heavy plant. | Generate inter-disciplinary clash report. |  | Matthijs Klinkert
EBTA | EBTA096 | 2025-11-05 | NEL-STH-NSA-5500-CTW-REP-0003 | DESIGN REPORT - B115 – DONCASTER ROAD INTERCHANGE – TEMPORARY WORKS STAGE 1.1 DESIGN | Management | Implemented | Review of FSRs based on SiD register of prelim design to be undertaken by design and construction team. From this review, the team will decide which FSRs can be eliminated and mitigated by design or construction method. | FSR Chain of Responsibility | Ensures that safety accountabilities and risk information are passed correctly from the design team to the construction team, preventing gaps in risk management | Sign off SiD register. |  | Matthijs Klinkert
EBTA | EBTA097 | 2025-11-05 | NEL-STH-NSA-5500-CTW-REP-0003 | DESIGN REPORT - B115 – DONCASTER ROAD INTERCHANGE – TEMPORARY WORKS STAGE 1.1 DESIGN | Management | Ongoing | 4D model to be used as a communication and planning tool to ensure right first-time build. | FSR Traffic Management FSR Plant and Equipment | Visualizing the sequence highlights dangerous simultaneous operations (SIMOPS) or plant congestion issues before they occur on site. | Run 4D simulation for next stage. |  | Matthijs Klinkert
EBTA | EBTA098 | 2025-11-05 | NEL-STH-NSA-5500-CTW-REP-0003 | DESIGN REPORT - B115 – DONCASTER ROAD INTERCHANGE – TEMPORARY WORKS STAGE 1.1 DESIGN | Design | Closed – proposal assessed to be not feasible | Potential to omit ramp T1 (or make single bus lane) being investigated. On-going investigation with Traffic Modelling team. | FSR Traffic Management FSR Excavation | Omitting the ramp would completely eliminate the construction footprint for that section, removing all associated interface risks with live traffic and deep excavation hazards. | Review traffic model results. |  | Matthijs Klinkert
EBTA | EBTA099 | 2025-11-05 | NEL-STH-NSA-5900-CDR-REP-0002 | Design Report - B155 - Water Sensitive Urban Design |  |  | Engineered Safety is the next generation of safety in design and looks to engineer out risk and engineer in health at every stage of a project lifecycle for our clients and product end user through trusted and collaborative partnerships within the alliance and our supply chain. With inclusivity and connectivity across functions, we listen to and learn from our people improving how we plan for and go to work every day. Refer to packages B064 and B080 for the engineering safety initiatives that were incorporated for WSUD assets. |  |  |  |  | Matthijs Klinkert
EBTA | EBTA100 | 2025-11-05 | NEL-STH-NSA-5500-CUW-REP-0002 | DESIGN REPORT - B030 - U011 - YVW - WATER - W083, W110 |  | N/A | Table not in use. |  |  |  |  | Matthijs Klinkert
EBTA | EBTA101 | 2025-11-05 | NEL-STH-NSA-5400-CUS-REP-0002 | DESIGN REPORT - B127 – UTILITIES – SEWER S128A & S128B |  |  | Engineered Safety is the next generation of safety in design and aims to engineer out risk and engineer in health at every stage of a project lifecycle. For this design package, no Engineered Safety items have been considered, as it will be constructed by the Eastern Freeway Upgrades – Tram to Springvale Project. |  |  |  |  | Matthijs Klinkert
EBTA | EBTA102 | 2025-11-05 | NEL-STH-NSA-5900-CUM-REP-0001 | DESIGN REPORT - B215 – 5900 – INCIDENT RESPONSE BUILDING COMBINED UTILITIES | Design | Implemented | Digital Engineering – coordinated and fully federated model used to develop utility alignments and prevent clashes. | FSR Utilities and Services FSR Excavation | "Virtual construction" identifies and resolves utility conflicts (clashes) in the design phase, preventing catastrophic strikes on live gas, power, or water mains during excavation. | Update federated model with pothole data. |  | Matthijs Klinkert
EBTA | EBTA103 | 2025-11-05 | NEL-STH-NSA-5900-CUM-REP-0001 | DESIGN REPORT - B215 – 5900 – INCIDENT RESPONSE BUILDING COMBINED UTILITIES | Design | Implemented | Minimised excavation extent and depth in former landfill sites. Known areas of contamination and ACM (Asbestos Containing Materials). • horizontal alignments coordinated within combined (water & sewer) trench. • vertical alignment coordinated at minimum depth. | FSR Excavation FSR Asbestos | Reducing the volume and depth of excavation directly reduces the amount of contaminated soil and Asbestos Containing Material (ACM) that workers are exposed to. | Review soil contamination management plan. |  | Matthijs Klinkert
EBTA | EBTA104 | 2025-11-05 | NEL-STH-NSA-5900-CUM-REP-0001 | DESIGN REPORT - B215 – 5900 – INCIDENT RESPONSE BUILDING COMBINED UTILITIES | Design | Implemented | Risk of trench collapse in variable (uncontrolled fill) ground conditions minimised by vertical alignment coordination at minimum depth (900mm cover) | FSR Excavation | Keeping the alignment shallow (approx. 900mm) significantly reduces the risk of trench wall collapse and engulfment compared to deep excavations in unstable, uncontrolled fill. | Verify trench depth onsite. |  | Matthijs Klinkert
EBTA | EBTA105 | 2025-11-05 | NEL-STH-NSA-5122-SBS-REP-0001 | Design Report - B050 - BS106 – Bulleen Road SUP Bridge | Methodology | Implemented | Construction staging has been investigated and will be implemented by the Worksite Traffic Management Plan to delineate and minimize the duration/extent of high-risk activities working near live traffic with proposed temporary barrier works and associated signage. | FSR Traffic Management | Minimising the duration of work near the road and using physical delineation reduces the statistical likelihood of a vehicle entering the workspace and striking personnel. | Audit traffic control setup. |  | Matthijs Klinkert
EBTA | EBTA106 | 2025-11-05 | NEL-STH-NSA-5122-SBS-REP-0001 | Design Report - B050 - BS106 – Bulleen Road SUP Bridge | Precast | Implemented | SPARK Central Preliminary Design updated from fabricated steel super structure to precast concrete super structure reducing structure whole of life maintenance activities | FSR Working at Heights FSR Traffic Management | Eliminates the need for future repainting and extensive steel maintenance, significantly reducing the exposure of maintenance crews to working at heights over live traffic. | Update maintenance manual. |  | Matthijs Klinkert
EBTA | EBTA107 | 2025-11-05 | NEL-STH-NSA-5122-SBS-REP-0001 | Design Report - B050 - BS106 – Bulleen Road SUP Bridge | Methodology | Implemented | Pier diaphragm updated from cast insitu reinforced concrete to grout wet joint and post tensioned stress bar connection for Super T girder continuity removing need for significant temporary support of girders, formwork and steel reinforcement fabrication in the median of the freeway | FSR Formwork & Falsework FSR Traffic Management | Removes the need for significant temporary propping, formwork erection, and steel fixing in the freeway median, removing workers from a high-risk zone adjacent to high-speed traffic. | Review stressing procedure. |  | Matthijs Klinkert
EBTA | EBTA108 | 2025-11-05 | NEL-STH-NSA-5122-SBS-REP-0001 | Design Report - B050 - BS106 – Bulleen Road SUP Bridge | Design | Implemented | Pier pile cap and abutment levels were raised to reduce the excavation depth. | FSR Excavation FSR Confined Space | Shallower excavations significantly reduce the risk of trench collapse (engulfment) and often eliminate the classification of the pit as a Confined Space. | Verify as-built levels. |  | Matthijs Klinkert
EBTA | EBTA109 | 2025-11-05 | NEL-STH-NSA-5100-CUS-REP-0003 | DESIGN REPORT - B194 - UTILITIES - SEWER - U005 (S076, S077) | Design | Completed | Elimination of a siphon crossing the Eastern Freeway by rediverting the sewer main onto the Koonung Park Reserve. Justification: Avoid crossing significant infrastructure including the BEBO drainage structure and the Eastern Freeway. | FSR Utilities and Services FSR Traffic Management | Avoids high-risk under-boring or trenching across major infrastructure (freeway & drainage), eliminating the risk of striking critical assets or disrupting freeway traffic. | Confirm new alignment easement. |  | Matthijs Klinkert
EBTA | EBTA110 | 2025-11-05 | NEL-STH-NSA-5100-CUS-REP-0003 | DESIGN REPORT - B194 - UTILITIES - SEWER - U005 (S076, S077) | Design | Completed | Maintainability – majority of the maintenance holes are located within the Koonung Park Reserve which is accessible to YVW. Justification: Design ensures that the proposed sewer accommodates for safe maintenance accessibility by the utility asset owner. | FSR Traffic Management FSR Confined Space | Locating assets in the reserve completely separates future maintenance crews from live traffic hazards, avoiding the need for high-risk road closures during routine checks. | Confirm maintenance vehicle access path. |  | Matthijs Klinkert
EBTA | EBTA111 | 2025-11-05 | NEL-STH-NSA-5100-CUS-REP-0003 | DESIGN REPORT - B194 - UTILITIES - SEWER - U005 (S076, S077) | Methodology | Completed | Constructability – Majority of the maintenance holes are located behind the site hoarding. Justification: Avoid further risks and impacts the public and nearby residents. | FSR Traffic Management | Physical separation via hoarding prevents members of the public and local residents from inadvertently accessing the site or falling into open excavations/pits. | Audit hoarding integrity. |  | Matthijs Klinkert
EBTA | EBTA112 | 2025-11-05 | NEL-STH-NSA-5100-CUS-REP-0003 | DESIGN REPORT - B194 - UTILITIES - SEWER - U005 (S076, S077) | Design | Closed | Digital Engineering – coordinated and fully federated model. Justification: Digital tools to aid design coordination and help with visualisation and understanding of the design and associated risk and hazard potential. Tools such as the federated 3D model and GIS have been used to inform the SiD reviews and undertake clash detection. | FSR Utilities and Services FSR Excavation | Allows the team to "see" underground hazards and spatial conflicts virtually, preventing on-site utility strikes and unplanned high-risk rework. | Run final clash detection report. |  | Matthijs Klinkert
EBTA | EBTA113 | 2025-11-05 | NEL-STH-NSA-5100-CUS-REP-0003 | DESIGN REPORT - B194 - UTILITIES - SEWER - U005 (S076, S077) | Methodology | Closed – Existing DN525 could not be located on site. | Safety, Constructability – Reuse of existing 525 dia main as enveloper for proposed sewer. Justification: Avoids vegetation impacts and reduced traffic interfaces on Kosciusko Rd. relocate Manholes out of public roadways. | FSR Excavation FSR Traffic Management | Elimates the need for open trenching across Kosciusko Rd. This significantly reduces traffic disruption and eliminates the risk of excavating near live traffic and vegetation. | Verify condition of existing enveloper. |  | Matthijs Klinkert
EBTA | EBTA114 | 2025-11-05 | NEL-STH-NSA-5100-CUS-REP-0003 | DESIGN REPORT - B194 - UTILITIES - SEWER - U005 (S076, S077) | Methodology | Completed | Trenchless Construction Methodology – The sewer will be installed utilising a pipejacking / bored pipe construction methodology contingent on the ground conditions. Justification: The proposed pipejacking / bored pipe construction avoids impacting the existing Tree Protection Zones within the Koonung Creek Reserve and minimises the disruption to the public as majority of the Launch / retrieval pits are located behind the construction hoarding. | FSR Excavation FSR Traffic Management | Locating launch/retrieval pits behind hoarding and avoiding open trenches minimizes disruption and eliminates the risk of the public interacting with deep excavations or plant equipment. | Approve launch pit locations. |  | Matthijs Klinkert
EBTA | EBTA115 | 2025-11-05 | NEL-STH-NSA-5100-CUS-REP-0003 | DESIGN REPORT - B194 - UTILITIES - SEWER - U005 (S076, S077) | Design | Completed | Emergency Relief Structure removed from the design following YVW modelling of the proposed sewer alignment and upsizing the sewer from OD272 GRP pipe to an OD550 GRP pipe. Justification: The increased capacity in the sewer network eliminates any overflows into the stormwater network. | FSR Utilities and Services FSR Confined Space FSR Excavation | Preventing overflows eliminates exposure to raw sewage (biological hazard). Removing the physical structure eliminates the construction of a deep shaft and a permanent confined space asset. | Archive hydraulic model report. |  | Matthijs Klinkert
EBTA | EBTA116 | 2025-11-05 | NEL-STH-NSA-5500-CTW-REP-0023 | Design Report – E018-5500-0023 – DONCASTER STAGE D2.1 – TEMPORARY TRAFFIC SIGNALS |  |  | An Engineered Safety section is present under '9. Safety in Design'. It specifies that SiD (Safety in Design) workshops are undertaken for the civil 2D alignment throughout the detailed design phase of the different design packages. All SiD risks, proposed mitigation, residual risks and nominated 'owners' of those risks are identified and captured for all design packages, with registers included in the design report for each package. Temporary works and constructability are considered, with formal and informal meetings and reviews by Eastern BTA and VicRoads teams. Outcomes from the SiD and DTP preliminary design review are documented in the detailed design report if applicable. |  |  |  |  | Matthijs Klinkert
EBTA | EBTA117 | 2025-11-05 | NEL-STH-NSA-5900-STG-REP-0004 | DESIGN REPORT - B110 - MISCELLANEOUS STRUCTURES PACKAGE 2 | Precast | Closed | Box culvert is precast elements where possible, to minimise FRP works on site and reduce working at height. | FSR Formwork & Falsework FSR Working at Heights | Moving construction to a factory environment eliminates the fall risks and physical strain associated with erecting formwork and tying steel reinforcement in a live creek environment. | Inspect precast units upon delivery. |  | Matthijs Klinkert
EBTA | EBTA118 | 2025-11-05 | NEL-STH-NSA-5900-STG-REP-0004 | DESIGN REPORT - B110 - MISCELLANEOUS STRUCTURES PACKAGE 2 | Methodology | Closed | Box culvert staging to be further considered to consider constructability adjacent to services. | FSR Utilities and Services FSR Excavation | Careful staging ensures that heavy excavation plant maintains safe standoff distances from live underground assets, preventing service strikes. | Review staging plan against utility model. |  | Matthijs Klinkert
EBTA | EBTA119 | 2025-11-05 | NEL-STH-NSA-5900-STG-REP-0004 | DESIGN REPORT - B110 - MISCELLANEOUS STRUCTURES PACKAGE 2 | Design | Closed | Reducing scope of access box culvert extent to be further considered to minimise onsite construction works including manual handling on site. | FSR Formwork & Falsework FSR Excavation | Reducing the physical scope of the structure directly reduces the total man-hours workers are exposed to site hazards, excavation risks, and physical fatigue. | Review design scope reduction proposal. |  | Matthijs Klinkert
EBTA | EBTA120 | 2025-11-05 | NEL-STH-NSA-5900-STG-REP-0004 | DESIGN REPORT - B110 - MISCELLANEOUS STRUCTURES PACKAGE 2 | Methodology | Closed | Form safe working platform/surface during construction of ITS maintenance platform | FSR Working at Heights FSR Scaffolding | Establishing a certified, stable working surface ensures workers have secure footing during installation, preventing falls and slips. | Verify temporary works design for platform. |  | Matthijs Klinkert
EBTA | EBTA121 | 2025-11-05 | NEL-STH-NSA-5100-CTW-REP-0002 | Design Report - Bulleen Road Interchange - TEMPORARY WORKS DESIGN STAGE B2.0 | Methodology | Open | Based on discussion with Construction team, tree protection zone details are covered under VEDMP submission and installed as a temporary environmental artefact. It might be appropriate to repeat the details in the drawings as a continuing control before tree use. | FSR Plant and Equipment FSR Excavation | Physical delineation of TPZs prevents heavy plant from entering unstable ground zones near root systems, reducing the risk of machinery tipping or striking protected vegetation. | Verify TPZ fencing installation. |  | Matthijs Klinkert
EBTA | EBTA122 | 2025-11-05 | NEL-STH-NSA-9002-CFM-REP-0001 | Design Report - B034 Flood Modelling Report - Koonung Creek | Design | Proposed/Constructed | Raised noise mounds and flood walls at Koonung Creek Wetlands | FSR Excavation | Physical barriers separate the public and infrastructure from flood waters, reducing the risk of drowning or water damage during high-flow events. | Check as-built mound levels. |  | Matthijs Klinkert
EBTA | EBTA123 | 2025-11-05 | NEL-STH-NSA-9002-CFM-REP-0001 | Design Report - B034 Flood Modelling Report - Koonung Creek | Design | Proposed/Constructed | Flood walls and traffic barriers at Valda Wetlands, Doncaster Interchange, Koonung Creek Reserve Wetlands (adj Wilburton Pde), and Bulleen Interchange | FSR Traffic Management | Dual-purpose barriers protect infrastructure from flood waters while simultaneously preventing errant vehicles from entering wetland/water hazard areas. | Audit barrier integrity. |  | Matthijs Klinkert
EBTA | EBTA124 | 2025-11-05 | NEL-STH-NSA-9002-CFM-REP-0001 | Design Report - B034 Flood Modelling Report - Koonung Creek | Design | Constructed/Planned | Koonung Creek channel realignment and regrading at Bulleen Rd & between Elgar Rd and Doncaster Rd | FSR Excavation | Engineered regrading stabilizes the creek banks, reducing erosion and the risk of bank collapse (engulfment) for maintenance workers and the public. | Monitor bank stability. |  | Matthijs Klinkert
EBTA | EBTA125 | 2025-11-05 | NEL-STH-NSA-9002-CFM-REP-0001 | Design Report - B034 Flood Modelling Report - Koonung Creek | Design | Proposed | Debris poles and debris deflection fins at new culvert BR605 (Valda) | FSR Work On, Over Or Adjacent to Water FSR Plant and Equipment | Engineered debris controls prevent clogging, eliminating the need for maintenance crews to perform high-risk manual clearing works during storm events or high-flow conditions. | Verify installation against design drawings. |  | Matthijs Klinkert
EBTA | EBTA126 | 2025-11-05 | NEL-STH-NSA-9002-CFM-REP-0001 | Design Report - B034 Flood Modelling Report - Koonung Creek | Design | Proposed/Constructed | Secondary path shield culverts with 10% AEP+CC immunity | FSR Traffic Management FSR Work On, Over Or Adjacent to Water | Ensuring the path remains passable during significant rain events prevents pedestrians and cyclists from being stranded or attempting to cross hazardous flooded sections. | Check flood modeling report. |  | Matthijs Klinkert
EBTA | EBTA127 | 2025-11-05 | NEL-STH-NSA-9002-CFM-REP-0001 | Design Report - B034 Flood Modelling Report - Koonung Creek | Design | Proposed/Constructed | Property floodwalls at Valda Avenue/Jocelyn Ave and Winfield Reserve | FSR Excavation FSR Work On, Over Or Adjacent to Water | Physical barriers protect residential properties from inundation, preventing structural damage, electrical hazards, and exposure to contaminated floodwaters for residents. | Verify wall height relative to flood levels. |  | Matthijs Klinkert
EBTA | EBTA128 | 2025-11-05 | NEL-STH-NSA-9002-CFM-REP-0001 | Design Report - B034 Flood Modelling Report - Koonung Creek | Design | Proposed/Constructed | Upsized and new trunk and cross drainage (e.g., Doncaster Park and Ride, High St, Estelle St, Ayr St/Outhwaite Ave) | FSR Excavation FSR Traffic Management | Increasing drainage capacity prevents flash flooding on roadways, significantly reducing the risk of vehicle hydroplaning and loss-of-control accidents during storms. | Confirm pipe sizes in as-builts. |  | Matthijs Klinkert
EBTA | EBTA129 | 2025-11-05 | NEL-STH-NSA-9002-CFM-REP-0001 | Design Report - B034 Flood Modelling Report - Koonung Creek | Design | Proposed | Flood gates at Estelle St and Kampman St diversion pipes | FSR Work On, Over Or Adjacent to Water FSR Excavation | Prevents floodwaters from surcharging the drainage network and inundating residential streets, removing the risk of public exposure to hazardous floodwaters. | Verify gate operation mechanism. |  | Matthijs Klinkert
EBTA | EBTA130 | 2025-11-05 | NEL-STH-NSA-9002-CFM-REP-0001 | Design Report - B034 Flood Modelling Report - Koonung Creek | Design | Proposed | Open overflow (dry) channels within Koonung Creek Reserve | FSR Work On, Over Or Adjacent to Water FSR Excavation | Provides a designated, safe path for excess water, preventing uncontrolled overland flows that could scour banks or trap pedestrians on public paths. | Inspect channel grading. |  | Matthijs Klinkert
EBTA | EBTA131 | 2025-11-05 | NEL-STH-NSA-9002-CFM-REP-0001 | Design Report - B034 Flood Modelling Report - Koonung Creek | Design | Proposed/Constructed | Permeable and impermeable road barriers at Bulleen to maintain flow path and control afflux | FSR Traffic Management FSR Work On, Over Or Adjacent to Water | Manages flood levels to prevent upstream property inundation while ensuring the roadway remains passable and safe from wash-outs. | Verify barrier permeability spec. |  | Matthijs Klinkert
EBTA | EBTA132 | 2025-11-05 | NEL-STH-NSA-9002-CFM-REP-0001 | Design Report - B034 Flood Modelling Report - Koonung Creek | Design | Proposed/Constructed | Bridge, culvert and SUP (shared user path) raising at key points (BR601, BR605, BR607, BS401 etc.) | FSR Traffic Management FSR Work On, Over Or Adjacent to Water | Ensures critical transport routes and evacuation paths remain open and dry during storm events, preventing isolation of the workforce or community. | Check as-built levels against flood model. |  | Matthijs Klinkert
EBTA | EBTA133 | 2025-11-05 | NEL-STH-NSA-9002-CFM-REP-0001 | Design Report - B034 Flood Modelling Report - Koonung Creek | Design | Proposed/Constructed | Reinforcement and upsizing of kerbs and road drainage in road network and flood-prone ramps/exits | FSR Traffic Management FSR Work On, Over Or Adjacent to Water | Improving drainage capacity on ramps and exits prevents hydroplaning and flash flooding on high-speed road networks, reducing the risk of vehicle accidents and loss of control. | Verify drainage capacity calculations. |  | Matthijs Klinkert
EBTA | EBTA134 | 2025-11-05 | NEL-STH-NSA-5100-CTW-REP-0014 | DESIGN REPORT - E018-5100-0022 - Ramp U4 switch to ultimate alignment - TEMPORARY TRAFFIC SIGNALS |  |  | Section 9 'Safety in Design' details the engineered safety process for the package. SiD (Safety in Design) workshops are undertaken during the detailed design phase. All SiD risks, proposed mitigation, residual risks and risk owners are captured and included in the design report for each package in accordance with the Eastern BTA Design Management Plan. Temporary works and constructability are considered throughout, with constraints communicated early, and the design is reviewed by Eastern BTA and VicRoads Signal Services (for road safety). Outcomes of SiD and DTP preliminary design review are documented in the detailed design report if applicable. |  |  |  |  | Matthijs Klinkert
EBTA | EBTA135 | 2025-11-05 | NEL-STH-NSA-5100-CUW-REP-0003 | DESIGN REPORT - B020 - UTILITIES - YVW - WATER - BULLEEN INTERCHANGE - W076, W079 | Methodology | Implemented | Temporary water main in stage one to traverse along the rear of the existing walls to mitigate risk of interface with public and to eliminate interface with construction plant and personnel whilst keeping the asset within the Project’s construction zone | FSR Utilities and Services FSR Plant and Equipment FSR Traffic Management | Isolating the temporary main removes the risk of accidental plant strikes and protects the public from potential bursts or high-pressure leaks. | Verify temporary alignment on site. |  | Matthijs Klinkert
EBTA | EBTA136 | 2025-11-05 | NEL-STH-NSA-5100-CUW-REP-0003 | DESIGN REPORT - B020 - UTILITIES - YVW - WATER - BULLEEN INTERCHANGE - W076, W079 | Design | Implemented | Permanent water main to run under SUP for connection onto existing water main on Mountain View Road and Viewpoint Road to maintain sufficient clearance to proposed infrastructures in consideration of future maintenance of the water main | FSR Utilities and Services FSR Traffic Management | Locating the main under the SUP provides a safe, hardstand area for future maintenance crews, avoiding the need to work within live traffic lanes on Mountain View/Viewpoint Rd. | Confirm SUP pavement design load capacity. |  | Matthijs Klinkert
EBTA | EBTA137 | 2025-11-05 | NEL-STH-NSA-5100-CUW-REP-0003 | DESIGN REPORT - B020 - UTILITIES - YVW - WATER - BULLEEN INTERCHANGE - W076, W079 | Design | Implemented | Placement of proposed water main in accessible areas in consideration of future maintenance and replacement | FSR Utilities and Services FSR Excavation | Easy access reduces the physical strain, complexity, and excavation depth required for future repairs, minimizing the time crews spend in hazardous zones. | Review maintenance access plan. |  | Matthijs Klinkert
EBTA | EBTA138 | 2025-11-05 | NEL-STH-NSA-5115-SBS-REP-0001 | DESIGN REPORT - B046 - BS102 – BULLEEN RAMP SUP UNDERPASS | Methodology | Implemented | Top down construction for the bridge deck has been used to reduce the risk of working at height and permanent barriers at live edge will be installed prior to excavation. | FSR Working at Heights FSR Excavation | Installing permanent barriers before digging creates an immediate, engineered edge protection system, eliminating the risk of falls into the open excavation. | Approve barrier installation SWMS. |  | Matthijs Klinkert
EBTA | EBTA139 | 2025-11-05 | NEL-STH-NSA-5115-SBS-REP-0001 | DESIGN REPORT - B046 - BS102 – BULLEEN RAMP SUP UNDERPASS | Methodology | Implemented | Construction staging has been investigated and will be implemented by the Worksite Traffic Management Plan to delineate and minimize the duration/extent of high-risk activities working near live traffic with proposed temporary barrier works and associated signage. | FSR Traffic Management | Physical separation via barriers and reduced exposure time significantly lowers the statistical likelihood of vehicle-worker collisions. | Audit barrier installation. |  | Matthijs Klinkert
EBTA | EBTA140 | 2025-11-05 | NEL-STH-NSA-5115-SBS-REP-0001 | DESIGN REPORT - B046 - BS102 – BULLEEN RAMP SUP UNDERPASS | Design | Implemented | The proposed excavation profile minimises the risk of plant striking bridge deck without increasing risk of collapse of cut face during excavation. | FSR Excavation FSR Plant and Equipment | Prevents excavator booms from striking the overhead structure (avoiding equipment tipping/damage) while ensuring the trench walls remain stable for workers below. | Verify excavation profile onsite. |  | Matthijs Klinkert
EBTA | EBTA141 | 2025-11-05 | NEL-STH-NSA-5115-SBS-REP-0001 | DESIGN REPORT - B046 - BS102 – BULLEEN RAMP SUP UNDERPASS | Design | Implemented | Elimination of stone wall demolishing and permanent work outside the project boundary within the school property by reducing the underpass width. | FSR Demolition FSR Traffic Management | Completely removes demolition hazards (dust, noise, collapse) and eliminates the high-risk safety interface of working within an active school environment. | Confirm new boundary alignment. |  | Matthijs Klinkert
EBTA | EBTA142 | 2025-11-05 | NEL-STH-NSA-5115-SBS-REP-0001 | DESIGN REPORT - B046 - BS102 – BULLEEN RAMP SUP UNDERPASS | Design | Implemented | Enhanced safety and reduced the risk of clashes with the sewer system by increasing the spacing between piles and integrating a bridge beam, allowing for improved separation and construction flexibility. | FSR Utilities and Services FSR Piling | Increasing physical separation significantly lowers the risk of piling rigs striking the sewer, preventing biological contamination and ground instability. | Verify pile set-out coordinates. |  | Matthijs Klinkert
EBTA | EBTA143 | 2025-11-05 | NEL-STH-NSA-5115-SBS-REP-0001 | DESIGN REPORT - B046 - BS102 – BULLEEN RAMP SUP UNDERPASS | Design | Implemented | Implemented a top-mounted handrail system to mitigate working-at-heights risks, ensuring safer access and reducing the need for elevated work platforms during construction. | FSR Working at Heights | Top-mounting allows the handrails to be installed from a safe, stable surface, reducing the need for workers to lean over edges or use elevated work platforms (EWPs) in precarious positions. | Verify handrail fixation details. |  | Matthijs Klinkert
EBTA | EBTA144 | 2025-11-05 | NEL-STH-NSA-5115-SBS-REP-0001 | DESIGN REPORT - B046 - BS102 – BULLEEN RAMP SUP UNDERPASS | Design | Implemented | Strategically relocated utilities through the bridge using a squared sleeve design, optimizing the utility path while maintaining structural integrity and minimizing interference during construction. | FSR Utilities and Services FSR Formwork & Falsework | Optimizing the sleeve shape and location minimizes clashes with reinforcement and structural elements, reducing the need for on-site modifications or difficult manual handling during fit-off. | Check sleeve dimensions in pre-pour. |  | Matthijs Klinkert
EBTA | EBTA145 | 2025-11-05 | NEL-STH-NSA-5100-CTW-REP-0009 | DESIGN REPORT - E018E-5100-0010 – BULLEEN STAGE B2.1A TEMPORARY TRAFFIC SIGNALS |  |  | There is no table with the columns 'Number', 'Item', 'Status', and 'Design Stage' found in these pages. However, there is an 'Engineered Safety' section under '9. Safety in Design' that describes the procedural and review steps involved in Safety in Design (SiD), including workshops to identify risks, assessment of constructability, input from relevant stakeholders, and the documentation of outcomes in a design report. |  |  |  |  | Matthijs Klinkert
EBTA | EBTA146 | 2025-11-05 | NEL-STH-NSA-5200-CBR-REP-0002 | DESIGN REPORT - B069 – 5100/5200 ROAD BARRIERS WEST | Methodology | Implemented | Construction staging has been investigated and will be implemented by the Worksite Traffic Management Plan to delineate and minimize the duration/extent of high-risk activities working near live traffic with proposed temporary barrier works and associated signage. | FSR Traffic Management | Physical separation via barriers and reduced exposure time significantly lowers the statistical likelihood of vehicle-worker collisions. | Audit barrier installation. |  | Matthijs Klinkert
EBTA | EBTA147 | 2025-11-05 | NEL-STH-NSA-5500-CTW-REP-0004 | DESIGN REPORT - E018M – 5500 – 0004 - DONCASTER STAGE D1.1A – TEMPORARY TRAFFIC SIGNALS |  |  | An 'Engineered Safety' table with columns 'Number', 'Item', 'Status', and 'Design Stage' was not found in the provided pages. However, Section 9 'Safety in Design' outlines the safety methodology: SiD workshops are conducted throughout the detailed design phase for various design packages. All risks, proposed mitigations, residual risks, and nominated owners are identified and recorded. Temporary works and constructability are considered in all design solutions, alongside both internal and external reviews (including by VicRoads Signal Services and Road Safety teams). Outcomes from SiD and preliminary design reviews are documented in detailed design reports as applicable. |  |  |  |  | Matthijs Klinkert
EBTA | EBTA148 | 2025-11-05 | NEL-STH-NSA-5900-CNW-REP-0001 | Design Report - B038 - Acoustics - Traffic Noise Assessment |  |  | Section 9.2 "Engineered Safety" explicitly states: 'Not applicable to this design package. This is addressed by the relevant design packages noted in Section 6.3.' No table was found with the columns 'Number', 'Item', 'Status', and 'Design Stage' for engineered safety methods. |  |  |  |  | Matthijs Klinkert
EBTA | EBTA149 | 2025-11-05 | NEL-STH-NSA-5490-CTW-REP-0001 | DESIGN REPORT - B199 - SPRINGVALE ROAD STOCKPILE | Design | Implemented | The stockpile itself is an engineered safety measure to take trucks carrying soil off the roads. Without the stockpile, trucks would need to take the excess soil from site at a longer distance to an approved tip site, prolonging the time that the Trucks interface with the public and increasing the risk of an accident. | FSR Traffic Management | Eliminating the need for trucks to travel long distances to tip sites drastically reduces the duration and frequency of heavy vehicle interaction with the public, thereby lowering accident risks. | Verify stockpile stability. |  | Matthijs Klinkert
EBTA | EBTA150 | 2025-11-05 | NEL-STH-NSA-9004-CFM-REP-0001 | DESIGN REPORT - B035 FLOOD MODELLING REPORT - YARRA |  |  | There is no table with columns 'Number', 'Item', 'Status', and 'Design Stage' listing engineered safety methods in the provided images. However, there is an 'Engineered Safety' section (9.2) which explains: "Engineered Safety is the next generation of safety in design and looks to engineer out risk and engineer in health at every stage of a project lifecycle for our clients and product end user through trusted and collaborative partnerships within the alliance and our supply chain. With inclusivity and connectivity across functions, we listen to and learn from our people improving how we plan for and go to work every day." Section 9.2.1 states that the engineered safety initiatives that have been investigated/included are documented in the relevant drainage, civil and structures design packages. |  |  |  |  | Matthijs Klinkert
EBTA | EBTA151 | 2025-11-05 | NEL-STH-NSA-5119-SBR-REP-0001 | DESIGN REPORT - B047 - BR103 – SB NEL TO WB OVERHEAD STRUCTURE (RAMP U8) & SB NEL TO THOMPSONS RD | Methodology | Implemented | Construction staging has been investigated and will be implemented by the Worksite Traffic Management Plan to delineate and minimize the duration/extent of high-risk activities working near live traffic with proposed temporary barrier works and associated signage. | FSR Traffic Management | Physical separation via barriers and reduced exposure time significantly lowers the statistical likelihood of vehicle-worker collisions. | Audit barrier installation. |  | Matthijs Klinkert
EBTA | EBTA152 | 2025-11-05 | NEL-STH-NSA-5119-SBR-REP-0001 | DESIGN REPORT - B047 - BR103 – SB NEL TO WB OVERHEAD STRUCTURE (RAMP U8) & SB NEL TO THOMPSONS RD | Methodology | Implemented | Construction staging implemented to separate works around live traffic with a temporary diversion of traffic at Thompsons Road and Bulleen Road to remove the risk in the area with the bridge deck complete prior to opening to traffic and deliver works north of Thompsons when traffic is switched back to the permanent Bulleen Road Bridge. | FSR Traffic Management | By diverting traffic away from the active bridge deck work area, the risk of overhead heavy lifting occurring above live traffic is completely eliminated. | Verify diversion setup. |  | Matthijs Klinkert
EBTA | EBTA153 | 2025-11-05 | NEL-STH-NSA-5119-SBR-REP-0001 | DESIGN REPORT - B047 - BR103 – SB NEL TO WB OVERHEAD STRUCTURE (RAMP U8) & SB NEL TO THOMPSONS RD | Methodology | Implemented | Precast Driven Piles adopted over bored piles where possible to remove open hole and remove the need to dispose of pile spoil material. | FSR Excavation FSR Piling | Eliminates the hazard of "open holes" (deep excavations) which pose fall risks to personnel and collapse risks to adjacent plant. | Confirm pile driveability. |  | Matthijs Klinkert
EBTA | EBTA154 | 2025-11-05 | NEL-STH-NSA-5119-SBR-REP-0001 | DESIGN REPORT - B047 - BR103 – SB NEL TO WB OVERHEAD STRUCTURE (RAMP U8) & SB NEL TO THOMPSONS RD | Modularisation | Implemented | Steel reinforcement to pile cap bottom mat, pier column and crosshead will be modelled and prefabricated to drop, reducing on site steel reinforcement fabrication to the top mat/sides of the pile cap to tie in the prefabricated sections. | FSR Formwork & Falsework FSR Working at Heights | Significantly reduces the manual handling and repetitive strain injuries associated with tying steel in-situ, often in awkward positions or at height. | Verify cage lifting points. |  | Matthijs Klinkert
EBTA | EBTA155 | 2025-11-05 | NEL-STH-NSA-5119-SBR-REP-0001 | DESIGN REPORT - B047 - BR103 – SB NEL TO WB OVERHEAD STRUCTURE (RAMP U8) & SB NEL TO THOMPSONS RD | Methodology | Implemented | Self-Propelled Modular Transport (SPMT) construction method adopted for spans over the eastbound carriageway to enable spans to be assembled offline and deliver in single section to reduce working around live traffic, multiple carriageway closures and working at heights. | FSR Traffic Management FSR Working at Heights FSR Plant and Equipment | Assembling spans "offline" drastically reduces the time workers spend working at heights over live traffic and minimizes the need for high-risk carriageway closures. | Approve SPMT lift plan. |  | Matthijs Klinkert
EBTA | EBTA156 | 2025-11-05 | NEL-STH-NSA-5119-SBR-REP-0001 | DESIGN REPORT - B047 - BR103 – SB NEL TO WB OVERHEAD STRUCTURE (RAMP U8) & SB NEL TO THOMPSONS RD | Design | Implemented | Precast concrete piers and crossheads updated to insitu concrete and consolidated to a single profile column/crosshead to have reuse of formwork moulds and repeatability of works. | FSR Formwork & Falsework | "Repeatability of works" allows crews to become familiar with the specific hazards of the formwork system, reducing the likelihood of error compared to constantly changing bespoke setups. | Verify formwork design. |  | Matthijs Klinkert
EBTA | EBTA157 | 2025-11-05 | NEL-STH-NSA-5400-CUM-REP-0001 | Design Report - B128 - Combined Utilities | Design | Closed | Digital engineering tools (iTwin) have been used to avoid clashes with other design elements, avoiding the potential need for change during construction. | FSR Plant and Equipment FSR Excavation | Identifying clashes virtually prevents dangerous "clash on site" scenarios that often force unplanned, high-risk rework or demolition activities. | Generate clash report. |  | Matthijs Klinkert
EBTA | EBTA158 | 2025-11-05 | NEL-STH-NSA-5400-CUM-REP-0001 | Design Report - B128 - Combined Utilities | Design | Closed | Permanent utility relocations to maintain clearances to existing services, proposed services and new road assets (including retaining walls, noise walls, etc) to maintain clearances in accordance with DTP and utility asset owners guidelines | FSR Utilities and Services FSR Excavation | Adhering to DTP and asset owner guidelines for clearance ensures a safe buffer zone, preventing accidental strikes on live assets during construction and future maintenance. | Verify clearance on as-builts. |  | Matthijs Klinkert
EBTA | EBTA159 | 2025-11-05 | NEL-STH-NSA-5400-CUM-REP-0001 | Design Report - B128 - Combined Utilities | Design | Closed | Development of alignment and space-proofing designs undertaken with input from the USPs to ensure constructability and maintainability. | FSR Utilities and Services FSR Excavation | Ensuring adequate space for construction and future maintenance prevents overcrowding and clashes, reducing the risk of accidental strikes on adjacent infrastructure. | Finalize alignment drawings. |  | Matthijs Klinkert
EBTA | EBTA160 | 2025-11-05 | NEL-STH-NSA-5100-CTW-REP-0013 | DESIGN REPORT - E018-5100-0024 - Ramp U3 stage 4 - TEMPORARY TRAFFIC SIGNALS |  |  | There is no table with the columns 'Number', 'Item', 'Status', and 'Design Stage' visible in the provided images. However, there is an 'Engineered Safety' (Safety in Design - SiD) section, which details the methodology, context, and outcomes for safety in the design phase. The SiD section covers how workshops will be undertaken, risks will be tracked, and preliminary design reviewed for constructability and safety, as outlined in sections 9.1, 9.2, and 9.3 of the document. |  |  |  |  | Matthijs Klinkert
EBTA | EBTA161 | 2025-11-05 | NEL-STH-NSA-5604-SBR-REP-0001 | Design Report - B102 – BR603 – BEBO ARCH PROTECTION WEST OF DONCASTER ROAD | Methodology | Adopted and Closed | Adopt ductile iron piles in lieu of bored piles to utilise smaller rigs (excavator), thereby reducing the risk of bearing failure. Allows for minimising use of various plants in the trench (ie., option to only mobilise excavators). Protection slab width also reduced, thereby reducing overall excavation footprint, thus reducing likely impact to adjacent infrastructure. Relevant FSRs: Excavation, Piling. Controls: Engineering Controls. | FSR Excavation FSR Piling | Using smaller rigs reduces the overall excavation footprint and likely impact to adjacent infrastructure, while also minimizing the number of heavy plant interactions in the trench. | Verify pile load capacity. |  | Matthijs Klinkert
EBTA | EBTA162 | 2025-11-05 | NEL-STH-NSA-5604-SBR-REP-0001 | Design Report - B102 – BR603 – BEBO ARCH PROTECTION WEST OF DONCASTER ROAD | Design | Adopted and Closed | All works inside the BEBO has been precluded from the design. All proposed works for design package is above the BEBO, thus no construction activity is required in confined space. Relevant FSRs: Confined Space. Controls: Elimination. | FSR Confined Space | Completely eliminating work inside the BEBO structure removes the need for confined space entry, thereby eliminating all associated atmospheric and entrapment risks. | Confirm design clearance above BEBO. |  | Matthijs Klinkert
EBTA | EBTA163 | 2025-11-05 | NEL-STH-NSA-5604-SBR-REP-0001 | Design Report - B102 – BR603 – BEBO ARCH PROTECTION WEST OF DONCASTER ROAD | Methodology | Adopted and Closed | Consideration of pre-trial ductile iron pile testing which will provide ground lateral displacements and associated vibration to ensure existing BEBO is not compromised is being investigated. Also refer to notes on drawing sheet No 2081, which require hold point on the pre-trial results. Relevant FSRs: N/A. Controls: Engineering Controls. | NA | Verifies that piling vibration and ground movement won't destabilize the critical BEBO structure, preventing potential structural failure or collapse during works. | Review pre-trial results. |  | Matthijs Klinkert
EBTA | EBTA164 | 2025-11-05 | NEL-STH-NSA-5604-SBR-REP-0001 | Design Report - B102 – BR603 – BEBO ARCH PROTECTION WEST OF DONCASTER ROAD | Design | Adopted and Closed | Reinforcement design for slab to be detailed with consideration of utilising Bamtec reinforcement to increase productivity and to minimise the need for heavy manual on-site labour for placing and tying reinforcement. Relevant FSRs: N/A. Controls: Engineering Controls. | NA | Bamtec eliminates the need for individual bar tying, significantly reducing the heavy manual handling and repetitive strain injuries associated with traditional steel fixing. | Approve Bamtec detailing. |  | Matthijs Klinkert
EBTA | EBTA165 | 2025-11-05 | NEL-STH-NSA-5604-SBR-REP-0001 | Design Report - B102 – BR603 – BEBO ARCH PROTECTION WEST OF DONCASTER ROAD | Methodology | Transferred to Construction. Closed in design | Vehicle/machinery rollover and/or pedestrians falling into the deep excavation. Mitigation would be to designate no-go zones and introduce fall protection as part of the construction set up. Relevant FSRs: Excavation, Working from Heights. Controls: Engineering Controls. | FSR Excavation FSR Working at Heights | Physical exclusion zones and fall protection barriers separate people and plant from the open edge, preventing fatal falls or equipment tipping into the excavation. | Verify fall protection setup. |  | Matthijs Klinkert
EBTA | EBTA166 | 2025-11-05 | NEL-STH-NSA-5100-CTW-REP-0005 | Design Report - B140 – Zone 5100 - Bulleen Rd Interchange - Temporary Works Ramps U3/U4 | Management |  | Engineered Safety is discussed in Section 9.2 under the heading 'Engineered Safety.' It describes the next generation of safety in design, focusing on eliminating or engineering out risk and engineering in health at all project stages. Key initiatives include optimizing construction staging to reduce the duration and extent of high-risk activities (such as working near live traffic), revising alignment for flexibility, minimizing detoured ramp length, and single stage pedestrian crossings. Traditional safety measures such as installation of road safety barriers and safe interaction with existing services are also included. Further, underground utility risks are de-risked through detailed planning. Details are described narratively in the section, not as a table. | FSR Traffic Management FSR Utilities and Services | proactively engineering out risks at the design phase (such as minimizing detoured ramp lengths and single-stage crossings) reduces the overall hazard profile for both the public and workforce. | Review SiD Report Section 9.2. |  | Matthijs Klinkert
EBTA | EBTA167 | 2025-11-05 | NEL-STH-NSA-5500-CTW-REP-0008 | DESIGN REPORT - E018-5500-0006-01 - DONCASTER ROAD – NEW BUS STOP CONSTRUCTION – HERITAGE BOULEVARD BUS U-TURN TEMPORARY TRAFFIC SIGNALS |  |  | No table with the columns 'Number', 'Item', 'Status', and 'Design Stage' is present in the provided images. However, an Engineered Safety section is present under section 9 'Safety in Design'. The section describes the SiD (Safety in Design) process for the project, including workshops, capture of risks and mitigations, involvement of various stakeholders, and reviews by subject matter experts. Outcomes from the SiD and preliminary design review are to be documented in the detailed design report if applicable. |  |  |  |  | Matthijs Klinkert
EBTA | EBTA168 | 2025-11-05 | NEL-STH-NSA-5900-CUW-REP-0002 | DESIGN REPORT - B208 - WATER DISTRIBUTION NETWORK MODIFICATION FOR PRS TIE IN | Design | Implemented | Placement of proposed main and appurtenances in accessible areas where possible in consideration of future maintenance and replacement | FSR Utilities and Services FSR Excavation | Easy access reduces the physical strain, complexity, and excavation depth required for future repairs, minimizing the time crews spend in hazardous zones. | Review maintenance access plan. |  | Matthijs Klinkert
EBTA | EBTA169 | 2025-11-05 | NEL-STH-NSA-5900-CUW-REP-0002 | DESIGN REPORT - B208 - WATER DISTRIBUTION NETWORK MODIFICATION FOR PRS TIE IN | Design | Implemented | Permanent water main to maintain sufficient clearances to existing and proposed services, where feasible and practical, in accordance with MRWA guidelines and respective utility asset owners’ guidelines. Dispensations to be sought otherwise. | FSR Utilities and Services FSR Excavation | Adhering to guidelines for clearance ensures a safe buffer zone, preventing accidental strikes on live assets during construction and future maintenance. | Verify clearance on as-builts. |  | Matthijs Klinkert
EBTA | EBTA170 | 2025-11-05 | NEL-STH-NSA-5900-CUW-REP-0002 | DESIGN REPORT - B208 - WATER DISTRIBUTION NETWORK MODIFICATION FOR PRS TIE IN | Design | Implemented | Utilising MSCL pipe type mitigated the need for thrust restraints. | FSR Excavation FSR Confined Space | Eliminating large thrust blocks reduces the volume of excavation and concrete works required in the trench, potentially avoiding confined space entries for formwork. | Archive pipe material specs. |  | Matthijs Klinkert
EBTA | EBTA171 | 2025-11-05 | NEL-STH-NSA-5900-CUW-REP-0002 | DESIGN REPORT - B208 - WATER DISTRIBUTION NETWORK MODIFICATION FOR PRS TIE IN | Design | Implemented | Permanent water main on Ayr Street and Timber Ridge has been located in the road instead of footpath to avoid clashes and working in and around existing utilities. | FSR Utilities and Services FSR Traffic Management | Moving the alignment to the road avoids the congested utility corridor in the footpath, reducing the risk of striking other services (gas/power) often found in verges. | Confirm road reinstatement plan. |  | Matthijs Klinkert
EBTA | EBTA172 | 2025-11-05 | NEL-STH-NSA-5900-STG-REP-0003 | Design Report - B109 - Miscellaneous Structures Package 1 | Design | Complete | Retention of Culvert Vents where possible, minimising overall site works, but also exposure to key risk of potential asbestos exposure. | FSR Asbestos FSR Excavation | Minimizing disturbance of the existing ground and asset structure directly reduces the risk of releasing airborne asbestos fibers, protecting workers from chronic respiratory disease. | Update asbestos register. |  | Matthijs Klinkert
EBTA | EBTA173 | 2025-11-05 | NEL-STH-NSA-5900-STG-REP-0003 | Design Report - B109 - Miscellaneous Structures Package 1 | Design | Complete | The connection point of the vents into the culvert has not been changed, eliminating risks associated interaction with existing ageing asset. | FSR Utilities and Services FSR Confined Space | Avoiding physical alterations to the aging culvert prevents structural instability/collapse and eliminates the need for hazardous confined space entry to modify connections. | Verify as-built condition. |  | Matthijs Klinkert
EBTA | EBTA174 | 2025-11-05 | NEL-STH-NSA-5900-STG-REP-0003 | Design Report - B109 - Miscellaneous Structures Package 1 | Material | Complete | Light weight fill over BEBO arch adopted over strengthening or direct interaction with existing ageing asset. | FSR Excavation FSR Utilities and Services | Reduces the dead load on the fragile BEBO structure, preventing collapse, while eliminating the safety risks associated with invasive strengthening works. | Approve fill material submittal. |  | Matthijs Klinkert
EBTA | EBTA175 | 2025-11-05 | NEL-STH-NSA-5900-STG-REP-0003 | Design Report - B109 - Miscellaneous Structures Package 1 | Design | Complete | Optimising the plan dimensions and depth of the Bulleen Pumping Station shoring structure to minimise working from heights risks | FSR Working at Heights FSR Excavation | Reducing the physical depth and footprint of the shoring structure directly reduces the fall height and limits the complexity of worker access/egress in the excavation. | Review shoring design. |  | Matthijs Klinkert
EBTA | EBTA176 | 2025-11-05 | NEL-STH-NSA-5290-CRW-REP-0001 | Design Report – B189 – 5290 FREEWAY INTERFACE PACKAGE - WEST | Design | Implemented | EBTA Temporary Works Design B198 - Fwy Median Temporary Works - Burke Rd pavement design integrated with permanent works to avoid rework for the Western Alliance. | FSR Traffic Management FSR Plant and Equipment | Eliminates the need for a separate demolition and reconstruction phase, reducing the total duration of high-risk plant movements and traffic interface. | Verify pavement levels. |  | Matthijs Klinkert
EBTA | EBTA177 | 2025-11-05 | NEL-STH-NSA-5500-CUM-REP-0001 | DESIGN REPORT - B099 – COMBINED UTILITIES – DONCASTER INTERCHANGE | Digital | Complete | Digital Engineering – coordinated and fully federated model used to develop USP alignments and prevent clashes. | FSR Utilities and Services FSR Excavation | Virtual clash detection identifies conflicts before breaking ground, preventing dangerous "clash on site" scenarios that lead to unplanned, high-risk hand digging or rework. | Update federated model. |  | Matthijs Klinkert
EBTA | EBTA178 | 2025-11-05 | NEL-STH-NSA-5500-CUM-REP-0001 | DESIGN REPORT - B099 – COMBINED UTILITIES – DONCASTER INTERCHANGE | Design | Complete | Constructability – multiple options have been identified for utilities across Doncaster bridge and fully scrutinised to develop a constructable and safe to install utility route across the structure. Solution removes need for deep excavations (eg. launch and retrieval pits). However, there will be some work from height risk still for utility support installation. Cast in methods have been developed to limit the amount of work at height, and remove the need for insitu drilling and resin fixing of supports. | FSR Working at Heights FSR Excavation | Replacing post-drilled anchors with cast-in supports eliminates overhead drilling (silica dust/ergonomics) and reduces the time workers spend on ladders or platforms. | Inspect cast-in inserts. |  | Matthijs Klinkert
EBTA | EBTA179 | 2025-11-05 | NEL-STH-NSA-5500-CUM-REP-0001 | DESIGN REPORT - B099 – COMBINED UTILITIES – DONCASTER INTERCHANGE | Methodology | Complete | Installation method – work has been undertaken with USPs to ensure installation can be completed without the need for work at height. Essentially USPs can work from behind the bridge abutments to install utilities | FSR Working at Heights FSR Fall Prevention | Allows crews to work from a safe, stable ground-level platform behind the abutment rather than using EWPs or scaffolding over the void/traffic. | Approve installation SWMS. |  | Matthijs Klinkert
EBTA | EBTA180 | 2025-11-05 | NEL-STH-NSA-5500-CUM-REP-0001 | DESIGN REPORT - B099 – COMBINED UTILITIES – DONCASTER INTERCHANGE | Design | Complete | Temporary Works coordination – work has been undertaken to coordinate and amend design to work with the temporary traffic ramps required for the bridge construction staging | FSR Traffic Management FSR Formwork & Falsework | Ensuring the design accommodates temporary ramps prevents geometric conflicts and unsafe driving conditions during complex staging changes. | Verify ramp alignment. |  | Matthijs Klinkert
EBTA | EBTA181 | 2025-11-05 | NEL-STH-NSA-5500-CUM-REP-0001 | DESIGN REPORT - B099 – COMBINED UTILITIES – DONCASTER INTERCHANGE | Design | Complete | Route for E086A has been amended to run down Paul Street and to be mounted on existing assets (HV poles) reducing new works | FSR Utilities and Services FSR Excavation | Mounting on existing assets eliminates the need for new trenching or pole foundations, reducing ground disturbance and potential utility strikes. | Confirm pole structural capacity. |  | Matthijs Klinkert
EBTA | EBTA182 | 2025-11-05 | NEL-STH-NSA-5900-CTW-REP-0003 | Design Report – B141 – Flood Modelling Report – EBTA Phase 3 Works | Design |  | No table with the columns 'Number', 'Item', 'Status', and 'Design Stage' was found in the provided pages. However, there are multiple sections discussing engineered safety and mitigation measures, such as the inclusion of temporary hoarding/fencing and barriers in the EBTA Phase 3 works, concrete traffic barriers along the freeway, kerb line re-enforcement at certain locations, and inclusion of additional SUP bridges in reserves. Please refer to the relevant sections such as 9.2.1, 9.2.4, 9.2.5, and 10.1.2 for detailed narrative description of these measures. | FSR Traffic Management FSR Excavation | These physical controls (hoarding, barriers) provide robust separation between the workforce, the public, and high-risk hazards like live traffic or open excavations. | Audit barrier installation. |  | Matthijs Klinkert
EBTA | EBTA183 | 2025-11-05 | NEL-STH-NSA-5300-CUM-REP-0001 | Design Report - B088 - 5300 - Combined Utilities | Digital | Closed | Digital engineering tools (iTwin) have been used to avoid clashes with other design elements, avoiding the potential need for change during construction. | FSR Plant and Equipment FSR Excavation | Identifying clashes virtually prevents dangerous "clash on site" scenarios that often force unplanned, high-risk rework or demolition activities. | Generate clash report. |  | Matthijs Klinkert
EBTA | EBTA184 | 2025-11-05 | NEL-STH-NSA-5300-CUM-REP-0001 | Design Report - B088 - 5300 - Combined Utilities | Design | Closed | Permanent utility relocations to maintain clearances to existing services, proposed services and new road assets (including retaining walls, noise walls, etc) to maintain clearances in accordance with DtP and utility asset owners guidelines. | FSR Utilities and Services FSR Excavation | Maintaining strict clearances in accordance with DTP and asset owner guidelines ensures a safe buffer zone, preventing accidental strikes on live assets during construction and future maintenance. | Verify clearance on as-builts. |  | Matthijs Klinkert
EBTA | EBTA185 | 2025-11-05 | NEL-STH-NSA-5300-CUM-REP-0001 | Design Report - B088 - 5300 - Combined Utilities | Design | Closed | Development of alignment and space-proofing designs undertaken with input from the USPs to ensure constructability and maintainability. | FSR Utilities and Services FSR Excavation | Ensuring adequate space for construction and future maintenance prevents overcrowding and clashes, reducing the risk of accidental strikes on adjacent infrastructure. | Finalize alignment drawings. |  | Matthijs Klinkert
EBTA | EBTA186 | 2025-11-05 | NEL-STH-NSA-5490-CRW-REP-0001 | Design Report – B188 – 5490 FREEWAY INTERFACE PACKAGE - EAST | Design | Implemented | Pavement levels have been lifted and designed to avoid impacting and replacing underground services such as the twin 1800dia pipes just to the east of the interface line. This eliminates any safety and construction risks associated with replacing those services. | FSR Utilities and Services FSR Excavation | Avoiding the replacement of major large-diameter services eliminates the significant safety risks associated with deep excavations, heavy pipe lifting, and potential utility strikes. | Confirm pavement design levels. |  | Matthijs Klinkert
EBTA | EBTA187 | 2025-11-05 | NEL-STH-NSA-5490-CRW-REP-0001 | Design Report – B188 – 5490 FREEWAY INTERFACE PACKAGE - EAST | Design | Implemented | The freeway shoulder has been locally reduced in front of the Northern Tram Road Bridge abutment in order to avoid modifying and lengthening the Tram Road Bridge. This eliminates any safety and construction risks associated with lengthening the bridge. | FSR Working at Heights FSR Traffic Management | Eliminating bridge lengthening works removes the need for high-risk construction activities at height and over live traffic, significantly reducing the project's overall hazard profile. | Verify shoulder width compliance. |  | Matthijs Klinkert
EBTA | EBTA188 | 2025-11-05 | NEL-STH-NSA-5900-CTW-REP-0002 | Design Report – B141 – Flood Modelling Report – EBTA Phase 2 Works | Design |  | There is no explicit table with columns 'Number', 'Item', 'Status', and 'Design Stage' under engineered safety methods in the provided images. However, there is coverage of engineered safety-related measures, especially under the 'Hoarding and Barriers' section (10.1.2). It states that temporary hoarding/fencing and barriers are included in the EBTA Phase 2 works area as part of the main temporary works design case. This is intended to mitigate impacts on flooding, particularly as the EBTA hoarding sits more on the flood fringe and overlaps with Koonung Creek flooding. Sensitivity analysis for hoarding placement and impact has also been undertaken. In summary: Temporary hoarding/fencing and barriers are considered as engineered safety elements for the temporary works case in the EBTA Phase 2 area. | FSR Work On, Over Or Adjacent to Water FSR Traffic Management | Sensitivity analysis ensures the hoarding placement does not worsen local flooding, protecting the public and downstream properties while maintaining a secure site boundary. | Verify hoarding placement vs flood model. |  | Matthijs Klinkert
EBTA | EBTA189 | 2025-11-05 | NEL-STH-NSA-5900-STG-REP-0002_IFC |  | Design | Implemented | Overall, package offers flexibility in solutions so that alternative details can be used if unexpected conditions are found, which allows rapid reaction and therefore also supports construction progression, minimising risky reactive positions. | FSR Excavation FSR Plant and Equipment | Allows for rapid, engineered reactions to site surprises, preventing "risky reactive positions" where ad-hoc decisions often lead to accidents or unsafe rework. | Archive alternative details. |  | Matthijs Klinkert
EBTA | EBTA190 | 2025-11-05 | NEL-STH-NSA-5114-SBS-REP-0001 | DESIGN REPORT - B051 - BS107 – BULLEEN RAMP SUP UNDERPASS | Methodology | Implemented | Top down construction for the bridge deck has been used to reduce the risk of working at height and permanent barriers at live edge will be installed prior to excavation. | FSR Working at Heights FSR Excavation | Installing permanent barriers before digging creates an immediate, engineered edge protection system, eliminating the risk of falls into the open excavation. | Approve barrier installation SWMS. |  | Matthijs Klinkert
EBTA | EBTA191 | 2025-11-05 | NEL-STH-NSA-5114-SBS-REP-0001 | DESIGN REPORT - B051 - BS107 – BULLEEN RAMP SUP UNDERPASS | Methodology | Implemented | Construction staging has been investigated and will be implemented by the Worksite Traffic Management Plan to delineate and minimize the duration/extent of high-risk activities working near live traffic with proposed temporary barrier works and associated signage. | FSR Traffic Management | Physical separation via barriers and reduced exposure time significantly lowers the statistical likelihood of vehicle-worker collisions. | Audit barrier installation. |  | Matthijs Klinkert
EBTA | EBTA192 | 2025-11-05 | NEL-STH-NSA-5114-SBS-REP-0001 | DESIGN REPORT - B051 - BS107 – BULLEEN RAMP SUP UNDERPASS | Design | Implemented | Proposed excavation profile minimises risk of plant striking bridge deck without increasing risk of collapse of cut face during excavation. | FSR Work On, Over Or Adjacent to Water FSR Traffic Management | Sensitivity analysis ensures the hoarding placement does not worsen local flooding, protecting the public and downstream properties while maintaining a secure site boundary. | Verify hoarding placement vs flood model. |  | Matthijs Klinkert
EBTA | EBTA193 | 2025-11-05 | NEL-STH-NSA-5500-CTW-REP-0009 | DESIGN REPORT - E018K – 5500 – 0003 – DONCASTER STAGE D1.0B – TEMPORARY TRAFFIC SIGNALS | Design |  | There is no table with the columns 'Number', 'Item', 'Status', and 'Design Stage' in the provided images. However, an Engineered Safety (Safety in Design - SiD) section is present, explaining the context, methodology, and outcomes. SiD workshops are conducted for the design packages to identify mitigation measures and risks, with registers included in design reports. Temporary works and constructability are considered, and reviews are performed by Eastern BTA and VicRoads subject matter experts. | FSR Excavation FSR Plant and Equipment | Allows for rapid, engineered reactions to site surprises, preventing "risky reactive positions" where ad-hoc decisions often lead to accidents or unsafe rework. | Archive alternative details. |  | Matthijs Klinkert
EBTA | EBTA194 | 2025-11-05 | NEL-STH-NSA-5100-CTW-REP-0004 | Design Report - B118 - 5100 Bulleen Road Interchange - Temporary Works Design - Stage B1.2 | Digital |  | 3D DESIGN MODEL – B118 STAGE 1.2 TEMPORARY BARRIERS | FSR Working at Heights FSR Excavation | Installing permanent barriers before digging creates an immediate, engineered edge protection system, eliminating the risk of falls into the open excavation. | Approve barrier installation SWMS. |  | Matthijs Klinkert
EBTA | EBTA195 | 2025-11-05 | NEL-STH-NSA-5100-CTW-REP-0004 | Design Report - B118 - 5100 Bulleen Road Interchange - Temporary Works Design - Stage B1.2 | Digital |  | 3D DESIGN MODEL – B118 STAGE 1.2 PAVEMENT MARKING | FSR Traffic Management | Physical separation via barriers and reduced exposure time significantly lowers the statistical likelihood of vehicle-worker collisions. | Audit barrier installation. |  | Matthijs Klinkert
EBTA | EBTA196 | 2025-11-05 | NEL-STH-NSA-5200-CUM-REP-0001 | Design Report - B065 - Utilities – Combined Utilities Zone 5200 | Design |  | An SiD (Safety in Design) workshop for the Preliminary Design was undertaken on 17/07/2023. All SiD risks, proposed mitigation, residual risks, and nominated 'owners' of those risks were identified and captured with registers included in the design report showing risks relating to the design package in accordance with the NELSA Design Management Plan. SiD will be undertaken throughout the detailed design phase. Temporary works and constructability are to be considered throughout the design process in the preparation of design solutions, with ongoing input from NELSA CNOP and the design review process. Major constructability constraints will be communicated as early as identified to allow for consideration in design. NELSA CNOP is expected to provide input during the formal design review process to ensure that the design accommodates any specific temporary works or staging requirements. Details of SiD outcomes have been provided in Appendix D. | FSR Excavation FSR Plant and Equipment | Prevents excavator booms from striking the overhead structure (avoiding equipment tipping/damage) while ensuring the trench walls remain stable for workers below. | Verify excavation profile onsite. |  | Matthijs Klinkert
EBTA | EBTA197 | 2025-11-05 | NEL-STH-NSA-5100-CTW-REP-0012 | DESIGN REPORT - E018-5100-0016 - BULLEEN STAGE B3.1A TEMPORARY TRAFFIC SIGNALS | Management |  | SiD (Safety in Design) workshops will be undertaken during the detailed design phase for the different design packages. All SiD risks, proposed mitigation, residual risks and nominated 'owners' of those risks will be identified and captured for all design packages, with registers included in the design report for each package. The temporary works and constructability will be considered through the design process, with input and review from key stakeholders (Eastern BTA, VicRoads Signal Services, VicRoads Region teams) to ensure road safety and constructability constraints are addressed. Outcomes from the SiD and DTP preliminary design review will be documented in the detailed design report if applicable. | FSR Chain of Responsibility | Systematically capturing and mitigating risks through multi-disciplinary reviews ensures that safety hazards are identified early by experts, preventing latent defects in the design. | Document SiD workshop outcomes. |  | Matthijs Klinkert
EBTA | EBTA198 | 2025-11-05 | NEL-STH-NSA-5118-SBR-REP-0001 | EASTERN FREEWAY UPGRADES - BURKE TO TRAM - DESIGN REPORT - B048 - BR104 – BULLEEN ROAD OVER BUSWAY | Design | Implemented | Construction staging implemented to separate works around live traffic with a temporary diversion of traffic at Thompsons Road and Bulleen Road to remove the risk in the area with the bridge deck complete prior to opening to traffic. | FSR Traffic Management FSR Plant and Equipment | Using 3D models allows the team to verify that barriers provide adequate protection and do not obstruct sightlines or clash with plant equipment before physical installation. | Review 3D barrier model. |  | Matthijs Klinkert
EBTA | EBTA199 | 2025-11-05 | NEL-STH-NSA-5118-SBR-REP-0001 | EASTERN FREEWAY UPGRADES - BURKE TO TRAM - DESIGN REPORT - B048 - BR104 – BULLEEN ROAD OVER BUSWAY | Design | Implemented | Top down construction for the bridge deck has been used to reduce the risk of working at height and permanent barriers at live edge will be installed prior to excavation. | FSR Traffic Management | Virtual modelling ensures linemarking is logical, visible, and compliant with standards, reducing driver confusion and the risk of accidents in temporary traffic arrangements. | Review 3D marking model. |  | Matthijs Klinkert
EBTA | EBTA200 | 2025-11-05 | NEL-STH-NSA-5118-SBR-REP-0001 | EASTERN FREEWAY UPGRADES - BURKE TO TRAM - DESIGN REPORT - B048 - BR104 – BULLEEN ROAD OVER BUSWAY | Design | Implemented | Barriers to the cut area of the busway to be cast insitu as part of the pile wall as an upstand to be fall protection and also remove the need for ongoing inspection and maintenance when compared to cladding. | NA | Provides immediate, permanent fall protection at the edge and eliminates the future working-at-heights risk associated with inspecting and maintaining separate cladding systems. | Verify upstand reinforcement. |  | Matthijs Klinkert
EBTA | EBTA201 | 2025-11-05 | NEL-STH-NSA-5300-SRW-REP-0001_6 |  | Design | Complete | Minimise frequency of precast lifting – The team has designed the panel widths of each precast wall type to achieve a maximum of approximately 22t units. This optimises the lifting frequency for precast walls while avoiding employing heavy duty cranes. The goal is to reduce exposure of site personnel hazards of lifting heavy loads and eliminate the risks associated with working with heavy machinery. | FSR Crane and Lifting FSR Plant and Equipment | limiting panel weight ensures standard cranes can be used, avoiding the complexities and ground pressure risks of heavy lift cranes, while reducing the total number of lift operations. | Check lift plan weight allowance. |  | Matthijs Klinkert
EBTA | EBTA202 | 2025-11-05 | NEL-STH-NSA-5300-SRW-REP-0001_6 |  | Design | Complete | Minimise risk of striking critical utilities by omitting piled foundations – Where appropriate, the design team has opted for the shallow foundations of the “L-wall” type or mechanically stabilised earth walls to minimise the risk of striking critical/ hazardous utilities. | FSR Utilities and Services FSR Piling | Eliminating deep piles significantly reduces the risk of striking deep critical or hazardous utilities that may not be accurately mapped | Confirm utility depth on survey. |  | Matthijs Klinkert
EBTA | EBTA203 | 2025-11-05 | NEL-STH-NSA-5300-SRW-REP-0001_6 |  | Design | Complete | Minimise piled foundations – There was a design directive for Type 6 post and panel to adopt 3 m post spacings (originally 2.4 m) to achieve the same outcomes as per BTA-B081-ES02 and reduce working time on-site due to piling. | FSR Piling FSR Plant and Equipment | Increasing the spacing reduces the total number of piles required, directly reducing the duration workers are exposed to piling rigs and open bore hazards. | Verify post spacing on drawings. |  | Matthijs Klinkert
EBTA | EBTA204 | 2025-11-05 | NEL-STH-NSA-5300-SRW-REP-0001_6 |  | Design | Complete | Integration of Noise Walls to minimise piling – To achieve similar outcomes as per BTA-B081-ES02-03 in reduced piling and working time on-site, the design team has prioritised, if appropriate, a design where noise walls are supported on retaining walls. | FSR Piling FSR Plant and Equipment | Reducing the quantity of piling works directly minimizes the time workers are exposed to heavy piling rigs, noise, and vibration hazards. | Verify wall interface design. |  | Matthijs Klinkert
EBTA | EBTA205 | 2025-11-05 | NEL-STH-NSA-5300-SRW-REP-0001_6 |  | Design | Complete | Minimising risk of damaging critical/ hazardous utilities – Where possible, the design team has prioritised orienting the L-walls in “reverse” direction to minimise imposed loads on existing utilities, as for SRW200-Type 3G. | FSR Utilities and Services FSR Excavation | Directing structural loads away from buried assets prevents pipe collapse or rupture, eliminating the risk of gas leaks, water bursts, or service interruption. | Confirm utility location on survey. |  | Matthijs Klinkert
EBTA | EBTA206 | 2025-11-05 | NEL-STH-NSA-5605-SBR-REP-0001 | DESIGN REPORT - B103 – BR604 – KOONUNG CREEK CULVERT PROTECTION EAST OF DONCASTER ROAD | Precast | Adopted | Utilise precast elements (arch, wingwalls, headwalls) in lieu of in-situ to expedite construction time with aim of minimising duration of works in the creek area. Relevant FSRs: Work in, Over or Adjacent to Water, Precast and Tiltup Controls: Engineering Controls | FSR Work On, Over Or Adjacent to Water FSR Precast and Tilt up Concrete | Minimizing the duration of works in the creek significantly reduces the window of exposure to flash flooding events and slippery/unstable ground conditions. | Inspect precast units at yard. |  | Matthijs Klinkert
EBTA | EBTA207 | 2025-11-05 | NEL-STH-NSA-5605-SBR-REP-0001 | DESIGN REPORT - B103 – BR604 – KOONUNG CREEK CULVERT PROTECTION EAST OF DONCASTER ROAD | Design | Adopted | Pre-install handrails to headwalls and wingwalls to act as fall protection for workforce. Relevant FSRs: Working at Heights Controls: Engineering Controls | FSR Working at Heights | Eliminates the "unprotected edge" risk during installation, as the fall protection system arrives already attached to the concrete element. | Verify fixing certification. |  | Matthijs Klinkert
EBTA | EBTA208 | 2025-11-05 | NEL-STH-NSA-5605-SBR-REP-0001 | DESIGN REPORT - B103 – BR604 – KOONUNG CREEK CULVERT PROTECTION EAST OF DONCASTER ROAD | Methodology | Adopted | Adopt iron piles in lieu of bored piles to utilise smaller rigs (excavator). Reducing risk of bearing failure in creek area and utilising more mobile rigs in the instance of an unmanageable flood. Relevant FSRs: Work in, Over or Adjacent to Water, Plant and Equipment, Piling Controls: Engineering Controls | FSR Work On, Over Or Adjacent to Water FSR Plant and Equipment FSR Piling | Smaller, more mobile rigs can be evacuated quickly if creek levels rise, preventing equipment loss and ensuring operator safety during unmanageable floods. | Verify pile capacity in creek bed. |  | Matthijs Klinkert
EBTA | EBTA209 | 2025-11-05 | NEL-STH-NSA-5605-SBR-REP-0001 | DESIGN REPORT - B103 – BR604 – KOONUNG CREEK CULVERT PROTECTION EAST OF DONCASTER ROAD | Design | Adopted | All works inside the BEBO has been precluded from the design. All proposed works for design package is above the BEBO, thus no construction activity is required in confined space. Relevant FSRs: Confined Space Controls: Elimination | FSR Confined Space | Completely eliminating work inside the BEBO structure removes the need for confined space entry, thereby eliminating all associated atmospheric and entrapment risks. | Confirm design clearance above BEBO. |  | Matthijs Klinkert
EBTA | EBTA210 | 2025-11-05 | NEL-STH-NSA-5605-SBR-REP-0001 | DESIGN REPORT - B103 – BR604 – KOONUNG CREEK CULVERT PROTECTION EAST OF DONCASTER ROAD | Design | Ongoing | Minimise work over the existing BEBO structure to reduce risk of damaging existing infrastructure by substantiating the removal of the protection slab over the existing freeway previously detailed, via thorough and detailed analysis. Relevant FSRs: N/A | NA | Avoiding the construction of a heavy protection slab reduces the load and vibration imposed on the existing fragile infrastructure, preventing potential collapse. | Archive structural analysis report. |  | Matthijs Klinkert
EBTA | EBTA211 | 2025-11-05 | NEL-STH-NSA-5605-SBR-REP-0001 | DESIGN REPORT - B103 – BR604 – KOONUNG CREEK CULVERT PROTECTION EAST OF DONCASTER ROAD | Design | Ongoing | Reinforcement design for slab to be detailed with consideration of utilising Bamtec reinforcement to increase productivity and to minimise the need for heavy manual on-site labour for placing and tying reinforcement. Relevant FSRs: N/A Controls: Engineering Controls | NA | Bamtec eliminates the need for individual bar tying, significantly reducing the heavy manual handling and repetitive strain injuries associated with traditional steel fixing | Approve Bamtec detailing. |  | Matthijs Klinkert
EBTA | EBTA212 | 2025-11-05 | NEL-STH-NSA-5290-CTW-REP-0001 | DESIGN REPORT - B198 – FWY MEDIAN TEMPORARY WORKS – BURKE RD | Design | Implemented | Adopt build up pavement overlay procedures to limit work within the freeway carriageway (minimize deep asphalt solutions where possible). | FSR Traffic Management FSR Plant and Equipment | Minimizing deep excavation in the carriageway reduces the duration of high-risk work adjacent to live traffic. | Verify pavement design profiles. |  | Matthijs Klinkert
EBTA | EBTA213 | 2025-11-05 | B215 - NEL-STH-NSA-5900-CUM-REP-0001 |  | Design | Implemented | Digital Engineering – coordinated and fully federated model used to develop utility alignments and prevent clashes. | FSR Utilities and Services FSR Excavation | Virtual clash detection identifies conflicts before construction, preventing dangerous utility strikes and unplanned rework. | Update federated model. |  | Matthijs Klinkert
EBTA | EBTA214 | 2025-11-05 | B215 - NEL-STH-NSA-5900-CUM-REP-0001 |  | Design | Implemented | Minimised excavation extent and depth in former landfill sites. Known areas of contamination and ACM (Asbestos Containing Materials). • horizontal alignments coordinated within combined (water & sewer) trench. • vertical alignment coordinated at minimum depth. | FSR Excavation FSR Asbestos | Reducing excavation volume directly reduces worker exposure to hazardous contaminated soil and airborne asbestos fibers. | Review contamination management plan. |  | Matthijs Klinkert
EBTA | EBTA215 | 2025-11-05 | B215 - NEL-STH-NSA-5900-CUM-REP-0001 |  | Design | Implemented | Risk of trench collapse in variable (uncontrolled fill) ground conditions minimised by vertical alignment coordination at minimum depth (900mm cover) | FSR Excavation | Shallow excavations significantly reduce the risk of trench wall collapse and engulfment compared to deep trenches in unstable ground. | Verify trench depth onsite. |  | Matthijs Klinkert
EBTA | EBTA216 | 2025-11-05 | NEL-STH-NSA-5900-CRW-REP-0003 | DESIGN REPORT - B108 - CIVIL TYPICAL DETAILS | Design | Applied | Barrier interface with existing pavements have been designed to minimise the amount of saw cut and layers to be reinstated. The material choice also avoids concrete layers that would require curing time, which would increase the time where temporary traffic management and works adjacent to live traffic areas would be required. | FSR Traffic Management | Eliminating curing times reduces the duration of temporary traffic management, lowering the window of exposure to live traffic risks. | Audit barrier installation. |  | Matthijs Klinkert
EBTA | EBTA217 | 2025-11-05 | NEL-STH-NSA-5900-CRW-REP-0003 | DESIGN REPORT - B108 - CIVIL TYPICAL DETAILS | Design | Applied | Pit abandonment detail has been capped to subgrade with a layer that doesn't require compaction, again to try to minimise the amount of works that need to be undertaken in live traffic. | FSR Traffic Management FSR Plant and Equipment | Eliminating the compaction requirement reduces the time workers and plant need to spend in high-risk zones adjacent to live traffic. | Verify cap material spec. |  | Matthijs Klinkert
EBTA | EBTA218 | 2025-11-05 | NEL-STH-NSA-5900-CRW-REP-0003 | DESIGN REPORT - B108 - CIVIL TYPICAL DETAILS | Design | Applied | Overall, package offers flexibility in solutions so that alternative details can be used if unexpected conditions are found, which allows rapid reaction and therefore also supports construction progression, minimising risky reactive positions. | FSR Excavation FSR Chain of Responsibility | Allows for rapid, engineered reactions to site surprises, preventing "risky reactive positions" where ad-hoc decisions often lead to accidents or unsafe rework. | Archive alternative details. |  | Matthijs Klinkert
EBTA | EBTA219 | 2025-11-05 | NEL-STH-NSA-5100-CUM-REP-0001 | Design Report - B060 - COMBINED UTILITIES - BULLEEN INTERCHANGE - ZONE 5100 | Design | Implemented | Digital engineering tools (iTwin) have been used to avoid clashes with other design elements, avoiding the potential need for change during construction. | FSR Plant and Equipment FSR Excavation | Identifying clashes virtually prevents dangerous "clash on site" scenarios that often force unplanned, high-risk rework or demolition activities. | Generate clash report. |  | Matthijs Klinkert
EBTA | EBTA220 | 2025-11-05 | NEL-STH-NSA-5100-CUM-REP-0001 | Design Report - B060 - COMBINED UTILITIES - BULLEEN INTERCHANGE - ZONE 5100 | Design | Implemented | Permanent utility relocations to maintain clearances to existing services, proposed services and new road assets (including retaining walls, noise walls, etc) to maintain clearances in accordance with DTP and utility asset owners’ guidelines | FSR Utilities and Services FSR Excavation | Adhering to DTP and asset owner guidelines for clearance ensures a safe buffer zone, preventing accidental strikes on live assets during construction and future maintenance. | Verify clearance on as-builts. |  | Matthijs Klinkert
EBTA | EBTA221 | 2025-11-05 | NEL-STH-NSA-5100-CUM-REP-0001 | Design Report - B060 - COMBINED UTILITIES - BULLEEN INTERCHANGE - ZONE 5100 | Design | Implemented | Descoping of Gas relocation works. Investigation and design undertaken to avoid the need to relocate gas main G039 and G049. | FSR Utilities and Services FSR Excavation | Completely eliminates the risks associated with excavating around and handling live high-pressure gas mains, removing the potential for catastrophic leaks or explosions. | Update utility model. |  | Matthijs Klinkert
EBTA | EBTA222 | 2025-11-05 | NEL-STH-NSA-5500-CTW-REP-0005 | Design Report – E018N-5500-0005 – DONCASTER STAGE D1.1B – TEMPORARY TRAFFIC SIGNALS | Management |  | There is no table with the columns 'Number', 'Item', 'Status', and 'Design Stage' on the provided pages. However, there is an Engineered Safety (Safety in Design) section. Key points are: - SiD workshops will be undertaken for the civil 2D alignment throughout the detailed design phase for the different design packages. - All SiD risks, proposed mitigation, residual risks, and nominated 'owners' of those risks will be identified and captured for all design packages with registers included in the design report for each individual package. - Temporary works and constructability will be considered throughout the design preparation, with formal and informal meetings during the review process. - Major constructability constraints are to be communicated as early as possible. - VicRoads Signal Services and VicRoads Region teams review the design from a Road Safety Perspective. - Outcomes from SiD and DTP preliminary design review will be documented in the detailed design report. | FSR Chain of Responsibility | Early engagement with subject matter experts ensures road safety and constructability constraints are addressed before construction begins, preventing latent defects. | Document SiD outcomes. |  | Matthijs Klinkert
EBTA | EBTA223 | 2025-11-05 | NEL-STH-NSA-5100-CTW-REP-0008 | Design Report - B191 - Temporary SUP Package 1 (Thompsons to Bulleen) | Design | Complete | The design basis for the temporary SUPs is to use as much of the permanent SUP alignment and construction specification as possible so that there is an opportunity that the temporary works can be left in place and adopted as the permanent works. Hence eliminating the need to 'build twice'. | FSR Traffic Management FSR Plant and Equipment | Eliminating the need to "build twice" significantly reduces the total duration of construction plant operating in public reserves, lowering the risk of plant-pedestrian interaction. | Verify SUP grades. |  | Matthijs Klinkert
EBTA | EBTA224 | 2025-11-05 | NEL-STH-NSA-5100-CTW-REP-0008 | Design Report - B191 - Temporary SUP Package 1 (Thompsons to Bulleen) | Design | Complete | User safety – signs and lines to assist way-finding. Desirable grades with clearance to obstacles selected | FSR Traffic Management | Clear delineation and compliant grades prevent user confusion and collisions between cyclists and pedestrians, or collisions with fixed obstacles. | Audit signage plan. |  | Matthijs Klinkert
EBTA | EBTA225 | 2025-11-05 | NEL-STH-NSA-5100-CTW-REP-0008 | Design Report - B191 - Temporary SUP Package 1 (Thompsons to Bulleen) | Design | Complete | Utility avoidance – 3D utilities model used in coordination with SUP design model to avoid risk of clashes and associated FSR’s | FSR Utilities and Services FSR Excavation | Virtual clash detection identifies conflicts before breaking ground, preventing dangerous utility strikes that could lead to electrocution, gas leaks, or service outages. | Update federated model. |  | Matthijs Klinkert
EBTA | EBTA226 | 2025-11-05 | NEL-STH-NSA-5100-CDR-REP-0001 | DESIGN REPORT - B059 5100 DRAINAGE BULLEEN ROAD INTERCHANGE | Methodology | Implemented | Construction staging has been investigated and will be implemented by the Worksite Traffic Management Plan to delineate and minimize the duration/extent of high-risk activities working near live traffic with proposed temporary barrier works and associated signage. | FSR Traffic Management | Physical separation via barriers and reduced exposure time significantly lowers the statistical likelihood of vehicle-worker collisions. | Audit barrier installation. |  | Matthijs Klinkert
EBTA | EBTA227 | 2025-11-05 | NEL-STH-NSA-5100-CDR-REP-0001 | DESIGN REPORT - B059 5100 DRAINAGE BULLEEN ROAD INTERCHANGE | Design | Implemented | Spill containment tanks optimised and removed from the SPARK reference design by integrating with other drainage elements. This has avoided deep excavation for installation of tanks and ongoing maintenance requirements. | FSR Excavation FSR Confined Space | Removing deep tanks eliminates the need for deep excavations (collapse risk) and future confined space entries required for tank maintenance/cleaning. | Verify drainage integration. |  | Matthijs Klinkert
EBTA | EBTA228 | 2025-11-05 | NEL-STH-NSA-5900-CRF-REP-0001_IFC |  | Design | Completed | The detailed design has identified total number of access rings within each ring to comply the requirement that there shall be no more than ten (10) access switches within each access ring | FSR Utilities and Services | Ensuring network redundancy and limiting failure domains prevents widespread communication blackouts during emergency situations or maintenance. | Confirm switch count. |  | Matthijs Klinkert
EBTA | EBTA229 | 2025-11-05 | NEL-STH-NSA-5900-CRF-REP-0001_IFC |  | Management | Completed | All equipment, patch panels, outlets, cabinets, and racks shall be clearly labelled in accordance with the approved label list. A list to be produced and submit in IFC documentation. RAI addressing to be provided by DTP. | FSR Plant and Equipment FSR Utilities and Services | Clear, standardized labeling prevents isolation errors during maintenance, ensuring workers do not accidentally interact with live or incorrect equipment. | Submit label list for IFC. |  | Matthijs Klinkert
EBTA | EBTA230 | 2025-11-05 | NEL-STH-NSA-5900-CRF-REP-0001_IFC |  | Design | Completed | Cable lengths to be rationalised to reduce need of large cable drums sizes and minimize heavy handling / cranage risk. | FSR Crane and Lifting FSR Plant and Equipment | Reducing the size and weight of cable drums allows for the use of smaller lifting equipment and reduces the severity of potential crush injuries during handling. | Verify cable schedule. |  | Matthijs Klinkert
EBTA | EBTA231 | 2025-11-05 | NEL-STH-NSA-5900-CRF-REP-0001_IFC |  | Methodology | Completed | The use of winches to pull cable safely from cable drum. To avoid manual handling risks during construction. Draw string to be installed with blower to ease of fibre cable pulling. | FSR Plant and Equipment | Replacing strenuous manual pulling with mechanical winches and blowers directly prevents musculoskeletal injuries and repetitive strain. | Approve winch SWMS. |  | Matthijs Klinkert
EBTA | EBTA232 | 2025-11-05 | NEL-STH-NSA-5900-CRF-REP-0001_IFC |  | Design | Completed | A marker tape with trace wire shall be placed above all conduits in accordance with the Wiring Rules. Enabling asset location and avoidance of impact during excavation. | FSR Utilities and Services FSR Excavation | Allows future crews to electronically locate non-conductive conduits before digging, preventing accidental utility strikes and service interruptions. | Inspect trench before backfill. |  | Matthijs Klinkert
EBTA | EBTA233 | 2025-11-05 | NEL-STH-NSA-5120-SBR-REP-0001 | DESIGN REPORT - B053 – BR109 – WB EF TO NB NEL OVERHEAD STRUCTURE(RAMP U6) | Methodology | Implemented | Construction staging has been investigated and will be implemented by the Worksite Traffic Management Plan to delineate and minimize the duration/extent of high-risk activities working near live traffic with proposed temporary barrier works and associated signage. | FSR Traffic Management | Physical separation via barriers and reduced exposure time significantly lowers the statistical likelihood of vehicle-worker collisions. | Audit barrier installation. |  | Matthijs Klinkert
EBTA | EBTA234 | 2025-11-05 | NEL-STH-NSA-5120-SBR-REP-0001 | DESIGN REPORT - B053 – BR109 – WB EF TO NB NEL OVERHEAD STRUCTURE(RAMP U6) | Methodology | Implemented | Construction staging implemented to separate works around live traffic with a temporary diversion of traffic at Thompsons Road and Bulleen Road to remove the risk in the area with the bridge deck complete prior to opening to traffic and deliver works north of Thompsons when traffic is switched back to the permanent Bulleen Road Bridge. | FSR Traffic Management | Completing the bridge deck offline eliminates the high-risk interface of heavy construction occurring overhead of live traffic, removing dropped object risks for the public. | Verify diversion setup. |  | Matthijs Klinkert
EBTA | EBTA235 | 2025-11-05 | NEL-STH-NSA-5120-SBR-REP-0001 | DESIGN REPORT - B053 – BR109 – WB EF TO NB NEL OVERHEAD STRUCTURE(RAMP U6) | Methodology | Implemented | Precast Driven Piles adopted over bored piles where possible to remove open hole and remove the need to dispose of pile spoil material. | FSR Excavation FSR Piling | Eliminates the hazard of "open holes" (deep excavations) which pose fall risks to personnel and collapse risks to adjacent plant. | Confirm pile driveability. |  | Matthijs Klinkert
EBTA | EBTA236 | 2025-11-05 | NEL-STH-NSA-5120-SBR-REP-0001 | DESIGN REPORT - B053 – BR109 – WB EF TO NB NEL OVERHEAD STRUCTURE(RAMP U6) | Modularisation | Implemented | Steel reinforcement to pile cap bottom mat, pier column and crosshead will be modelled and prefabricated to drop, reducing on site steel reinforcement fabrication to the top mat / sides of the pile cap to tie in the prefabricated sections. | FSR Formwork & Falsework FSR Working at Heights | Significantly reduces the manual handling and repetitive strain injuries associated with tying steel in-situ, often in awkward positions or at height. | Verify cage lifting points. |  | Matthijs Klinkert
EBTA | EBTA237 | 2025-11-05 | NEL-STH-NSA-5120-SBR-REP-0001 | DESIGN REPORT - B053 – BR109 – WB EF TO NB NEL OVERHEAD STRUCTURE(RAMP U6) | Methodology | Implemented | Self-Propelled Modular Transport (SPMT) construction method adopted for spans over the eastbound carriageway to enable spans to be assembled offline and deliver in single section to reduce working around live traffic, multiple carriageway closures and working at heights. | FSR Traffic Management FSR Working at Heights FSR Plant and Equipment | Assembling spans "offline" drastically reduces the time workers spend working at heights over live traffic and minimizes the need for high-risk carriageway closures. | Approve SPMT lift plan. |  | Matthijs Klinkert
EBTA | EBTA238 | 2025-11-05 | NEL-STH-NSA-5119-SBR-REP-0003 | DESIGN REPORT - B193 - BR103 PIER 8 PACKAGE | [7 empty] | Matthijs Klinkert
EBTA | EBTA239 | 2025-11-05 | NEL-STH-NSA-5500-CTW-REP-0006 | Design Report – E018O-5500-0008 – DONCASTER STAGE D1.1C-2 – TEMPORARY TRAFFIC SIGNALS | Management |  | Section 9, 'Safety in Design', outlines that SiD (Safety in Design) workshops are performed for civil 2D alignment during detailed design phases. All SiD risks, proposed mitigation measures, residual risks, and nominated 'owners' are identified and recorded in design reports. Methodology includes assessing temporary works and constructability constraints and reviewing the design by subject matter experts from VicRoads. Outcomes of these SiD and DTP preliminary design reviews will be documented in the detailed design report. However, there is no specific table with columns 'Number', 'Item', 'Status', and 'Design Stage' visible in the provided images. | FSR Chain of Responsibility | A structured, multi-disciplinary review process ensures safety hazards are identified and engineered out early by experts, preventing latent defects from reaching construction. | Document SiD outcomes. |  | Matthijs Klinkert
EBTA | EBTA240 | 2025-11-05 | NEL-STH-NSA-5509-SBR-REP-0001 | Design Report - B094 - BR501 – Doncaster Road Bridge | Methodology | Implemented | Construction staging implemented to separate works around live traffic with a temporary diversion of traffic along Doncaster Road to remove the risk in the area with the bridge deck complete prior to opening to traffic. Relevant FSRs: Traffic Management Controls: Elimination | FSR Traffic Management | Removing the risk in the area by completing the bridge deck prior to opening to traffic eliminates the high-risk interface between the public and overhead construction. | Verify diversion setup. |  | Matthijs Klinkert
EBTA | EBTA241 | 2025-11-05 | NEL-STH-NSA-5509-SBR-REP-0001 | Design Report - B094 - BR501 – Doncaster Road Bridge | Methodology | Implemented | Precast concrete girders and precast floor panels are used together with edge barriers installed prior to deck construction to reduce the risk of working from height. Relevant FSRs: Working at Heights, Cranes and Lifting. Controls: Engineering controls, Elimination | FSR Working at Heights FSR Cranes and Lifting | Installing edge barriers early (before the deck is fully constructed) provides immediate edge protection for workers, while precast elements reduce the time spent forming decks at height. | Inspect barrier installation. |  | Matthijs Klinkert
EBTA | EBTA242 | 2025-11-05 | NEL-STH-NSA-5509-SBR-REP-0001 | Design Report - B094 - BR501 – Doncaster Road Bridge | Design | Implemented | Bridge configuration has been changed from maximum of 4 spans to 2 spans since RFP-F Central package to current design. This reduces the complexity, and the manhour required to complete the bridge construction. Relevant FSRs: Working at Heights, Cranes and Lifting. Controls: Elimination | FSR Working at Heights FSR Cranes and Lifting | Reducing the number of spans directly reduces the number of heavy lifts required and the total manhours workers spend exposed to height and lifting hazards. | Verify span setout. |  | Matthijs Klinkert
EBTA | EBTA243 | 2025-11-05 | NEL-STH-NSA-5509-SBR-REP-0001 | Design Report - B094 - BR501 – Doncaster Road Bridge | Methodology | Implemented | Deck pouring and construction sequence revised to provide overall stability of the girders especially for the steel trough and I girders, which also reduce the loads on the temporary props during construction. Relevant FSRs: Working at Heights Controls: Engineering controls, Elimination | FSR Working at Heights | Ensuring girder stability during the pour prevents structural shifting or collapse, creating a safer working platform and reducing the reliance on temporary propping. | Approve pour sequence. |  | Matthijs Klinkert
EBTA | EBTA244 | 2025-11-05 | NEL-STH-NSA-5500-CTW-REP-0010 | DESIGN REPORT - DONCASTER STAGE D1.1C-1 – TEMPORARY TRAFFIC SIGNALS | Management |  | There is no table with the columns 'Number', 'Item', 'Status', and 'Design Stage' present in the provided images. However, there is an 'Engineered Safety' section under 'Safety in Design' (SiD): SiD workshops will be undertaken for the civil 2D alignment throughout the detailed design phase for the different design packages. All SiD risks, proposed mitigation, residual risks and nominated ‘owners’ of those risks will be identified and captured for all design packages with registers included in the design report for each individual design package showing risks relating to the design package in accordance with Eastern BTA Design Management Plan. Temporary works and constructability will be considered throughout the design process. Major constructability constraints will be communicated early for consideration. Eastern BTA will provide input during the formal design review to ensure that design accommodates any specific temporary works or staging requirements. The preliminary design is also reviewed by VicRoads Signal Services as Subject Matter Experts and VicRoads Region teams from a Road Safety Perspective. Outcomes from SiD and DTP preliminary design review will be documented in the detailed design report if applicable. | FSR Chain of Responsibility | Early identification of constructability constraints and safety risks by key stakeholders (VicRoads, Eastern BTA) prevents latent defects from reaching the construction phase. | Document SiD outcomes. |  | Matthijs Klinkert
EBTA | EBTA245 | 2025-11-05 | NEL-STH-NSA-5299-SSG-REP-0001 | Design Report - B070 - 5100 / 5200 - Signage and ITS Gantries | Design | Completed | Optimization in the number of gantries - Where possible and compliant the number of gantries is optimised. Where possible ITS (Intelligent Transport Systems) signs LUMS has proposed to be mounted on the bridge structure instead of independent structure to minimize the construction and maintenance effort. e.g, LUMS on BS106 | FSR Working at Heights FSR Traffic Management | Eliminating independent gantry structures reduces the need for separate foundations (excavation) and reduces future maintenance work over live traffic. | Verify structural mount details. |  | Matthijs Klinkert
EBTA | EBTA246 | 2025-11-05 | NEL-STH-NSA-5299-SSG-REP-0001 | Design Report - B070 - 5100 / 5200 - Signage and ITS Gantries | Methodology | Completed | Limit the maximum gantry member length to 40m for transportation. This will allow greater control over transportation logistics and programming deliveries away from peak traffic periods and minimize exposure to traffic-related hazards. | FSR Traffic Management FSR Plant and Equipment | Avoiding peak traffic for oversized deliveries significantly reduces the likelihood of heavy haulage interacting with the public, preventing potential road accidents. | Approve logistics plan. |  | Matthijs Klinkert
EBTA | EBTA247 | 2025-11-05 | NEL-STH-NSA-5299-SSG-REP-0001 | Design Report - B070 - 5100 / 5200 - Signage and ITS Gantries | Design | Completed | Power arrangement and functional and protective earthing arrangement at the gantry structure has been reviewed by Certified Electrical engineers at shared ITS Asset devices at shared gantry. Conduit details within gantry have been provided in DD stage. Earthing assessment of the Gantries was done in the DD design stage. | FSR Utilities and Services FSR Plant and Equipment | Certified review and proper earthing design prevents electrical faults and shock hazards for maintenance personnel working on shared ITS assets. | Archive earthing assessment. |  | Matthijs Klinkert
EBTA | EBTA248 | 2025-11-05 | NEL-STH-NSA-5299-SSG-REP-0001 | Design Report - B070 - 5100 / 5200 - Signage and ITS Gantries | Methodology | Completed | Prewiring of gantry and attaching CCTV poles assembly before installation off-site under a controlled environment. This will eliminate risks associated with working; in challenging terrain, at heights/near free edges, in extreme weather and in proximity to live traffic for this task. LUMS signs will be installed on the ground before lifting. CCTV and VMS (Variable message sign) can be installed after. Gantry leg boxes can be installed before or after gantry lift. General Construction methodology has been added in design report section 6.6.1A | FSR Working at Heights FSR Traffic Management | Shifting complex assembly tasks from the gantry (at height over traffic) to the ground eliminates fall risks and reduces workers' exposure to weather and live traffic. | Inspect pre-assembly QA. |  | Matthijs Klinkert
EBTA | EBTA249 | 2025-11-05 | NEL-STH-NSA-5299-SSG-REP-0001 | Design Report - B070 - 5100 / 5200 - Signage and ITS Gantries | Methodology | Completed | The girder splices will be completed on-ground and then lifted by crane to connect to the gantry’s columns. Construction recommended splices to be bolted not welded at site. The location of splices and lifting lugs are designed at DD stage with consideration for equal weight distribution and lift safety. Construction methodology has been updated in this report. Lifting schedule has been added in drawing NEL-STH-NSA-5299-SSG-DRG-0552 with details of weight of segment and lifting lug type etc. | FSR Cranes and Lifting FSR Working at Heights | Bolting on the ground eliminates the fire/fume risks of onsite welding and removes the need for workers to perform lengthy connection tasks while suspended at height. | Verify lifting lug certification. |  | Matthijs Klinkert
EBTA | EBTA250 | 2025-11-05 | NEL-STH-NSA-5299-SSG-REP-0001 | Design Report - B070 - 5100 / 5200 - Signage and ITS Gantries | Modularisation | Completed | Steel work shall be prefabricated and delivered to site. Prechamber shall be provided from the fabrication yard. Welding, painting, and ITS cabling/wiring shall be ready before delivered to site. Construction sequence updated in design report. | FSR Hot Works FSR Working at Heights | Performing welding and cabling offsite eliminates fire/fume risks on site and reduces the need for workers to perform complex wiring tasks at height or in live traffic corridors. | Verify fabrication QA. |  | Matthijs Klinkert
EBTA | EBTA251 | 2025-11-05 | NEL-STH-NSA-5900-STG-REP-0001 | DESIGN REPORT - B040 – DESIGN BASIS REPORT – PROJECT WIDE STRUCTURES | Management |  | Constructability and Safety in Design workshops have taken place for the project including all civil structures and bridge design packages at different stages of design. All Safety in Design risks, proposed mitigation, residual risks and nominated ‘owners’ of those risks will be identified and captured for all design packages with registers included in the design report for each individual structure design package in accordance with NELSA Design Management Plan. This register is continually updated during the design phase and complemented through a number of design reviews. Refer to individual structure package design report for the extracts from the register as applied to respective design packages. | FSR Chain of Responsibility | Ensuring risks are captured and assigned to "owners" during the design phase prevents undefined hazards from surprising the construction team. | Document SiD outcomes. |  | Matthijs Klinkert
EBTA | EBTA252 | 2025-11-05 | NEL-STH-NSA-5300-CDR-REP-0001 | Design Report - B078 - Zone 5300 Mainline Drainage (Complex) | Design | Adopted | Spill Containment Tank lifted to match temp ramp level. Depth to spill containment tank reduced significantly. Reduced risk of high risk temp works (reduced retained depth to construct the tank), improved maintenance access. Relevant FSRs: Excavation Controls: Engineering Controls | FSR Excavation | Reducing the depth of the tank installation directly reduces the risk of trench collapse and improves safe access for future maintenance. | Verify tank levels. |  | Matthijs Klinkert
EBTA | EBTA253 | 2025-11-05 | NEL-STH-NSA-5300-CDR-REP-0001 | Design Report - B078 - Zone 5300 Mainline Drainage (Complex) | Design | Adopted | Minimise works in high risk areas including creeks. Works limited to drainage outlet to spill containment north of BR604. Therefore, minimise requirement for temporary works associated adjacent creek, and limit need for emergency plans to the BR604 area. Relevant FSRs: Work in, over or adjacent to water Controls: Eliminate (other than BR604 area) | FSR Work On, Over Or Adjacent to Water | Minimizing the footprint and duration of works in the creek reduces the workforce's exposure to flash flooding and unstable riverbank conditions. | Approve SWMS for creek works. |  | Matthijs Klinkert
EBTA | EBTA254 | 2025-11-05 | NEL-STH-NSA-5300-CDR-REP-0001 | Design Report - B078 - Zone 5300 Mainline Drainage (Complex) | Design | Adopted | Drainage assets elevated as close to surface as possible to minimise deep excavation, thus minimising the risk of undermining the existing running freeway during construction activity, and minimising the risk of falling from heights. Relevant FSRs: Excavation, Working at Heights Controls: Engineering Controls | FSR Excavation FSR Working at Heights | Avoiding deep excavations near the freeway prevents the undermining of live traffic lanes and reduces the risk of falls into deep trenches. | Confirm drainage invert levels. |  | Matthijs Klinkert
EBTA | EBTA255 | 2025-11-05 | NEL-STH-NSA-5300-CDR-REP-0001 | Design Report - B078 - Zone 5300 Mainline Drainage (Complex) | Methodology | Adopted | Deep 1200 dia pipe crossing the freeway near Estelle St is intended to be underbored to avoid the need for deep excavations and works adjacent freeway. This isolation allows works to proceed critical works in a safe and controlled manner away from live traffic. Necessary freeway settlement analysis for the underbore will be undertaken as part of a temporary works activity for this underbore. Relevant FSRs: Excavation, Traffic Management Controls: Engineering Controls | FSR Excavation FSR Traffic Management | Isolating works via underboring allows critical tasks to proceed away from live traffic, avoiding the risks of deep open-cut excavation near active lanes. | Review settlement analysis. |  | Matthijs Klinkert
EBTA | EBTA256 | 2025-11-05 | NEL-STH-NSA-5300-CDR-REP-0001 | Design Report - B078 - Zone 5300 Mainline Drainage (Complex) | Design | Adopted | Majority of drainage works are within the freeway footprint, thus excavation near existing ground levels. This provides a level working surface for excavators, minimising works adjacent steep slopes. Works designed to align with the project’s temp traffic staging plans, thereby ensuring all works occur with safe protection from running road traffic. Relevant FSRs: Excavation, Traffic Management Controls: Isolation, Engineering Controls | FSR Excavation FSR Traffic Management | Provides a stable, level platform for excavators (minimising tipping risk on steep slopes) and ensures all works occur behind established traffic protection. | Verify surface levels. |  | Matthijs Klinkert
EBTA | EBTA257 | 2025-11-05 | NEL-STH-NSA-5300-CDR-REP-0001 | Design Report - B078 - Zone 5300 Mainline Drainage (Complex) | Design | Adopted | Introduction of staggered pipe crossings across lanes to accommodate traffic staging as well as to reduce number of deep drainage pits just west of Doncaster interchange. Solution resulted in being able to maximise work behind barrier protection detailed in the temporary traffic staging plan, plus reduced risk of deep(er) excavation requirements which reduces risk of shoring criteria and thus ground collapse (especially adjacent existing BEBO). Furthermore, shallower excavations provide a reduced chance of exposing unexpected obstructions being nearby a landfill area. Relevant FSRs: Excavation, Traffic Management Controls: Isolation, Engineering Controls | FSR Excavation FSR Traffic Management | Reducing the depth of pits lowers shoring requirements and ground collapse risks (especially near the existing BEBO) while keeping crews behind barrier protection. | Check staging plan alignment. |  | Matthijs Klinkert
EBTA | EBTA258 | 2025-11-05 | NEL-STH-NSA-5300-CDR-REP-0001 | Design Report - B078 - Zone 5300 Mainline Drainage (Complex) | Material | Adopted | Maximise use of flexible pipe to reduce the material mass for transport and manual handling. Relevant FSRs: Cranes and Lifting Controls: Substitution | FSR Cranes and Lifting | Lighter flexible pipes significantly reduce the physical strain on workers during transport and installation compared to rigid, heavy concrete pipes. | Approve pipe material submittal. |  | Matthijs Klinkert
EBTA | EBTA259 | 2025-11-05 | NEL-STH-NSA-5300-CDR-REP-0001 | Design Report - B078 - Zone 5300 Mainline Drainage (Complex) | Methodology | To be explored during construction phase. | Minimising need to remove redundant drainage assets (especially deep assets) and instead propose grout filling. This will minimise the need for deep excavations, need for cranage adjacent deep excavation to remove exiting drainage, as well as potential exposure to hazardous materials (ie. asbestos). Ongoing – to be discussed with relevant stakeholders/asset owners. Relevant FSRs: Excavation, Cranes and Lifting, Asbestos Controls: Substitution | FSR Excavation FSR Cranes and Lifting FSR Asbestos | Avoids the need for deep excavation and cranage to remove old pipes, significantly reducing the risk of disturbing hazardous materials like asbestos. | Confirm asset owner agreement. |  | Matthijs Klinkert
EBTA | EBTA260 | 2025-11-05 | NEL-STH-NSA-5111-SBR-REP-0001 | EASTERN FREEWAY – BURKE TO TRAM ALLIANCE - Design Report B045 - BR101 - Bulleen Rd Over EF EB Ramp to NEL NB (incl Bulleen Rd N & SB Elevated Structures) | Methodology | Implemented | Construction staging implemented to separate works around live traffic with a temporary diversion of traffic at Thompsons Road and Bulleen Road to remove the risk in the area with the bridge deck complete prior to opening to traffic. | FSR Traffic Management | Completing the bridge deck offline eliminates the high-risk interface of heavy construction occurring overhead of live traffic, removing dropped object risks for the public. | Verify diversion setup. |  | Matthijs Klinkert
EBTA | EBTA261 | 2025-11-05 | NEL-STH-NSA-5111-SBR-REP-0001 | EASTERN FREEWAY – BURKE TO TRAM ALLIANCE - Design Report B045 - BR101 - Bulleen Rd Over EF EB Ramp to NEL NB (incl Bulleen Rd N & SB Elevated Structures) | Methodology | Implemented | Construction staging has been investigated and will be implemented by the Worksite Traffic Management Plan to delineate and minimize the duration/extent of high-risk activities working near live traffic with proposed temporary barrier works and associated signage. | FSR Traffic Management | Physical separation via barriers and reduced exposure time significantly lowers the statistical likelihood of vehicle-worker collisions. | Audit barrier installation. |  | Matthijs Klinkert
EBTA | EBTA262 | 2025-11-05 | NEL-STH-NSA-5111-SBR-REP-0001 | EASTERN FREEWAY – BURKE TO TRAM ALLIANCE - Design Report B045 - BR101 - Bulleen Rd Over EF EB Ramp to NEL NB (incl Bulleen Rd N & SB Elevated Structures) | Design | Implemented | Precast concrete piers and crossheads updated to in-situ concrete removing transport, lifting and handling of precast concrete elements | FSR Cranes and Lifting FSR Plant and Equipment | shifting to in-situ construction removes the need for high-risk heavy lifts of massive precast elements and the associated transport logistics through public roads. | Verify formwork design. |  | Matthijs Klinkert
EBTA | EBTA263 | 2025-11-05 | NEL-STH-NSA-5111-SBR-REP-0001 | EASTERN FREEWAY – BURKE TO TRAM ALLIANCE - Design Report B045 - BR101 - Bulleen Rd Over EF EB Ramp to NEL NB (incl Bulleen Rd N & SB Elevated Structures) | Design | Implemented | SPARK Central Preliminary Design updated from fabricated steel super structure to precast concrete super structure reducing structure whole of life maintenance activities. | FSR Working at Heights FSR Traffic Management | Concrete requires significantly less maintenance (e.g., painting) than steel, reducing future requirements for lane closures and working at heights over live traffic. | Archive maintenance plan. |  | Matthijs Klinkert
EBTA | EBTA264 | 2025-11-05 | NEL-STH-NSA-5100-CTW-REP-0007 | Design Report – E018B-5100-0005 – BULLEEN STAGE B2.0 / B2.0c / B2.0c TEMPORARY TRAFFIC SIGNALS | Management |  | There is no table with columns 'Number', 'Item', 'Status', and 'Design Stage' present. However, the 'Safety in Design' section outlines the SiD context, methodology, and outcomes. SiD workshops will identify and capture all risks, proposed mitigation, residual risks and nominated ‘owners’ for design packages. Registers will be included in design reports. The methodology involves considering temporary works and constructability, ensuring constraints are identified and incorporated through review processes involving VicRoads and other stakeholders. Outcomes from SiD and DTP preliminary design review will be documented in the detailed design report. | FSR Chain of Responsibility | Ensuring risks are captured and assigned to "owners" during the design phase prevents undefined hazards from surprising the construction team. | Document SiD outcomes. |  | Matthijs Klinkert
EBTA | EBTA265 | 2025-11-05 | NEL-STH-NSA-5100-CTW-REP-0011 | DESIGN REPORT - E108-5100-0013 - BULLEEN STAGE B3.0 TEMPORARY TRAFFIC SIGNALS | Management |  | Section 9, 'Safety in Design', serves as the Engineered Safety section. It outlines that Safety in Design (SiD) workshops are undertaken throughout the detailed design phase to identify risks, mitigations, and residual risks, with formal and informal reviews to ensure temporary works and constructability are addressed. The approach includes consultation with stakeholders and subject matter experts to cover road safety and constructability in the design review process. Outcomes of the SiD process are documented in the detailed design report if applicable. | FSR Chain of Responsibility | Ensuring risks are captured and assigned to "owners" during the design phase prevents undefined hazards from surprising the construction team. | Document SiD outcomes. |  | Matthijs Klinkert
EBTA | EBTA266 | 2025-11-05 | NEL-STH-NSA-5200-CDR-REP-0001 | DESIGN REPORT - B063 5200 DRAINAGE DESIGN | Methodology | Implemented | Construction staging has been investigated and will be implemented by the Worksite Traffic Management Plan to delineate and minimize the duration/extent of high-risk activities working near live traffic with proposed temporary barrier works and associated signage. | FSR Traffic Management | Physical separation via barriers and reduced exposure time significantly lowers the statistical likelihood of vehicle-worker collisions. | Audit barrier installation. |  | Matthijs Klinkert
EBTA | EBTA267 | 2025-11-05 | NEL-STH-NSA-5200-CDR-REP-0001 | DESIGN REPORT - B063 5200 DRAINAGE DESIGN | Design | Implemented | EBTA have challenged the requirement of spill containment tanks ultimately removing several spill containment tanks from the SPARK’s reference design thus avoiding deep excavation for installation and ongoing maintenance requirements | FSR Excavation FSR Confined Space | Removing the tanks completely eliminates the need for deep excavations (collapse risk) and the future confined space entry risks associated with tank maintenance. | Verify drainage design. |  | Matthijs Klinkert
EBTA | EBTA268 | 2025-11-05 | NEL-STH-NSA-5200-CDR-REP-0001 | DESIGN REPORT - B063 5200 DRAINAGE DESIGN | Design | Implemented | Through engagement with NELP / DTP and EBTA’s delivery team several existing transverse drainage pipes across the mainline have been retained thus avoiding complicated boring techniques and deep launch shafts required for construction | FSR Excavation FSR Confined Space | Avoiding deep launch shafts eliminates the fall hazards and ground collapse risks associated with constructing large, deep access pits. | Assess condition of existing pipes. |  | Matthijs Klinkert
EBTA | EBTA269 | 2025-11-05 | NEL-STH-NSA-5200-CDR-REP-0001 | DESIGN REPORT - B063 5200 DRAINAGE DESIGN | Design | Implemented | Pits that are deeper than 4m have been designed out where avoidable as per BTN 033 Structural Requirements for Reinforced Concrete Drainage Pits Section 4.6. | FSR Excavation FSR Confined Space | Designing out deep pits reduces the complexity of safe access/egress for workers and minimizes the risks associated with deep trench shoring failure. | Verify pit schedule depths. |  | Matthijs Klinkert
EBTA | EBTA270 | 2025-11-05 | NEL-STH-NSA-5900-CTM-REP-0001_Rev0 |  | Design | Under Investigation | Pedestrian Countdown Timer - Discussions with NELP and DTP for the use of pedestrian countdown timer was investigated to reduce the likelihood for pedestrians stored in an exposed environment at Bulleen / Thompsons Road intersection. Per the VicRoads Supplements to AS1742.14:2014 cl2.4(d), this has been proposed to DTP for consideration and acceptance for use. | FSR Traffic Management | Provides pedestrians with clear information on crossing time, preventing them from being caught in the intersection during signal changes and exposed to live traffic. | Track DTP acceptance. |  | Matthijs Klinkert
EBTA | EBTA271 | 2025-11-05 | NEL-STH-NSA-5900-CUS-REP-0001 | DESIGN REPORT - B134 – UTILITIES – SEWER – U046 (MAINTENANCE HOLE MODIFICATIONS) | Design | Implemented | Digital Engineering – coordinated and fully federated model used to develop sewer alignment and prevent clashes. | FSR Utilities and Services FSR Excavation | Virtual clash detection identifies conflicts before breaking ground, preventing dangerous "clash on site" scenarios that lead to unplanned excavation or utility damage. | Update federated model. |  | Matthijs Klinkert
EBTA | EBTA272 | 2025-11-05 | NEL-STH-NSA-5900-CUS-REP-0001 | DESIGN REPORT - B134 – UTILITIES – SEWER – U046 (MAINTENANCE HOLE MODIFICATIONS) | Design | Implemented | Sewer manholes which are being lowered will have bolted manhole covers installed to resist dislodgement in the event of storm surcharge. | FSR Traffic Management FSR Confined Space | Prevents heavy covers from being blown off by water pressure, eliminating the risk of open holes (fall hazard) and loose covers becoming projectiles/obstacles for traffic. | Verify cover spec. |  | Matthijs Klinkert
EBTA | EBTA273 | 2025-11-05 | NEL-STH-NSA-5900-CUS-REP-0001 | DESIGN REPORT - B134 – UTILITIES – SEWER – U046 (MAINTENANCE HOLE MODIFICATIONS) | Design | Implemented | KNC3 and KNC5 maintenance holes will be structurally modified to accommodate trafficable loadings as they are currently located in the verge and will be located in a running lane / bus lane on completion of the works. | FSR Traffic Management FSR Plant and Equipment | Ensuring the asset can support heavy vehicle loads prevents structural collapse of the road surface, avoiding catastrophic accidents for public traffic. | Verify structural design. |  | Matthijs Klinkert
EBTA | EBTA274 | 2025-11-05 | NEL-STH-NSA-5900-CUS-REP-0001 | DESIGN REPORT - B134 – UTILITIES – SEWER – U046 (MAINTENANCE HOLE MODIFICATIONS) | Design | Implemented | The access cover for KNC5 maintenance hole will be re-oriented so that there is at minimum 1m clearance to an adjacent structure (the road barrier) to allow for safe entry & exit. | FSR Confined Space FSR Traffic Management | Providing adequate physical space ensures workers can safely enter and exit the confined space without being trapped against the barrier or forced into live traffic lanes. | Check clearance on drawings. |  | Matthijs Klinkert
EBTA | EBTA275 | 2025-11-05 | NEL-STH-NSA-5121-SBR-REP-0001 | DESIGN REPORT - B057 - BR121 – EASTERN FREEWAY EASTBOUND TO NEL NORTHBOUND OVER BUSWAY | Methodology | Implemented | Construction staging implemented to separate works around live traffic at the Eastern Freeway eastbound off ramp at Bulleen Road to remove the risk in the area with the bridge deck complete prior to opening to traffic. | FSR Traffic Management | Completing the bridge deck offline eliminates the high-risk interface of heavy construction occurring overhead of live traffic, removing dropped object risks for the public. | Verify diversion setup. |  | Matthijs Klinkert
EBTA | EBTA276 | 2025-11-05 | NEL-STH-NSA-5121-SBR-REP-0001 | DESIGN REPORT - B057 - BR121 – EASTERN FREEWAY EASTBOUND TO NEL NORTHBOUND OVER BUSWAY | Design | Implemented | Fall-protection barriers to the cut area of the busway to be cast-in-situ as extension of the blade wall (concrete upstand). Additionally, concrete wall design removes the need for ongoing inspection and maintenance when compared to cladding. | FSR Working at Heights | Concrete upstands provide permanent edge protection and eliminate the future working-at-heights risk associated with inspecting and maintaining separate cladding systems. | Verify upstand reinforcement. |  | Matthijs Klinkert
EBTA | EBTA277 | 2025-11-05 | NEL-STH-NSA-5121-SBR-REP-0001 | DESIGN REPORT - B057 - BR121 – EASTERN FREEWAY EASTBOUND TO NEL NORTHBOUND OVER BUSWAY | Methodology | Implemented | CFA Piles adopted over bored piles where possible to remove open hole and continuous slewing of pile rig during boring of pile and dumping of material. | FSR Piling FSR Excavation | CFA piling pumps concrete as the auger withdraws, eliminating the "open hole" fall hazard and reducing the need for the rig to slew back and forth to dump spoil. | Confirm CFA rig availability. |  | Matthijs Klinkert
EBTA | EBTA278 | 2025-11-05 | NEL-STH-NSA-5200-CPA-REP-0001 | DESIGN REPORT - B064 – 5200 SHARED USE PATH, CIVIL AND WATERWAYS | Design | Implemented | Avoiding steep batters, particularly adjacent to waterways to reduce plant rollover risk. FSR: Working adjacent to water ways waterways and plant and equipment | FSR Work On, Over Or Adjacent to Water FSR Plant and Equipment | Designing shallower gradients near water edges ensures the stability of heavy earthmoving plant, preventing catastrophic rollover incidents into the waterway. | Verify batter slopes. |  | Matthijs Klinkert
EBTA | EBTA279 | 2025-11-05 | NEL-STH-NSA-5200-CPA-REP-0001 | DESIGN REPORT - B064 – 5200 SHARED USE PATH, CIVIL AND WATERWAYS | Design | Implemented | Reduction of creek alignment works to minimise disturbance of concrete apron and lining adjacent the BEBO outlet structure and hence avoid temporary works requirements on existing structural elements or partial demolition and reinstatement. FSR: Working adjacent to water ways waterways and demolition | FSR Work On, Over Or Adjacent to Water FSR Demolition | Avoiding disturbance to the existing apron eliminates the risks associated with partial demolition and the complex temporary propping of aged water infrastructure. | Inspect BEBO apron condition. |  | Matthijs Klinkert
EBTA | EBTA280 | 2025-11-05 | NEL-STH-NSA-5200-CPA-REP-0001 | DESIGN REPORT - B064 – 5200 SHARED USE PATH, CIVIL AND WATERWAYS | Methodology | Implemented | Inclusion of sacrificial sheet piling to minimise area of intervention around the creek and reduce vegetation clearing scope as well as batter stabilisation scope. Relevant FSRs: Working adjacent to water ways waterways. Controls: Engineering Controls | FSR Work On, Over Or Adjacent to Water | Minimizing the intervention area prevents extensive vegetation clearing (preserving bank stability) and reduces the need for complex batter stabilization near water. | Verify piling limits. |  | Matthijs Klinkert
EBTA | EBTA281 | 2025-11-05 | NEL-STH-NSA-5200-CPA-REP-0001 | DESIGN REPORT - B064 – 5200 SHARED USE PATH, CIVIL AND WATERWAYS | Design | Implemented | Drainage assets elevated as close to surface as possible to minimise deep excavation, thus minimising the risk of undermining adjacent infrastructure and fall from height. Relevant FSRs: Excavation, Working at Heights. Controls: Engineering Controls | FSR Excavation FSR Working at Heights | Shallow excavations prevent the destabilization of nearby structures and significantly reduce the risk of workers falling into deep trenches. | Confirm invert levels. |  | Matthijs Klinkert
EBTA | EBTA282 | 2025-11-05 | NEL-STH-NSA-5100-CTW-REP-0010 | DESIGN REPORT - B202 - 5100 BULLEEN ROAD INTERCHANGE - TEMPORARY WORKS DESIGN STAGE B2.1 | Design | Implemented | Reuse of existing and ultimate pavement levels where possible to limit the required volume of works | FSR Traffic Management FSR Plant and Equipment | Reducing the total volume of civil works directly lowers the duration of plant operation and workforce exposure to live traffic environments. | Verify pavement levels. |  | Matthijs Klinkert
EBTA | EBTA283 | 2025-11-05 | NEL-STH-NSA-5100-CTW-REP-0010 | DESIGN REPORT - B202 - 5100 BULLEEN ROAD INTERCHANGE - TEMPORARY WORKS DESIGN STAGE B2.1 | Design | Implemented | Traffic modelling to ensure user safety is maintained with proposed alignment – considering queue length and driver behaviour. | FSR Traffic Management | Predictive modelling allows the design to accommodate actual driver behaviors and queue lengths, preventing rear-end collisions and dangerous weaving. | Archive traffic model report. |  | Matthijs Klinkert
EBTA | EBTA284 | 2025-11-05 | NEL-STH-NSA-5400-CDR-REP-0001 | Design Report - B079 - Zone 5400 Mainline Drainage (Complex) | Design | Adopted | Spill Containment Tank has been lifted up to surface level as much as possible reducing the extent of temporary works required to build it. | FSR Excavation FSR Confined Space | Raising the tank drastically reduces the depth of excavation required (lowering collapse risk) and simplifies future access, potentially avoiding deep confined space entry. | Verify tank pad level. |  | Matthijs Klinkert
EBTA | EBTA285 | 2025-11-05 | NEL-STH-NSA-5400-CDR-REP-0001 | Design Report - B079 - Zone 5400 Mainline Drainage (Complex) | Design | Adopted | Drainage pipe connections into BR607 culvert have been shifted to a location where it can penetrate the pre-cast portion of the culvert structure rather than the in-situ wing walls which would require more complicated and intricate formwork. | FSR Formwork & Falsework FSR Confined Space | Avoiding intricate formwork significantly reduces the manual handling burden and the time workers spend building complex structures in potentially restricted access areas. | Verify connection detail. |  | Matthijs Klinkert
EBTA | EBTA286 | 2025-11-05 | NEL-STH-NSA-5400-CDR-REP-0001 | Design Report - B079 - Zone 5400 Mainline Drainage (Complex) | Design | Adopted | Re-using existing drainage road crossings where possible to avoid installation of new drainage crossings. | FSR Excavation FSR Traffic Management | Eliminating the need for new crossings avoids deep trenching across live roads, reducing traffic disruption and worker exposure to live traffic risks. | Assess condition of existing pipes. |  | Matthijs Klinkert
EBTA | EBTA288 | 2025-11-05 | NEL-STH-NSA-5300-CPA-REP-0001 | Design Report - B080 – 5300/5400 SUP CIVIL AND WATERWAYS | Design | Adopted | Drainage assets elevated as close to surface as possible to minimise deep excavation, thus minimising the risk of undermining the existing running freeway during construction activity and minimising the risk of falling from heights. Relevant FSRs: Excavation, Working at Heights Controls: Engineering Controls | FSR Excavation FSR Working at Heights | Shallow excavations prevent the destabilization of the existing freeway and reduce the risk of workers falling into deep trenches or being trapped by collapse. | Confirm invert levels. |  | Matthijs Klinkert
EBTA | EBTA289 | 2025-11-05 | NEL-STH-NSA-5300-CPA-REP-0001 | Design Report - B080 – 5300/5400 SUP CIVIL AND WATERWAYS | Design | Adopted | Maximise use of flexible pipe to reduce the material mass for transport and manual handling. Relevant FSRs: Cranes and Lifting Controls: Substitution | FSR Cranes and Lifting | Lighter flexible pipes significantly reduce the physical strain on workers during transport and installation compared to rigid, heavy concrete pipes. | Approve pipe material submittal. |  | Matthijs Klinkert
EBTA | EBTA290 | 2025-11-05 | NEL-STH-NSA-5300-CPA-REP-0001 | Design Report - B080 – 5300/5400 SUP CIVIL AND WATERWAYS | Methodology | Adopted | Minimising need to remove redundant drainage assets (especially deep assets) and instead propose grout filling and lifting drainage lines. This will minimise the need for deep excavations, need for cranage adjacent deep excavation to remove exiting drainage, as well as potential exposure to hazardous materials (i.e. asbestos). Ongoing – to be discussed with relevant stakeholders/asset owners. Relevant FSRs: Excavation, Cranes and Lifting, Asbestos Controls: Substitution | FSR Excavation FSR Cranes and Lifting FSR Asbestos | Avoids the need for deep excavation and cranage to remove old pipes, significantly reducing the risk of disturbing hazardous materials like asbestos. | Confirm asset owner agreement. |  | Matthijs Klinkert
EBTA | EBTA291 | 2025-11-05 | NEL-STH-NSA-5900-CUW-REP-0001 | DESIGN REPORT - B135 – DTP MAINLINE HYDRANT WORKS | Design | Closed | Please confirm minimum cover of 1.2 m at all locations under arterial roads is provided. | FSR Traffic Management FSR Excavation | Ensuring adequate cover protects the pipes from traffic loads and prevents road surface deformation, maintaining safety for the travelling public. | Verify cover depth on drawings. |  | Matthijs Klinkert
EBTA | EBTA292 | 2025-11-05 | NEL-STH-NSA-5900-CUW-REP-0001 | DESIGN REPORT - B135 – DTP MAINLINE HYDRANT WORKS | Design | Closed | The proposed pipe crossings under DTP arterial roads have been designed with minimum 1200mm cover in accordance with DTP’s specification - Section 706. | FSR Traffic Management FSR Excavation | Adhering to DTP specifications ensures structural integrity under heavy traffic loads, preventing collapse or damage to the road surface. | Confirm cover depth onsite. |  | Matthijs Klinkert
EBTA | EBTA293 | 2025-11-05 | NEL-STH-NSA-5900-CUW-REP-0001 | DESIGN REPORT - B135 – DTP MAINLINE HYDRANT WORKS | Material | Closed | Use of HDPE Pipe under arterial roads may require DTP approval. | FSR Cranes and Lifting | Identifying lighter material options early allows for planning of safer manual handling practices compared to heavy concrete pipes. | Submit material approval request. |  | Matthijs Klinkert
EBTA | EBTA294 | 2025-11-05 | NEL-STH-NSA-5900-CUW-REP-0001 | DESIGN REPORT - B135 – DTP MAINLINE HYDRANT WORKS | Material | Closed | The proposed pipe crossings under DTP arterial roads have compliant minimum 1200mm pipe cover in accordance with DTP’s specification - Section 706. BTA is not aware of the need to seek for DTP’s approval to use HDPE pipes under arterial roads. | FSR Cranes and Lifting | Confirming the use of lighter HDPE pipes significantly reduces the physical strain on workers during transport and installation. | Proceed with HDPE procurement. |  | Matthijs Klinkert
EBTA | EBTA295 | 2025-11-05 | NEL-STH-NSA-5900-CRF-REP-0001 | Design Report - B112 - 5900 - Comms - Schematic and Architecture | Design | Completed | The detailed design has identified total number of access rings within each ring to comply the requirement that there shall be no more than ten (10) access switches within each access ring | FSR Utilities and Services | Ensuring network redundancy and limiting failure domains prevents widespread communication blackouts during emergency situations or maintenance. | Confirm switch count. |  | Matthijs Klinkert
EBTA | EBTA296 | 2025-11-05 | NEL-STH-NSA-5900-CRF-REP-0001 | Design Report - B112 - 5900 - Comms - Schematic and Architecture | Management | Completed | All equipment, patch panels, outlets, cabinets, and racks shall be clearly labelled in accordance with the approved label list. A list to be produced and submit in IFC documentation. RAI addressing to be provided by DTP. | FSR Plant and Equipment FSR Utilities and Services | Clear, standardized labeling prevents isolation errors during maintenance, ensuring workers do not accidentally interact with live or incorrect equipment. | Submit label list for IFC. |  | Matthijs Klinkert
EBTA | EBTA297 | 2025-11-05 | NEL-STH-NSA-5900-CRF-REP-0001 | Design Report - B112 - 5900 - Comms - Schematic and Architecture | Design | Completed | Cable lengths to be rationalised to reduce need of large cable drums sizes and minimize heavy handling / cranage risk. | FSR Cranes and Lifting FSR Plant and Equipment | Reducing the size and weight of cable drums allows for the use of smaller lifting equipment and reduces the severity of potential crush injuries during handling. | Verify cable schedule. |  | Matthijs Klinkert
EBTA | EBTA298 | 2025-11-05 | NEL-STH-NSA-5900-CRF-REP-0001 | Design Report - B112 - 5900 - Comms - Schematic and Architecture | Methodology | Completed | The use of winches to pull cable safely from cable drum. To avoid manual handling risks during construction. Draw string to be installed with blower to ease of fibre cable pulling. | FSR Plant and Equipment | Replacing strenuous manual pulling with mechanical winches and blowers directly prevents musculoskeletal injuries and repetitive strain. | Approve winch SWMS. |  | Matthijs Klinkert
EBTA | EBTA299 | 2025-11-05 | NEL-STH-NSA-5900-CRF-REP-0001 | Design Report - B112 - 5900 - Comms - Schematic and Architecture | Design | Completed | A marker tape with trace wire shall be placed above all conduits in accordance with the Wiring Rules. Enabling asset location and avoidance of impact during excavation. | FSR Utilities and Service FSR Excavation | Allows future crews to electronically locate non-conductive conduits before digging, preventing accidental utility strikes and service interruptions. | Inspect trench before backfill. |  | Matthijs Klinkert
EBTA | EBTA300 | 2025-11-05 | NEL-STH-NSA-5500-CDR-REP-0001 | DESIGN REPORT - B098 – 5500 DRAINAGE DESIGN – DONCASTER ROAD INTERCHANGE | Design | Adopted | Drainage re-alignment and utilising existing network as much as possible at Greythorn Rd to maximise clearance to HV to allow safe construction. Relevant FSRs: Buried services Controls: Engineering Controls | FSR Utilities and Services FSR Excavation | Maximizing clearance to High Voltage (HV) assets ensures safe construction buffers, preventing catastrophic electrical strikes during excavation. | Verify clearance on survey. |  | Matthijs Klinkert
EBTA | EBTA301 | 2025-11-05 | NEL-STH-NSA-5500-CDR-REP-0001 | DESIGN REPORT - B098 – 5500 DRAINAGE DESIGN – DONCASTER ROAD INTERCHANGE | Design | Adopted | Ramp D4 – drainage outlet updated to avoid connection into deep 12m pit and provide safer maintenance and construction. Relevant FSRs: Excavation, Working at Heights Controls: Elimination (where possible) | FSR Excavation FSR Working at Heights | Avoiding connections into deep pits eliminates the need for personnel to enter high-risk confined spaces or work at significant heights within shafts. | Verify outlet design. |  | Matthijs Klinkert
EBTA | EBTA302 | 2025-11-05 | NEL-STH-NSA-5500-CDR-REP-0001 | DESIGN REPORT - B098 – 5500 DRAINAGE DESIGN – DONCASTER ROAD INTERCHANGE | Design | Adopted | Heelsafe grates utilised where pedestrian traffic is expected to minimise tripping risk for pedestrians. Relevant FSRs: N/A – operation Controls: Elimination | NA | Specific grate design prevents heels from getting stuck, significantly reducing trip-and-fall incidents for the public walking through the area. | Inspect grate installation. |  | Matthijs Klinkert
EBTA | EBTA303 | 2025-11-05 | NEL-STH-NSA-5500-CDR-REP-0001 | DESIGN REPORT - B098 – 5500 DRAINAGE DESIGN – DONCASTER ROAD INTERCHANGE | Design | Adopted | Identification of existing pits within traffic lanes that do not need access and capped these pits to remove maintenance access Relevant FSRs: Traffic Management Controls: Elimination | FSR Traffic Management | Permanently capping pits in live lanes eliminates the need for future maintenance crews to close lanes and work in dangerous proximity to moving traffic. | Verify capping detail. |  | Matthijs Klinkert
EBTA | EBTA304 | 2025-11-05 | NEL-STH-NSA-5500-CDR-REP-0001 | DESIGN REPORT - B098 – 5500 DRAINAGE DESIGN – DONCASTER ROAD INTERCHANGE | Material | Adopted | Maximise use of flexible pipe to reduce the material mass for transport and handling Relevant FSRs: Cranes and Lifting Controls: Substitution | FSR Cranes and Lifting | Lighter flexible pipes significantly reduce the physical strain on workers during transport and installation compared to rigid, heavy concrete pipes. | Approve pipe material submittal. |  | Matthijs Klinkert
EBTA | EBTA305 | 2025-11-05 | NEL-STH-NSA-5500-CDR-REP-0001 | DESIGN REPORT - B098 – 5500 DRAINAGE DESIGN – DONCASTER ROAD INTERCHANGE | Design | Adopted | Re-using existing drainage road crossings where possible to avoid installation of new drainage crossings and working adjacent to live traffic / night works Relevant FSRs: Traffic Management Controls: Elimination | FSR Traffic Management | Eliminating the need for new crossings avoids deep trenching across live roads, reducing traffic disruption and worker exposure to live traffic risks. | Assess condition of existing pipes. |  | Matthijs Klinkert
EBTA | EBTA306 | 2025-11-05 | NEL-STH-NSA-5500-CDR-REP-0001 | DESIGN REPORT - B098 – 5500 DRAINAGE DESIGN – DONCASTER ROAD INTERCHANGE | Design | Adopted | Drainage assets elevated as close to surface as possible to minimise deep excavation, thus minimising the risk of undermining the existing running freeway during construction activity and minimising the risk of falling from heights. Relevant FSRs: Excavation, Working at Heights Controls: Engineering Controls | FSR Excavation FSR Working at Heights | Shallow excavations prevent the destabilization of the existing freeway and reduce the risk of workers falling into deep trenches or being trapped by collapse. | Confirm invert levels. |  | Matthijs Klinkert
EBTA | EBTA307 | 2025-11-05 | NEL-STH-NSA-5500-CDR-REP-0001 | DESIGN REPORT - B098 – 5500 DRAINAGE DESIGN – DONCASTER ROAD INTERCHANGE | Methodology | Adopted | Minimising need to remove redundant drainage assets (especially deep assets) and instead propose grout filling. This will minimise the need for deep excavations, need for cranage adjacent deep excavation to remove exiting drainage, as well as potential exposure to hazardous materials (i.e. asbestos). Ongoing – to be discussed with relevant stakeholders/asset owners. Relevant FSRs: Excavation, Cranes and Lifting, Asbestos Controls: Substitution | FSR Excavation FSR Cranes and Lifting FSR Asbestos | Avoids the need for deep excavation and cranage to remove old pipes, significantly reducing the risk of disturbing hazardous materials like asbestos. | Confirm asset owner agreement. |  | Matthijs Klinkert
EBTA | EBTA308 | 2025-11-05 | NEL-STH-NSA-5500-CDR-REP-0001 | DESIGN REPORT - B098 – 5500 DRAINAGE DESIGN – DONCASTER ROAD INTERCHANGE | Design | Adopted | Minimising the number of pits and drainage lines directly underneath overhead wires (LV and HV) Relevant FSRs: General Electrical Safety, Plant and Equipment, Cranes and Lifting, Utilities and Services Controls: Elimination, Engineering Controls | FSR General Electrical Safety FSR Plant and Equipment FSR Cranes and Lifting FSR Utilities and Services | Establishing a "no-go" zone for drainage works under wires prevents crane/excavator booms from arcing or striking live conductors during construction and maintenance. | Verify overhead clearances. |  | Matthijs Klinkert
EBTA | EBTA309 | 2025-11-05 | NEL-STH-NSA-5124-SBR-REP-0001 | DESIGN REPORT - B054 – BR110 – SB NEL TO EB EF OVERHEAD STRUCTURE (RAMP U7) | Methodology | Implemented | Construction staging has been investigated and will be implemented by the Worksite Traffic Management Plan to delineate and minimize the duration/extent of high-risk activities working near live traffic with proposed temporary barrier works and associated signage. | FSR Traffic Management | Physical separation via barriers and reduced exposure time significantly lowers the statistical likelihood of vehicle-worker collisions. | Audit barrier installation. |  | Matthijs Klinkert
EBTA | EBTA310 | 2025-11-05 | NEL-STH-NSA-5124-SBR-REP-0001 | DESIGN REPORT - B054 – BR110 – SB NEL TO EB EF OVERHEAD STRUCTURE (RAMP U7) | Methodology | Implemented | Construction staging implemented to separate works around live traffic with a temporary diversion of traffic at Thompsons Road and Bulleen Road to remove the risk in the area with the bridge deck complete prior to opening to traffic and deliver works north of Thompsons when traffic is switched back to the permanent Bulleen Road Bridge. | FSR Traffic Management | Completing the bridge deck offline eliminates the high-risk interface of heavy construction occurring overhead of live traffic, removing dropped object risks for the public. | Verify diversion setup. |  | Matthijs Klinkert
EBTA | EBTA311 | 2025-11-05 | NEL-STH-NSA-5124-SBR-REP-0001 | DESIGN REPORT - B054 – BR110 – SB NEL TO EB EF OVERHEAD STRUCTURE (RAMP U7) | Methodology | Implemented | Precast Driven Piles adopted over bored piles where possible to remove open hole and remove the need to dispose of pile spoil material. | FSR Excavation FSR Piling | Eliminates the hazard of "open holes" (deep excavations) which pose fall risks to personnel and collapse risks to adjacent plant. | Confirm pile driveability. |  | Matthijs Klinkert
EBTA | EBTA312 | 2025-11-05 | NEL-STH-NSA-5124-SBR-REP-0001 | DESIGN REPORT - B054 – BR110 – SB NEL TO EB EF OVERHEAD STRUCTURE (RAMP U7) | Modularisation | Implemented | Steel reinforcement to pile cap bottom mat, pier column and crosshead will be modelled and prefabricated to drop, reducing on site steel reinforcement fabrication to the top mat / sides of the pile cap to tie in the prefabricated sections. | FSR Formwork & Falsework FSR Working at Heights | Significantly reduces the manual handling and repetitive strain injuries associated with tying steel in-situ, often in awkward positions or at height. | Verify cage lifting points. |  | Matthijs Klinkert
EBTA | EBTA313 | 2025-11-05 | NEL-STH-NSA-5124-SBR-REP-0001 | DESIGN REPORT - B054 – BR110 – SB NEL TO EB EF OVERHEAD STRUCTURE (RAMP U7) | Methodology | Implemented | Self-Propelled Modular Transport (SPMT) construction method adopted for spans over the eastbound carriageway to enable spans to be assembled offline and deliver in single section to reduce working around live traffic, multiple carriageway closures and working at heights. | FSR Traffic Management FSR Working at Heights FSR Plant and Equipment | Assembling spans "offline" drastically reduces the time workers spend working at heights over live traffic and minimizes the need for high-risk carriageway closures. | Approve SPMT lift plan. |  | Matthijs Klinkert
EBTA | EBTA314 | 2025-11-05 | NEL-STH-NSA-5124-SBR-REP-0001 | DESIGN REPORT - B054 – BR110 – SB NEL TO EB EF OVERHEAD STRUCTURE (RAMP U7) | Design | Implemented | By adopting standardised solutions to columns and crosshead sizes reduces the number of temporary designs required to construct piers across the project. As such, onsite the team will be able to focus on training, constructing and inspection of formworks that are simple and repeatable. | FSR Formwork & Falsework FSR Temporary Works | Standardisation simplifies the construction process, making training easier and reducing the likelihood of installation errors that could lead to formwork failure. | Approve standard formwork design. |  | Matthijs Klinkert
EBTA | EBTA315 | 2025-11-05 | NEL-STH-NSA-5500-CTW-REP-0011 | Design Report – E018N-5500-0011 – DONCASTER STAGE D1.1C-1 – TEMPORARY TRAFFIC SIGNALS |  |  | There is no table with the columns 'Number', 'Item', 'Status', and 'Design Stage' present in the provided images. However, there is an Engineered Safety section under '9. Safety in Design' which details the SiD (Safety in Design) context, methodology, and outcomes. This section outlines the SiD workshops, temporary works and constructability considerations, review processes by subject matter experts, and the documentation of outcomes in design reports. |  |  |  |  | Matthijs Klinkert
EBTA | EBTA316 | 2025-11-05 | NEL-STH-NSA-5900-CNW-REP-0001.1 |  |  |  | Section 9.2, 'Engineered Safety', states: 'Not applicable to this design package. This is addressed by the relevant design packages noted in Section 6.3.' |  |  |  |  | Matthijs Klinkert
EBTA | EBTA317 | 2025-11-05 | NEL-STH-NSA-5608-SBR-REP-0001 | Design Report - B106 - BR607 - Koonung Creek Culvert East of Elgar Rd | Design | Adopted | Removal of piling within the creek. The original TAN B design was a pile and plank structure which has now been changed to a pre-cast crown unit system on base slab. We achieved the below through this approach: - Avoiding having a piling rig on unstable ground; - Avoid providing access for large piling rigs; - Avoids lifting in of large pile reinforcement cages. | FSR Work On, Over Or Adjacent to Water FSR Piling FSR Plant and Equipment | Avoids placing heavy piling rigs on unstable creek ground and eliminates the lifting of large pile reinforcement cages in a sensitive environment. | Verify base slab design. |  | Matthijs Klinkert
EBTA | EBTA318 | 2025-11-05 | NEL-STH-NSA-5608-SBR-REP-0001 | Design Report - B106 - BR607 - Koonung Creek Culvert East of Elgar Rd | Modularisation | Adopted | The corner crown units (the units bending the alignment) were originally proposed to be cast in-situ, which would result in tall formwork structures and tall reinforcement cages which would need to be supported. We have designed these out by working with the subcontractor to provide these as custom pre-cast units. | FSR Formwork & Falsework FSR Working at Heights | Eliminates the risks associated with erecting and supporting tall formwork structures and working at height to fix reinforcement cages. | Verify lifting study. |  | Matthijs Klinkert
EBTA | EBTA319 | 2025-11-05 | NEL-STH-NSA-5200-CBR-REP-0001 | Design Report - B186 - 5200A - Structural Barriers and Gantry Foundations | Methodology | Implemented | Pier and gantry protection barriers have been optimised and slip form barriers is preferred to reduce delivery and lifting of precast concrete barriers by cranes and mobile plants. | FSR Cranes and Lifting FSR Plant and Equipment | Significantly reduces the number of crane lifts and mobile plant movements required, lowering the risk of suspended load incidents. | Approve slip form methodology. |  | Matthijs Klinkert
EBTA | EBTA320 | 2025-11-05 | NEL-STH-NSA-5200-CBR-REP-0001 | Design Report - B186 - 5200A - Structural Barriers and Gantry Foundations | Design | Implemented | Barrier design has been optimised through road safety barrier risk assessment where some of the performance level barriers can be changed to test level barriers as per VicRoads standard drawings. The requirement of either pile or friction slab foundation for performance level barriers can then be eliminated. | FSR Excavation FSR Piling | Removing the foundation requirement eliminates the deep excavation and piling works associated with heavy-duty barrier foundations. | Verify barrier assessment. |  | Matthijs Klinkert
EBTA | EBTA321 | 2025-11-05 | NEL-STH-NSA-5511-SBR-REP-0001 | DESIGN REPORT - B095 - BR502 – DONCASTER ROAD OVER BUSWAY | Methodology | Implemented | Construction staging implemented to separate works around live traffic with a temporary diversion of traffic at High Street and Doncaster Road to remove the risk in the area with the bridge deck complete prior to opening to traffic. • Relevant FSRs: Traffic Management Controls: Elimination | FSR Traffic Management | Completing the bridge deck offline eliminates the high-risk interface of heavy construction occurring overhead of live traffic. | Verify diversion setup. |  | Matthijs Klinkert
EBTA | EBTA322 | 2025-11-05 | NEL-STH-NSA-5511-SBR-REP-0001 | DESIGN REPORT - B095 - BR502 – DONCASTER ROAD OVER BUSWAY | Methodology | Implemented | Top-down construction for the bridge deck has been used to reduce the risk of working at height and permanent barriers at live edge will be installed prior to excavation. • Relevant FSRs: Working at Heights, Excavation, Cranes and Lifting Controls: Engineering Controls, Elimination | FSR Working at Heights FSR Excavation FSR Cranes and Lifting | Installing permanent barriers before excavation provides immediate edge protection, significantly reducing fall risks and protecting workers during the dig. | Verify construction sequence. |  | Matthijs Klinkert
EBTA | EBTA323 | 2025-11-05 | NEL-STH-NSA-5511-SBR-REP-0001 | DESIGN REPORT - B095 - BR502 – DONCASTER ROAD OVER BUSWAY | Design | Implemented | Number of kerb bars reduced in the optimised design to reduce the risk of manual handling. Risk: Manual handling Controls: Elimination (partial) | FSR Cranes and Lifting | Reducing the quantity of bars directly decreases the frequency and cumulative load of manual handling tasks, preventing musculoskeletal injuries. | Verify design quantity. |  | Matthijs Klinkert
EBTA | EBTA324 | 2025-11-05 | NEL-STH-NSA-5500-CTW-REP-0007 | DESIGN REPORT - E018-5500-0006-00 - DONCASTER ROAD – NEW BUS STOP CONSTRUCTION - TEMPORARY TRAFFIC SIGNALS | Management |  | There is no explicit table with columns 'Number', 'Item', 'Status', and 'Design Stage' present in the provided images. However, there is an 'Engineered Safety' (Safety in Design) section which describes the methodology for considering safety risks, constructability, and design review input from various parties. SiD (Safety in Design) workshops are conducted, risks are registered, mitigation documented, and both formal and informal reviews are conducted for constructability and road safety. | FSR Chain of Responsibility | Early identification of hazards ensures safety is engineered into the design rather than managed reactively on site. | Document SiD outcomes. |  | Matthijs Klinkert
EBTA | EBTA325 | 2025-11-05 | NEL-STH-NSA-5499-CTW-REP-0001 | EASTERN FREEWAY UPGRADES - BURKE TO TRAM - TEMPORARY WORK - 5499-TW017 - DESIGN REPORT | Methodology |  | There is no table with the columns 'Number', 'Item', 'Status', and 'Design Stage' in the provided images. However, there is an 'Engineered Safety' related section under '10. Safety in Design' and relevant guidance in 'Risks and Limitation' and the 'Information Sheet'. These sections highlight designed safety actions, such as: - Material source validation and site suitability testing via Dynamic Cone Penetrometer (DCP) at specified frequency. - Limitation of ground information; nomination for additional frequency and location testing. - Plant position and slope offset requirements; installation of barrier systems to prevent instability. - Awareness of and mitigation for identified or unidentified nearby buried services/infrastructure. - Construction controls and operation pressures not to exceed design specifications. - Ongoing observation of site and performance monitoring, with requirement to seek additional advice or halt work if changes, excessive deformation, or cracking is detected or conditions vary from those assumed in design. These points are detailed stipulations for safety during design and construction but are not organized in the requested table format. | FSR Excavation FSR Plant and Equipment FSR Utilities and Services | Strict ground testing and plant positioning requirements prevent catastrophic ground failures, excavator rollovers, and contact with unknown services. | Review geotechnical monitoring logs. |  | Matthijs Klinkert
EBTA | EBTA326 | 2025-11-05 | NEL-STH-NSA-5300-CBR-REP-0001 | Design Report – B085 – 5300/5400/5500 Road Barriers East | Methodology | Applied | Use of Slipform to construct barriers where possible eliminates the risks associated with lifting in pre-cast barriers with Franna cranes. | FSR Cranes and Lifting FSR Plant and Equipment | Eliminates high-risk pick-and-carry crane operations (Franna), reducing the risk of dropped loads and plant-pedestrian interaction. | Verify slipform availability. |  | Matthijs Klinkert
EBTA | EBTA327 | 2025-11-05 | NEL-STH-NSA-5300-CBR-REP-0001 | Design Report – B085 – 5300/5400/5500 Road Barriers East | Design | Applied | Barriers have been used on the project to also function as retaining walls where feasible. This eliminates the requirement and the risks associated with building additional retaining walls where they can be designed out. | FSR Excavation FSR Formwork & Falsework | Designing out separate retaining walls eliminates the excavation, formwork, and manual handling risks associated with constructing those additional structures. | Verify barrier structural capacity. |  | Matthijs Klinkert
EBTA | EBTA328 | 2025-11-05 | NEL-STH-NSA-5300-CBR-REP-0001 | Design Report – B085 – 5300/5400/5500 Road Barriers East | Design | Applied | Gantry protection barriers have been combined with the gantry foundations. This eliminates the total quantity of performance level barriers which need to be constructed, eliminating any safety issues associated with their construction. | FSR Excavation FSR Piling | Reducing the total quantity of barriers constructed directly reduces the workforce's exposure to plant, traffic, and excavation hazards during installation. | Verify foundation integration details. |  | Matthijs Klinkert
EBTA | EBTA329 | 2025-11-05 | NEL-STH-NSA-5400-CRW-REP-0001 | DESIGN REPORT - B077 – 5400 MAINLINE ALIGNMENT AND CIVIL WORKS | Methodology | Implemented | Construction Staging has been investigated and will be implemented by the Worksite Traffic Management Plan to delineate and minimize the duration/extent of high-risk activities working near live traffic with proposed temporary barrier works and associated signage. | FSR Traffic Management | Physical separation via barriers and reduced exposure time significantly lowers the statistical likelihood of vehicle-worker collisions. | Audit barrier installation. |  | Matthijs Klinkert
EBTA | EBTA330 | 2025-11-05 | NEL-STH-NSA-5400-CRW-REP-0001 | DESIGN REPORT - B077 – 5400 MAINLINE ALIGNMENT AND CIVIL WORKS | Design | Implemented | ITS maintenance access bay at CH CEE 16750 from the freeway has been provided at location where there is a full width shoulder and good sight lines for safe access by maintenance vehicles. | FSR Traffic Management FSR Plant and Equipment | Positioning access bays at locations with optimal sight lines and shoulder width ensures maintenance vehicles can enter/exit traffic lanes safely without causing collisions. | Verify sight distance on site. |  | Matthijs Klinkert
EBTA | EBTA331 | 2025-11-05 | NEL-STH-NSA-5100-CTW-REP-0001 | Design Report - Bulleen Stage B1.1 & B1.2 Temporary Traffic Signals |  |  | Engineered Safety is the next generation of safety in design and looks to engineer out risk and engineer in health at every stage of a project lifecycle for our clients and product end user through trusted and collaborative partnerships within the alliance and our supply chain. With inclusivity and connectivity across functions, we listen to and learn from our people improving how we plan for and go to work every day. The Engineered Safety process has investigated / included the following key Initiatives in Table 9.3 below: [Table shows N/A, i.e., no specific engineered safety items were listed in the table for this design package]. |  |  |  |  | Matthijs Klinkert
EBTA | EBTA332 | 2025-11-05 | NEL-STH-NSA-5300-SSG-REP-0001 | DESIGN REPORT - B086 – 5300/5400/5500 – SIGNAGE AND ITS GANTRIES | Design | Completed | Optimization in the number of gantries - Where possible and compliant the number of gantries is optimized. Where possible ITS (Intelligent Transport Systems) signs LUMS has proposed to be mounted on the bridge structure instead of independent structure to minimize the construction and maintenance effort for additional structure. | FSR Working at Heights FSR Traffic Management | Eliminating independent gantry structures reduces the need for separate foundations and reduces future maintenance work over live traffic. | Verify structural mount details. |  | Matthijs Klinkert
EBTA | EBTA333 | 2025-11-05 | NEL-STH-NSA-5300-SSG-REP-0001 | DESIGN REPORT - B086 – 5300/5400/5500 – SIGNAGE AND ITS GANTRIES | Design | Completed | Where the cantilever is longer than 9m. Portal gantry is adopted. | FSR Excavation FSR Piling | Prevents the need for excessively deep or large foundations required for long cantilevers, reducing excavation risks and potential instability. | Verify gantry spans. |  | Matthijs Klinkert
EBTA | EBTA334 | 2025-11-05 | NEL-STH-NSA-5300-SSG-REP-0001 | DESIGN REPORT - B086 – 5300/5400/5500 – SIGNAGE AND ITS GANTRIES | Design | Completed | Where gantry foundations are in proximity of retaining walls, noise wall and their foundations – Combined foundation design has been adopted. (5300-SSG-P-52-North leg, 5300-SSG-P-56-57-North leg and south leg, 5400-SSG-P-63 -South leg, 5400-SSG-P-70-South leg). DD stage further review to be done to optimize structural spacing and reduce quantity of gantry piles across the project. This will allow flexibility in designing for clash mitigation and will reduce construction time and effort. Where excavation is needed to construct the pile-cap, design to minimize excavation depth. | FSR Excavation FSR Piling | Reducing the total number of piles and separate foundations required directly decreases the workforce's exposure to piling rigs and open excavations. | Review combined footing details. |  | Matthijs Klinkert
EBTA | EBTA335 | 2025-11-05 | NEL-STH-NSA-5300-SSG-REP-0001 | DESIGN REPORT - B086 – 5300/5400/5500 – SIGNAGE AND ITS GANTRIES | Design | Completed | Prewiring of gantry and attaching CCTV poles assembly before installation off-site under a controlled environment. This will eliminate risks associated with working: in challenging terrain, at heights/near free edges, in extreme weather and in proximity to live traffic for this task. LUMS signs will be installed on the ground before lifting. CCTV and VMS (Variable message sign) can be installed after. Gantry leg boxes can be installed before or after gantry lift. | FSR Working at Heights FSR Traffic Management | Shifting complex assembly tasks from the gantry (at height over traffic) to the ground eliminates fall risks and reduces workers' exposure to weather and live traffic. | Inspect pre-assembly QA. |  | Matthijs Klinkert
EBTA | EBTA336 | 2025-11-05 | NEL-STH-NSA-5300-SSG-REP-0001 | DESIGN REPORT - B086 – 5300/5400/5500 – SIGNAGE AND ITS GANTRIES | Methodology | Completed | Limit the maximum gantry member length to 40m for transportation. This will allow greater control over transportation logistics and programming deliveries away from peak traffic periods and minimize exposure to traffic-related hazards. | FSR Traffic Management FSR Plant and Equipment | Avoiding peak traffic for oversized deliveries significantly reduces the likelihood of heavy haulage interacting with the public, preventing potential road accidents. | Approve logistics plan. |  | Matthijs Klinkert
EBTA | EBTA337 | 2025-11-05 | NEL-STH-NSA-5300-SSG-REP-0001 | DESIGN REPORT - B086 – 5300/5400/5500 – SIGNAGE AND ITS GANTRIES | Methodology | Completed | The girder spikes will be completed on-ground and then lifted by crane to connect to the gantry’s columns. Construction recommended splices to be bolted not welded at site. Location of splices and lifting lugs to be identified and clearly specified in design at DD stage and construction sequence to be added. | FSR Cranes and Lifting FSR Working at Heights | Bolting on the ground eliminates the fire/fume risks of onsite welding and removes the need for workers to perform lengthy connection tasks while suspended at height. | Verify lifting lug certification. |  | Matthijs Klinkert
EBTA | EBTA338 | 2025-11-05 | NEL-STH-NSA-5300-SSG-REP-0001 | DESIGN REPORT - B086 – 5300/5400/5500 – SIGNAGE AND ITS GANTRIES | Design | Completed | Power arrangement and functional and protective earthing arrangement at the gantry structure to be reviewed by Certified engineers at shared ITS Asset devices at shared gantry. Earthing assessment of the Gantries to be carried out in the next design stage. More design details to be produced for any special earthing requirement. | FSR Utilities and Services FSR Plant and Equipment | Certified review and proper earthing design prevents electrical faults and shock hazards for maintenance personnel working on shared ITS assets. | Archive earthing assessment. |  | Matthijs Klinkert
EBTA | EBTA339 | 2025-11-05 | NEL-STH-NSA-5500-CRW-REP-0001 | DESIGN REPORT - B097 – DONCASTER ROAD INTERCHANGE – ALIGNMENTS AND CIVIL DESIGN INCLUDING LANDSCAPING | Design | Adopted | Civil re-grading at Greythorn Rd to maximise clearance to HV as much as possible to allow safe construction | FSR Utilities and Services FSR Excavation | Maximizing vertical clearance to HV lines ensures safe operation of construction plant (excavators/cranes) and prevents catastrophic electrical arcing. | Maximizing vertical clearance to HV lines ensures safe operation of construction plant (excavators/cranes) and prevents catastrophic electrical arcing. |  | Matthijs Klinkert
EBTA | EBTA340 | 2025-11-05 | NEL-STH-NSA-5500-CRW-REP-0001 | DESIGN REPORT - B097 – DONCASTER ROAD INTERCHANGE – ALIGNMENTS AND CIVIL DESIGN INCLUDING LANDSCAPING | Methodology | Adopted | Bridge alignment designed to allow for offline construction | FSR Traffic Management FSR Working at Heights | Constructing the bridge away from active traffic lanes eliminates the high-risk interface between the public and overhead heavy construction activities. | Verify construction staging. |  | Matthijs Klinkert
EBTA | EBTA341 | 2025-11-05 | NEL-STH-NSA-5500-CRW-REP-0001 | DESIGN REPORT - B097 – DONCASTER ROAD INTERCHANGE – ALIGNMENTS AND CIVIL DESIGN INCLUDING LANDSCAPING | Design | Adopted | Pedestrian crossing added near Gardinia Rd to facilitate safer pedestrian movements | FSR Traffic Management | Provides a designated, controlled point for pedestrians to cross, reducing the likelihood of uncontrolled person-to-vehicle collisions in public areas. | Audit crossing signal timing. |  | Matthijs Klinkert
EBTA | EBTA342 | 2025-11-05 | NEL-STH-NSA-5500-CRW-REP-0001 | DESIGN REPORT - B097 – DONCASTER ROAD INTERCHANGE – ALIGNMENTS AND CIVIL DESIGN INCLUDING LANDSCAPING | Design | Adopted | Staggering pedestrian crossing near Doncaster Road to facilitate safer pedestrian movements | FSR Traffic Management | Staggering the crossing forces pedestrians to face oncoming traffic before the second stage of the crossing, reducing the risk of "trap" incidents and accidental strikes. | Verify refuge island width. |  | Matthijs Klinkert
EBTA | EBTA343 | 2025-11-05 | NEL-STH-NSA-5500-CRW-REP-0001 | DESIGN REPORT - B097 – DONCASTER ROAD INTERCHANGE – ALIGNMENTS AND CIVIL DESIGN INCLUDING LANDSCAPING | Design | Adopted | Partial U-turn control at Hender Street intersection to reduce potential vehicle x pedestrian crossings | FSR Traffic Management | Removing U-turn capabilities at busy intersections directly eliminates a high-risk vehicle movement that frequently conflicts with pedestrian crossing phases. | Verify signal phase logic. |  | Matthijs Klinkert
EBTA | EBTA344 | 2025-11-05 | NEL-STH-NSA-5500-CRW-REP-0001 | DESIGN REPORT - B097 – DONCASTER ROAD INTERCHANGE – ALIGNMENTS AND CIVIL DESIGN INCLUDING LANDSCAPING | Design | Adopted | Raised safety platforms to lower vehicle speeds and increase user safety | FSR Traffic Management | Physical speed reduction measures force drivers to slow down at conflict points, significantly reducing the severity and likelihood of pedestrian-vehicle accidents. | Verify platform design grades. |  | Matthijs Klinkert
EBTA | EBTA345 | 2025-11-05 | NEL-STH-NSA-5500-CRW-REP-0001 | DESIGN REPORT - B097 – DONCASTER ROAD INTERCHANGE – ALIGNMENTS AND CIVIL DESIGN INCLUDING LANDSCAPING | Design | Adopted | Removal of pedestrian crossing at Hender St x Doncaster Rd to remove conflict with left-turn vehicles outside Hender St | FSR Traffic Management | Completely removes the physical interface between pedestrians and left-turning vehicles at a high-conflict location, preventing collisions. | Update wayfinding signage. |  | Matthijs Klinkert
EBTA | EBTA346 | 2025-11-05 | NEL-STH-NSA-5500-CRW-REP-0001 | DESIGN REPORT - B097 – DONCASTER ROAD INTERCHANGE – ALIGNMENTS AND CIVIL DESIGN INCLUDING LANDSCAPING | Design | Adopted | Removed right turn at Winfield | FSR Traffic Management | Eliminating right-hand turns across oncoming lanes of traffic reduces the number of conflict points and the likelihood of high-impact T-bone collisions.Verify line marking plan. | Verify line marking plan. |  | Matthijs Klinkert
EBTA | EBTA347 | 2025-11-05 | NEL-STH-NSA-5500-CRW-REP-0001 | DESIGN REPORT - B097 – DONCASTER ROAD INTERCHANGE – ALIGNMENTS AND CIVIL DESIGN INCLUDING LANDSCAPING | Design | Adopted | Extending SUP connecting from Koonung Creek Road to Winfield Road to allow for safer pedestrian movements | FSR Traffic Management | Providing a dedicated, continuous path separates pedestrians and cyclists from road traffic, significantly reducing the likelihood of vehicle-user collisions. | Verify SUP pavement finish. |  | Matthijs Klinkert
EBTA | EBTA348 | 2025-11-05 | NEL-STH-NSA-5500-CRW-REP-0001 | DESIGN REPORT - B097 – DONCASTER ROAD INTERCHANGE – ALIGNMENTS AND CIVIL DESIGN INCLUDING LANDSCAPING | Management | Adopted | Co-locating key items requiring maintenance (e.g. cabinets, Incident Response Area etc) to better facilitate off-freeway parking and allow safer access | FSR Traffic Management FSR Plant and Equipment | Grouping assets in areas with safe off-freeway parking eliminates the need for maintenance crews to stop on active shoulders, reducing exposure to live traffic. | Finalize cabinet layouts. |  | Matthijs Klinkert
EBTA | EBTA349 | 2025-11-05 | NEL-STH-NSA-5500-CRW-REP-0001 | DESIGN REPORT - B097 – DONCASTER ROAD INTERCHANGE – ALIGNMENTS AND CIVIL DESIGN INCLUDING LANDSCAPING | Design | Adopted | Reduction in crossfall to lower Doncaster Road at tie-in | FSR Traffic Management | Optimizing the road gradient at tie-ins improves vehicle handling and stability, especially for heavy vehicles, reducing the risk of loss-of-control incidents. | Verify survey levels at tie-in. |  | Matthijs Klinkert
EBTA | EBTA350 | 2025-11-05 | NEL-STH-NSA-5500-CRW-REP-0001 | DESIGN REPORT - B097 – DONCASTER ROAD INTERCHANGE – ALIGNMENTS AND CIVIL DESIGN INCLUDING LANDSCAPING | Design | Adopted | Inclusion of asphalt geogrid inside resurfacing to reduce maintenance requirements | FSR Traffic Management | Geogrid reinforcement reduces pavement cracking and potholes, leading to fewer emergency repair call-outs and less frequent exposure of workers to live traffic for maintenance. | Approve geogrid material data. |  | Matthijs Klinkert
EBTA | EBTA351 | 2025-11-05 | NEL-STH-NSA-5500-CRW-REP-0001 | DESIGN REPORT - B097 – DONCASTER ROAD INTERCHANGE – ALIGNMENTS AND CIVIL DESIGN INCLUDING LANDSCAPING | Design | Adopted | 1m offset allowed for water main to allow for safe excavation | FSR Utilities and Services FSR Excavation | Providing a physical buffer between the asset and the excavation zone reduces the risk of accidental strikes and subsequent flooding or soil instability during works. | Verify offset on IFC drawings. |  | MatthiVerify offset on IFC drawings.js Klinkert
EBTA | EBTA352 | 2025-11-05 | NEL-STH-NSA-5500-CRW-REP-0001 | DESIGN REPORT - B097 – DONCASTER ROAD INTERCHANGE – ALIGNMENTS AND CIVIL DESIGN INCLUDING LANDSCAPING | Methodology | Adopted | Pressure reducing station co-located to have shared access with Koonung Carpark, protected behind barrier | FSR Traffic Management FSR Utilities and Services | Utilizing an existing carpark for access ensures maintenance personnel can park and work entirely away from live freeway traffic, protected by physical barriers. | Confirm barrier specification. |  | Matthijs Klinkert
EBTA | EBTA353 | 2025-11-05 | NEL-STH-NSA-5500-CRW-REP-0001 | DESIGN REPORT - B097 – DONCASTER ROAD INTERCHANGE – ALIGNMENTS AND CIVIL DESIGN INCLUDING LANDSCAPING | Design | Adopted | Planters adjacent to roadway provided with ample spacing for safe maintenance access from freeway | FSR Traffic Management | Wide spacing allows maintenance vehicles to pull over and crews to work with sufficient clearance from the running lane, minimizing the risk of vehicle-person strikes. | Verify planter setout. |  | Matthijs Klinkert
EBTA | EBTA354 | 2025-11-05 | NEL-STH-NSA-5500-CRW-REP-0001 | DESIGN REPORT - B097 – DONCASTER ROAD INTERCHANGE – ALIGNMENTS AND CIVIL DESIGN INCLUDING LANDSCAPING | Design | Adopted | No-maintenance planting provided above rock cutting to remove need for access over the cutting | FSR Working at Heights | By selecting species that do not require pruning or care, the design completely removes the need for workers to access the top of the cutting, eliminating fall risks. | Approve plant schedule. |  | Matthijs Klinkert
EBTA | EBTA355 | 2025-11-05 | NEL-STH-NSA-5500-CRW-REP-0001 | DESIGN REPORT - B097 – DONCASTER ROAD INTERCHANGE – ALIGNMENTS AND CIVIL DESIGN INCLUDING LANDSCAPING | Design | Adopted | Strip of planting along Doncaster Rd – green buffer to separate pedestrians from the road | FSR Traffic Management | Providing a physical and visual green barrier between the path and the road reduces the likelihood of pedestrians accidentally entering live traffic lanes. | Verify planting schedule. |  | Matthijs Klinkert
EBTA | EBTA356 | 2025-11-05 | NEL-STH-NSA-5500-CRW-REP-0001 | DESIGN REPORT - B097 – DONCASTER ROAD INTERCHANGE – ALIGNMENTS AND CIVIL DESIGN INCLUDING LANDSCAPING | Design | Adopted | Shaping of landscaped areas ensure potential vehicle trajectories do not impact barrier performance | FSR Traffic Management | Strategic contouring of the ground ensures that if a vehicle leaves the road, it will interact with safety barriers as designed, preventing rollover or barrier bypass. | Audit final site grading. |  | Matthijs Klinkert
EBTA | EBTA357 | 2025-11-05 | NEL-STH-NSA-5300-ULS-REP-0001 | Design Report - B090 - 5300/5400 LANDSCAPING | Management | Adopted | Reduce the amount of trees impacted to reduced tree removals and the risks associated with tree removal. | FSR Plant and Equipment | Minimizing the need for arboriculture work directly eliminates the high-risk activities associated with professional tree felling and heavy wood-chipping machinery. | Verify tree protection zones. |  | Matthijs Klinkert
EBTA | EBTA358 | 2025-11-05 | NEL-STH-NSA-5300-ULS-REP-0001 | Design Report - B090 - 5300/5400 LANDSCAPING | Management | Adopted | Soil amelioration advice included in technical spec. This allows construction the opportunity to reuse topsoil and reduce truck movement on/off site. | FSR Plant and Equipment FSR Traffic Management | Reusing soil on-site significantly reduces the number of truck movements required for spoil removal and material delivery, lowering the risk of plant-personnel interaction. | Review soil test results. |  | Matthijs Klinkert
EBTA | EBTA359 | 2025-11-05 | NEL-STH-NSA-5300-ULS-REP-0001 | Design Report - B090 - 5300/5400 LANDSCAPING | Design | Adopted | Change of the pots size to Tubestock/ 200 millimetre pot to reduce the manual handling of the plants on the site. (Note 400mm dia. pot sizes have been retained for some trees within parkland areas at Council Request) | FSR Plant and Equipment | Utilizing smaller, lighter plant containers significantly reduces the physical strain and risk of musculoskeletal injuries for workers during planting activities. | Confirm 400mm pots for Council areas. |  | Matthijs Klinkert
EBTA | EBTA360 | 2025-11-05 | NEL-STH-NSA-5200-CTW-REP-0001 | Design Report - B195 - Temporary SUP Package 3 (Koonung Ck Reserve West) | Design | Complete | The design basis for the temporary SUPs is to use as much of the permanent SUP alignment and construction specification as possible so that there is an opportunity that the temporary works can be left in place and adopted as the permanent works. Hence eliminating the need to 'build twice'. | FSR Traffic Management FSR Plant and Equipment | By adopting temporary works as permanent, the total duration of construction activity and plant operation is reduced, lowering workers' exposure to site hazards. | Verify SUP construction specs. |  | Matthijs Klinkert
EBTA | EBTA361 | 2025-11-05 | NEL-STH-NSA-5200-CTW-REP-0001 | Design Report - B195 - Temporary SUP Package 3 (Koonung Ck Reserve West) | Design | Complete | User safety – signs and lines to assist way-finding. Desirable grades with clearance to obstacles selected | FSR Traffic Management | Clear delineation and compliant grades prevent user confusion and collisions between pedestrians and cyclists in public areas. | Finalize signage and line marking. |  | Matthijs Klinkert
EBTA | EBTA362 | 2025-11-05 | NEL-STH-NSA-5200-CTW-REP-0001 | Design Report - B195 - Temporary SUP Package 3 (Koonung Ck Reserve West) | Design | Complete | Utility avoidance – 3D utilities model used in coordination with SUP design model to avoid risk of clashes and associated Fatal and Severe Risks (FSR’s) | FSR Utilities and Services FSR Excavation | Virtual clash detection identifies conflicts before breaking ground, preventing dangerous utility strikes and associated catastrophic injuries. | Update federated utility model. |  | Matthijs Klinkert
EBTA | EBTA363 | 2025-11-05 | NEL-STH-NSA-5113-SBR-REP-0001 | DESIGN REPORT - B056 – BR120 – THOMPSON ROAD TO NEL NORTHBOUND ENTRY RAMP | Methodology | Implemented | Construction staging implemented to separate works around live traffic with a temporary diversion of traffic at Thompsons Road and Bulleen Road to remove the risk in the area with the bridge deck complete prior to opening to traffic. | FSR Traffic Management | Completing the bridge deck offline eliminates the high-risk interface of heavy construction occurring overhead of live traffic, removing dropped object risks for the public. | Verify diversion setup. |  | Matthijs Klinkert
EBTA | EBTA364 | 2025-11-05 | NEL-STH-NSA-5113-SBR-REP-0001 | DESIGN REPORT - B056 – BR120 – THOMPSON ROAD TO NEL NORTHBOUND ENTRY RAMP | Methodology | Implemented | Construction staging has been investigated and will be implemented by the Worksite Traffic Management Plan to delineate and minimize the duration/extent of high-risk activities working near live traffic with proposed temporary barrier works and associated signage. | FSR Traffic Management | Physical separation via barriers and reduced exposure time significantly lowers the statistical likelihood of vehicle-worker collisions. | Audit barrier installation. |  | Matthijs Klinkert
EBTA | EBTA365 | 2025-11-05 | NEL-STH-NSA-5113-SBR-REP-0001 | DESIGN REPORT - B056 – BR120 – THOMPSON ROAD TO NEL NORTHBOUND ENTRY RAMP | Design | Implemented | Precast concrete piers and crossheads updated to insitu concrete removing transport, lifting and handling of precast concrete elements | FSR Cranes and Lifting FSR Plant and Equipment | Shifts construction methods to avoid high-risk heavy lifts of massive precast elements on public roads, reducing potential for crane failure or suspended load incidents. | Verify formwork design. |  | Matthijs Klinkert
EBTA | EBTA366 | 2025-11-05 | NEL-STH-NSA-5113-SBR-REP-0001 | DESIGN REPORT - B056 – BR120 – THOMPSON ROAD TO NEL NORTHBOUND ENTRY RAMP | Design | Implemented | SPARK Central Preliminary Design updated from fabricated steel super structure to precast concrete super structure reducing structure whole of life maintenance activities. | FSR Working at Heights FSR Traffic Management | Concrete requires significantly less maintenance than steel (e.g., painting/rust treatment), reducing future requirements for lane closures and working at heights. | Archive maintenance plan. |  | Matthijs Klinkert
EBTA | EBTA367 | 2025-11-05 | NEL-STH-NSA-5700-CRW-REP-0001 | DESIGN REPORT - B204 - ALIGNMENT AND CIVIL DESIGN | Methodology | Adopted | Removal of GPT to minimise excavation in asbestos containing spoil, deep excavation and confined space risks. Relevant FSRs: Excavation, Asbestos, Confined Space, Controls: Elimination | FSR Excavation FSR Asbestos FSR Confined Space | Removing the GPT from the design eliminates the need for deep excavations in asbestos-containing soil and removes the future risks associated with confined space entry for cleaning. | Verify drainage catchment update. |  | Matthijs Klinkert
EBTA | EBTA368 | 2025-11-05 | NEL-STH-NSA-5700-CRW-REP-0001 | DESIGN REPORT - B204 - ALIGNMENT AND CIVIL DESIGN | Material | Adopted - Flexible pipe extents are shown on the Drawings. | Maximise use of flexible pipe and investigate refinement of pipe sizes to reduce the material mass for transport and handling. Relevant FSRs: Cranes and Lifting Controls: Substitution | FSR Cranes and Lifting | Utilizing lighter flexible pipes instead of rigid concrete reduces the material mass for transport and installation, lowering the risk of manual handling injuries. | Approve refined pipe schedule. |  | Matthijs Klinkert
EBTA | EBTA369 | 2025-11-05 | NEL-STH-NSA-5700-CRW-REP-0001 | DESIGN REPORT - B204 - ALIGNMENT AND CIVIL DESIGN | Methodology | Adopted | Minimise works in high-risk areas including creeks. Works limited to drainage outlets to discharge to Koonung Creek. Therefore, minimise requirement for temporary works associated adjacent creek, and limit need for emergency plans to the area. Relevant FSRs: Work in, over or adjacent to water Controls: Eliminate (other than drainage discharge area) | FSR Work in, over or adjacent to water | Limiting the scope of works in the creek area minimizes the requirement for complex temporary works and reduces the need for emergency water rescue plans. | Verify outlet discharge points. |  | Matthijs Klinkert
EBTA | EBTA370 | 2025-11-05 | NEL-STH-NSA-5700-CRW-REP-0001 | DESIGN REPORT - B204 - ALIGNMENT AND CIVIL DESIGN | Design | Adopted | Impact attenuator and EABs proposed as mitigation for head on collision to protect columns within the bus interchange. Relevant FSRs: Traffic Management Controls: Engineering Controls | FSR Traffic Management | Strategic placement of EABs protects critical bridge infrastructure from head-on vehicle collisions, maintaining the safety of the structure and road users. | Verify barrier impact ratings. |  | Matthijs Klinkert
EBTA | EBTA371 | 2025-11-05 | NEL-STH-NSA-5306-SBS-REP-0001 | Design Report - B075 - BS301 - Estelle St Bridge | Methodology | Adopted | Provide bolted splice connections to remove the need for on-site welding. Detailed Design Update: Remove top bolted splice in pylon to reduce the need for site bolting - lift element in a single piece. | FSR Hot Works | Removing on-site welding eliminates fire risks, toxic fume exposure, and the need for specialized flash protection in active work zones. | Verify bolt torque specs. |  | Matthijs Klinkert
EBTA | EBTA372 | 2025-11-05 | NEL-STH-NSA-5306-SBS-REP-0001 | Design Report - B075 - BS301 - Estelle St Bridge | Modularisation | Adopted | Use precast panels with kerb to remove the need for cast in place deck formwork and volume of concrete cast at height. Relevant FSRs: Working at Heights. Controls: Engineering Controls. | FSR Cranes and Lifting FSR Working at Heights | Reducing the number of bolted connections at height minimizes the duration workers spend in elevated positions and reduces the number of critical lifts. | Approve single-piece lift plan. |  | Matthijs Klinkert
EBTA | EBTA373 | 2025-11-05 | NEL-STH-NSA-5306-SBS-REP-0001 | Design Report - B075 - BS301 - Estelle St Bridge | Modularisation | Adopted | Removing cantilever stages from stressing sequence for improved constructability, de-risking potentially wind sensitive stages. Furthermore, engaged the services of a Wind Consultant to de-risk any issues regarding aerodynamic instability. | FSR Working at Heights FSR Formwork & Falsework | Eliminates the high-risk task of erecting and stripping complex formwork at height and significantly reduces the volume of wet concrete handled at elevation. | Verify panel reinforcement. |  | Matthijs Klinkert
EBTA | EBTA374 | 2025-11-05 | NEL-STH-NSA-5306-SBS-REP-0001 | Design Report - B075 - BS301 - Estelle St Bridge | Design | Adopted | Updating pylon and plinth geometry to have a single plane slope to provide a safer and more constructable pylon. | FSR Formwork & Falsework | Simplifying the geometry allows for safer, more straightforward formwork assembly and reduces the likelihood of manual handling errors during construction. | Verify geometry on IFC drawings. |  | Matthijs Klinkert
EBTA | EBTA375 | 2025-11-05 | NEL-STH-NSA-5306-SBS-REP-0001 | Design Report - B075 - BS301 - Estelle St Bridge | Modularisation | Adopted | Majority of bridge furniture included in the module lift, minimising the number of elements required to be lifted and installed in place. | FSR Cranes and Lifting FSR Working at Heights | Installing furniture at ground level before lifting eliminates multiple high-risk installation tasks that would otherwise occur at height over live traffic. | Confirm furniture fixings. |  | Matthijs Klinkert
EBTA | EBTA376 | 2025-11-05 | NEL-STH-NSA-5306-SBS-REP-0001 | Design Report - B075 - BS301 - Estelle St Bridge | Design | Adopted | Lifting of south abutment pile cap to existing surface level to minimise deep excavation, thus minimising risk for falling from heights, need for temporary ground retention since it's shallow excavation. | FSR Excavation FSR Working at Heights | Raising the foundation to surface level eliminates the need for deep trenching and temporary ground retention, removing the risk of falls and soil collapse. | Verify pile cap level. |  | Matthijs Klinkert
EBTA | EBTA377 | 2025-11-05 | NEL-STH-NSA-5306-SBS-REP-0001 | Design Report - B075 - BS301 - Estelle St Bridge | Design | Adopted | Climbing deterrent measures implemented. Climbing deterrent plate included in Span 1 to mitigate access outside of the anti-throw screen. Infill screen provided at interface between Abutment B anti-throw screen and adjacent noise wall. Human factors assessment has been undertaken to implement anti-climb measures. | FSR Working at Heights | Deterrent plates and screens mitigate the risk of unauthorized access to the bridge exterior, preventing falls from height and objects being thrown onto the freeway. | Audit anti-climb plate installation. |  | Matthijs Klinkert
EBTA | EBTA378 | 2025-11-05 | NEL-STH-NSA-5306-SBS-REP-0001 | Design Report - B075 - BS301 - Estelle St Bridge | Management | Adopted | Develop highly detailed construction staging and lifting sequence to provide respective Contractor's ability to safely plan out associated works in a significant level of detail, thus minimising chance for errors in high risk work environment. This is especially important considering much of the activities are planned over the freeway (staging lane closures). | FSR Traffic Management FSR Cranes and Lifting | Detailed planning minimizes the chance for errors in high-risk environments involving lane closures, protecting both workers and the traveling public. | Review lifting sequence at DD stage. |  | Matthijs Klinkert
EBTA | EBTA379 | 2025-11-05 | NEL-STH-NSA-5306-SBS-REP-0001 | Design Report - B075 - BS301 - Estelle St Bridge | Design | Adopted | Integrating temporary works with permanent works designs, thus ensuring global and local capacity and stability checks have been accounted for. Clear load tables and diagrams are included primarily where elements are integral (i.e.. Plinth hob, welded lifting points, etc). | FSR Temporary Works | Including clear load tables and diagrams for integral elements (e.g., plinth hobs) ensures stability and prevents structural collapse during construction phases. | Verify integral element load tables. |  | Matthijs Klinkert
EBTA | EBTA380 | 2025-11-05 | NEL-STH-NSA-5306-SBS-REP-0001 | Design Report - B075 - BS301 - Estelle St Bridge | Methodology | Adopted | Pile reinforcement protruding straight without cogs to enable pile cropping or similar in lieu of manual jack hammering for pile break back. Manual jack hammering causes adverse harm to individual performing works, as well as creates significant dust and debris, of which pile cropping (or similar) alleviates. | FSR Plant and Equipment | Mechanical cropping eliminates the physical harm (Vibration White Finger) and respiratory risks (silica dust) associated with prolonged manual jackhammering. | Confirm pile reinforcement detail. |  | Matthijs Klinkert
EBTA | EBTA381 | 2025-11-05 | NEL-STH-NSA-5306-SBS-REP-0001 | Design Report - B075 - BS301 - Estelle St Bridge | Management | Adopted | Temporary support tower currently lands over the existing Melbourne Water culvert. This will be assessed via a load rating assessment which will be addressed through the temporary works package. Design Package B075 scope is permanent works only. Relevant FSRs: Utilities. Controls: Engineering Controls. | FSR Utilities and Services | Ensuring the existing culvert can support the temporary tower load prevents catastrophic asset failure and associated ground instability. | Finalise temporary works load assessment. |  | Matthijs Klinkert
EBTA | EBTA382 | 2025-11-05 | NEL-STH-NSA-5306-SBS-REP-0001 | Design Report - B075 - BS301 - Estelle St Bridge | Material | Adopted | Balustrade panel thickness reduced to minimum and has been panelised to allow for lighter weight manual installation and future removal for maintenance. Potential alternative lighter weight materials may also be considered in the next design stage, if sufficient. | FSR Cranes and Lifting | Lighter, panelised materials reduce the physical strain on workers during installation and future maintenance, lowering the risk of musculoskeletal injuries. | Investigate alternative lighter materials. |  | Matthijs Klinkert
EBTA | EBTA383 | 2025-11-05 | NEL-STH-NSA-5306-SBS-REP-0001 | Design Report - B075 - BS301 - Estelle St Bridge | Design | Adopted | Earthing and bonding lightning protection measures have been implemented in the design to reduce risk of electrocution of users in contact with the bridge during a lightning strike. | FSR General Electrical Safety | Proper bonding and earthing significantly reduce the risk of electrocution to bridge users in the event of a lightning strike. | Verify bonding points on site. |  | Matthijs Klinkert
EBTA | EBTA384 | 2025-11-05 | NEL-STH-NSA-5306-SBS-REP-0001 | Design Report - B075 - BS301 - Estelle St Bridge | Design | Adopted | Introduce a steel covering at the balustrades where future maintenance access is required (i.e. LUMS, junction boxes) to prevent dropping objects on live freeway during maintenances activities. | FSR Traffic Management | Prevents maintenance tools or debris from being dropped onto the live freeway below, protecting road users from potentially fatal impact incidents. | Verify covering installation. |  | Matthijs Klinkert
EBTA | EBTA385 | 2025-11-05 | NEL-STH-NSA-5300-CTW-REP-0001 | DESIGN REPORT - B196 - TEMPORARY SUP PACKAGE 4 (DONCASTER RESERVE) | Design | Complete | The design basis for the temporary SUPs is to use as much of the permanent SUP alignment and construction specification as possible so that there is an opportunity that the temporary works can be left in place and adopted as the permanent works. Hence eliminating the need to ‘build twice’. | FSR Traffic Management FSR Plant and Equipment | Eliminating redundant construction phases reduces the total time workers and machinery spend in high-risk zones, lowering the statistical likelihood of accidents. | Verify SUP construction specs. |  | Matthijs Klinkert
EBTA | EBTA386 | 2025-11-05 | NEL-STH-NSA-5300-CTW-REP-0001 | DESIGN REPORT - B196 - TEMPORARY SUP PACKAGE 4 (DONCASTER RESERVE) | Design | Complete | User safety – signs and lines to assist way-finding. Desirable grades with clearance to obstacles selected. | FSR Traffic Management | Proper way-finding and clear paths prevent user confusion and collisions between pedestrians and cyclists in shared public areas. | Finalize signage and line marking. |  | Matthijs Klinkert
EBTA | EBTA387 | 2025-11-05 | NEL-STH-NSA-5300-CTW-REP-0001 | DESIGN REPORT - B196 - TEMPORARY SUP PACKAGE 4 (DONCASTER RESERVE) | Design | Complete | Utility avoidance – 3D utilities model used in coordination with SUP design model to avoid risk of clashes and associated fatal and severe risks. | FSR Utilities and Services FSR Excavation | Identifying clashes virtually before construction prevents dangerous strikes on live underground assets, which can lead to fire, explosion, or electrocution. | Update federated utility model. |  | Matthijs Klinkert
EBTA | EBTA388 | 2025-11-05 | NEL-STH-NSA-5400-CUS-REP-0001 | Design Report - B126 - Utilities – Sewer S110, S112, & S113 | Design | Implemented | Elimination – S110 reticulation sewer alignment updated from PD to FD to eliminate high risk construction of building a new reticulation main in parallel to existing and close proximity to boundary fence. | FSR Utilities and Services FSR Excavation | Removing the requirement for construction in narrow, constrained corridors near existing assets reduces the risk of trench collapse and damage to third-party property. | Verify S110 alignment. |  | Matthijs Klinkert
EBTA | EBTA389 | 2025-11-05 | NEL-STH-NSA-5400-CUS-REP-0001 | Design Report - B126 - Utilities – Sewer S110, S112, & S113 | Design | Implemented | Elimination – S113 reticulation sewer alignment updated from TOC to FD to remove high risk construction of truncating a large diameter DN950 sewer main within the Valda Wetlands. | FSR Utilities and Services FSR Excavation | Avoiding complex modifications to large-diameter mains in environmentally sensitive areas eliminates high-risk manual tasks and potential sewage spills or structural failures. | Verify S113 design update. |  | Matthijs Klinkert
EBTA | EBTA390 | 2025-11-05 | NEL-STH-NSA-5400-CUS-REP-0001 | Design Report - B126 - Utilities – Sewer S110, S112, & S113 | Design | Implemented | Elimination - S113 GC MH truncated out of proposed inbound on ramp running lane and into a safe accessible location within the Valda Wetland. This improves access and maintainability of the existing asset as this GC is currently in the shoulder of the existing ramp. | FSR Traffic Management FSR Utilities and Services | Moving the asset from a high-traffic running lane to the wetland ensures maintenance crews can access and service the MH without exposure to live traffic. | Verify MH location on site. |  | Matthijs Klinkert
EBTA | EBTA391 | 2025-11-05 | NEL-STH-NSA-5500-CUW-REP-0001 | Design Report - B133 - UTILITIES – DONCASTER ROAD PRS W085 | Methodology | Implemented | Constructability – Moved water tie in point from centre of road to verge on timber ridge road to avoid clashes with proposed and existing utilities within the road. | FSR Utilities and Services FSR Excavation | Relocating the tie-in point avoids complex clashes with existing utilities in the road center, reducing the risk of accidental strikes during excavation. | Verify tie-in location. |  | Matthijs Klinkert
EBTA | EBTA392 | 2025-11-05 | NEL-STH-NSA-5500-CUW-REP-0001 | Design Report - B133 - UTILITIES – DONCASTER ROAD PRS W085 | Design | Implemented | Removal – removal of fence due location, noting fence may result in hazard/injury to public due to it being a highly trafficked area. | FSR Traffic Management | Eliminating the fence in a crowded area removes a potential tripping or impact hazard for the public in a busy environment. | Confirm fence removal scope. |  | Matthijs Klinkert
EBTA | EBTA393 | 2025-11-05 | NEL-STH-NSA-5500-CUW-REP-0001 | Design Report - B133 - UTILITIES – DONCASTER ROAD PRS W085 | Design | Implemented | Engineered Control – Use of acoustic panels within the slide rail cover to mitigate risk of noise exposure to local residents during operation of the PRV. | FSR Plant and Equipment | Reduces the high-decibel noise exposure for local residents and personnel during PRV operation, protecting long-term hearing health. | Verify acoustic panel specs. |  | Matthijs Klinkert
EBTA | EBTA394 | 2025-11-05 | NEL-STH-NSA-5500-CUW-REP-0001 | Design Report - B133 - UTILITIES – DONCASTER ROAD PRS W085 | Design | Implemented | Engineered Control – Adoption of lighter Pit lids for ease of Manual Handling, in non-trafficable areas. | FSR Plant and Equipment | Utilizing lighter materials significantly reduces the physical strain on workers and prevents musculoskeletal injuries during manual lifting for maintenance. | Confirm lid weight limits. |  | Matthijs Klinkert
EBTA | EBTA395 | 2025-11-05 | NEL-STH-NSA-5500-CUW-REP-0001 | Design Report - B133 - UTILITIES – DONCASTER ROAD PRS W085 | Design | Implemented | Engineered Control – Use of removable Safety Bollards to protect non-trafficable lids and stop unauthorised vehicle access. | FSR Traffic Management | Physically prevents unauthorized vehicles from driving over lids not designed for traffic loads, preventing structural failure and potential vehicle traps. | Finalize bollard placement. |  | Matthijs Klinkert
EBTA | EBTA396 | 2025-11-05 | NEL-STH-NSA-5500-CUW-REP-0001 | Design Report - B133 - UTILITIES – DONCASTER ROAD PRS W085 | Design | Implemented | Engineered Control – inclusion of Bollards to stop vehicle entry / egress onto PRS site. | FSR Traffic Management | Physical bollards prevent accidental vehicle impact with sensitive high-pressure equipment and protect maintenance personnel from errant vehicles while working on-site. | Finalize bollard placement. |  | Matthijs Klinkert
EBTA | EBTA397 | 2025-11-05 | NEL-STH-NSA-5500-CUW-REP-0001 | Design Report - B133 - UTILITIES – DONCASTER ROAD PRS W085 | Design | Implemented | Engineered Control – Hinged light poles specified to eliminate Working at height for flood light installation and maintenance. | FSR Working at Heights | Hinged poles allow the light fixture to be lowered to ground level for servicing, completely removing the requirement for workers to use ladders or elevated work platforms. | Verify pole specification. |  | Matthijs Klinkert
EBTA | EBTA398 | 2025-11-05 | NEL-STH-NSA-5500-CUW-REP-0001 | Design Report - B133 - UTILITIES – DONCASTER ROAD PRS W085 | Design | Implemented | Engineered Control – Rolling Cover to PRS specified to eliminate lifting during inspection and maintenance. | FSR Plant and Equipment | A rolling mechanism removes the high-risk manual handling task of lifting heavy access covers, preventing back injuries and finger entrapment/crush incidents. | Review cover design. |  | Matthijs Klinkert
EBTA | EBTA399 | 2025-11-05 | NEL-STH-NSA-5500-CUW-REP-0001 | Design Report - B133 - UTILITIES – DONCASTER ROAD PRS W085 | Design | Implemented | Engineered Control – PRV valves sited above ground to eliminate working within confined/restricted space for inspection, maintenance and operation. | FSR Confined Space | Placing valves above ground removes the risks of atmospheric hazards, engulfment, or difficult rescue associated with traditional underground valve pits. | Verify valve setout. |  | Matthijs Klinkert
EBTA | EBTA400 | 2025-11-05 | NEL-STH-NSA-5500-CUW-REP-0001 | Design Report - B133 - UTILITIES – DONCASTER ROAD PRS W085 | Design | Implemented | Engineered Control – PRS1 eliminates the requirement for a Potable Water trunk main connection across the Doncaster Rd Bridge, eliminating the need for working at heights along a significant length of bridge, potential for working/maintenance above traffic zones, maintenance restrictions along bridge and additional load cases required for bridge design. | FSR Working at Heights FSR Traffic Management | Eliminating the bridge-mounted pipe removes the risk of working at heights over traffic zones and simplifies future maintenance by removing bridge load and access restrictions. | Verify bridge design update. |  | Matthijs Klinkert
EBTA | EBTA401 | 2025-11-05 | NEL-STH-NSA-5200-ULS-REP-0001 | Design Report - B074 - 5100/5200 LANDSCAPING | Management | D | Cover to all overhead tanks to be mechanically fixed down. Fall from height/falling object from tank roofs | FSR Working at Heights | Secure mechanical fixings ensure covers cannot be dislodged by wind or pressure, protecting people below from falling objects and preventing open-hole fall hazards on the roof. | Inspect tank fixings. |  | Matthijs Klinkert
EBTA | EBTA402 | 2025-11-05 | NEL-STH-NSA-5200-ULS-REP-0001 | Design Report - B074 - 5100/5200 LANDSCAPING | Design | D | All openings in slabs or floors to be covered or barricaded as per standards to prevent falls through openings/shafts | FSR Working at Heights | Securely covering or barricading shafts and floor openings prevents personnel from accidentally falling through levels during construction and maintenance. | Inspect floor barricades. |  | Matthijs Klinkert
EBTA | EBTA403 | 2025-11-05 | NEL-STH-NSA-5200-ULS-REP-0001 | Design Report - B074 - 5100/5200 LANDSCAPING | Management | D | System to ensure emergency services access at all levels including podiums and basements | FSR Confined Space FSR Working at Heights | Providing clear, designated access for emergency responders ensures that injured personnel in complex or restricted areas can be reached and evacuated quickly. | Verify emergency access points. |  | Matthijs Klinkert
EBTA | EBTA404 | 2025-11-05 | NEL-STH-NSA-5200-ULS-REP-0001 | Design Report - B074 - 5100/5200 LANDSCAPING | Design | D | Appropriate protection to be installed at permanent edge conditions, e.g. parapets, balustrades etc. to ensure minimum 1.1m height and no opening greater than 100mm | FSR Working at Heights | Standard-compliant permanent barriers provide passive fall protection, ensuring maintenance workers are safe near edges without needing secondary harness systems. | Verify balustrade height. |  | Matthijs Klinkert
EBTA | EBTA405 | 2025-11-05 | NEL-STH-NSA-5200-ULS-REP-0001 | Design Report - B074 - 5100/5200 LANDSCAPING | Design | D | Design to include provision for fall arrest or fall restraint system for all permanent roof areas where regular access is required for maintenance | FSR Working at Heights | Implementing arrest systems ensures that if a fall occurs, the impact is absorbed and the worker is prevented from hitting the ground below. | Certify fall arrest anchors. |  | Matthijs Klinkert
EBTA | EBTA406 | 2025-11-05 | NEL-STH-NSA-5200-ULS-REP-0001 | Design Report - B074 - 5100/5200 LANDSCAPING | Design | D | Permanent anchor points to be provided for cleaning/maintenance at all locations where required by regulation or access constraints | FSR Working at Heights | Strategically placed, certified anchor points provide reliable tie-off locations for window cleaners and maintenance crews in difficult-to-access areas. | Audit anchor point locations. |  | Matthijs Klinkert
EBTA | EBTA407 | 2025-11-05 | NEL-STH-NSA-5200-ULS-REP-0001 | Design Report - B074 - 5100/5200 LANDSCAPING | Design | D | Access hatches to plant-room roofs and other locations to be self-closing and lockable from below | FSR Working at Heights | Self-closing mechanisms ensure that access points are not accidentally left open, removing the risk of workers falling back through the hatchway. | Verify hatch operation. |  | Matthijs Klinkert
EBTA | EBTA408 | 2025-11-05 | NEL-STH-NSA-5200-ULS-REP-0001 | Design Report - B074 - 5100/5200 LANDSCAPING | Design | D | Fire hydrant and booster locations to provide safe access/egress for fire brigade operations (min. 1.2m clear width) and set-down area identified for fire trucks | FSR Fire & Explosion | Providing adequate clearance and dedicated set-down areas ensures fire crews can operate equipment safely and efficiently during an emergency without obstruction. | Verify hydrant clearance on site. |  | Matthijs Klinkert
EBTA | EBTA409 | 2025-11-05 | NEL-STH-NSA-5200-ULS-REP-0001 | Design Report - B074 - 5100/5200 LANDSCAPING | Design | D | Access to BMU (Building Maintenance Unit) and cradle to be designed with adequate built-in handrails and guards, safe to use and as per manufacturer requirements | FSR Working at Heights | Built-in guards and handrails provide high-level passive protection for maintenance workers, preventing accidental falls from the BMU or cradle during facade works. | Review BMU safety certification. |  | Matthijs Klinkert
EBTA | EBTA410 | 2025-11-05 | NEL-STH-NSA-5200-ULS-REP-0001 | Design Report - B074 - 5100/5200 LANDSCAPING | Design | D | Provide protective barriers at the edge of all external stairs and ramps to comply with building code and standards regarding height and gap | FSR Working at Heights | Code-compliant barriers ensure that users of external stairs and ramps are protected from edge-fall hazards, specifically preventing children or small objects from slipping through gaps. | Verify barrier heights and gaps. |  | Matthijs Klinkert
EBTA | EBTA411 | 2025-11-05 | NEL-STH-NSA-5100-CRW-REP-0001 | DESIGN REPORT - B058 - 5100 - ALIGNMENT AND CIVIL ROAD DESIGN | Methodology | Implemented | Construction staging implemented to separate works around live traffic with a temporary diversion of traffic at Thompsons Road and Bulleen Road to remove the risk in the area with the bridge deck complete prior to opening to traffic. | FSR Traffic Management | Completing the bridge deck "offline" removes the high-risk interface where heavy construction occurs directly over active traffic lanes, protecting the public from dropped objects. | Verify diversion setup. |  | Matthijs Klinkert
EBTA | EBTA412 | 2025-11-05 | NEL-STH-NSA-5100-CRW-REP-0001 | DESIGN REPORT - B058 - 5100 - ALIGNMENT AND CIVIL ROAD DESIGN | Methodology | Implemented | Construction staging has been investigated and will be implemented by the Worksite Traffic Management Plan to delineate and minimize the duration/extent of high-risk activities working near live traffic with proposed temporary barrier works and associated signage. | FSR Traffic Management | Physical separation and minimized time in the "danger zone" significantly lower the statistical likelihood of vehicle-worker collisions. | Audit barrier installation. |  | Matthijs Klinkert
EBTA | EBTA413 | 2025-11-05 | NEL-STH-NSA-5100-CRW-REP-0001 | DESIGN REPORT - B058 - 5100 - ALIGNMENT AND CIVIL ROAD DESIGN | Design | Implemented | Provision of forward in and forward out maintenance access to the Busway pump station | FSR Traffic Management | Eliminating the need for maintenance vehicles to reverse into or out of the facility reduces the risk of collisions with pedestrians, other vehicles, or station infrastructure. | Verify swept path analysis. |  | Matthijs Klinkert
EBTA | EBTA414 | 2025-11-05 | NEL-STH-NSA-5300-CRF-REP-0001 | Design Report - B089 - 5300/5400/5500 - ITS and Comms (Cabling/Systems) | Design | Completed | ITS Roadside cabinet moved Off Freeway to SUP where possible to provide safety to maintenance person. Efforts were made to ensure cabinets were located behind noise walls where possible. E.g., Cabinet Behind Noise wall and retaining wall. (RGB-E-001, RGB-E-002, RGB-E-019, RGB-E-005, RCB-E-014-P, EAST-DB3, RCB-E006, EAST-DB5, RGB-E-008, RCB-E-015-P, RCB-E-016-P). Access to provide via SUP. A Maintenance Bay/vehicle hardstand have been provided to within 100m from ITS cabinets as per PRS requirement. This approach will minimize interactions with live traffic and to create safe work areas. | FSR Traffic Management | Moving assets away from the freeway allows maintenance personnel to work in areas protected by noise walls or distance, eliminating exposure to live traffic. | Verify cabinet locations behind walls. |  | Matthijs Klinkert
EBTA | EBTA415 | 2025-11-05 | NEL-STH-NSA-5300-CRF-REP-0001 | Design Report - B089 - 5300/5400/5500 - ITS and Comms (Cabling/Systems) | Design | Completed | Optimizing support infrastructure by grouping devices together to minimise services and to enable multiple devices to be accessed from a single point. Optimizing number pole by combining AP and RPT with CCTV. Combining PMC on CCTV pole. Shared distribution board cabinet for DTP ITS, Project Co ITS and DTP Lighting with separate metering systems e.g. East-DB1. | FSR Working at Heights FSR Plant and Equipment | Reducing the total number of poles across the project directly decreases the amount of high-risk installation and maintenance activities required at heights. | Finalize pole device layouts. |  | Matthijs Klinkert
EBTA | EBTA416 | 2025-11-05 | NEL-STH-NSA-5300-CRF-REP-0001 | Design Report - B089 - 5300/5400/5500 - ITS and Comms (Cabling/Systems) | Methodology | Completed | Prewiring of ITS Roadside cabinet and Pole mounted cabinet before installation off-site under a controlled environment. This will allow a secure and accessible location to be provided for pre-wired cabling (i.e., cables installed prior to gantry erection) to be connected to the wider cabling. This will eliminate risks associated with working; in challenging terrain, in extreme weather and in proximity to live traffic for this task. | FSR Working at Heights FSR Traffic Management | Shifting complex wiring tasks to a controlled environment eliminates the risks of working in challenging terrain, extreme weather, or near live traffic. | Inspect pre-wired units. |  | Matthijs Klinkert
EBTA | EBTA417 | 2025-11-05 | NEL-STH-NSA-5300-CRF-REP-0001 | Design Report - B089 - 5300/5400/5500 - ITS and Comms (Cabling/Systems) | Management | Completed | Installation of ITS devices during construction staging works behind the barriers and during day prior to traffic switch to avoid working next to live traffic and during night. | FSR Traffic Management | Scheduling high-precision tasks during the day and behind physical barriers avoids the increased risks of night works and proximity to live traffic lanes. | Review staging schedule. |  | Matthijs Klinkert
EBTA | EBTA418 | 2025-11-05 | NEL-STH-NSA-5300-CRF-REP-0001 | Design Report - B089 - 5300/5400/5500 - ITS and Comms (Cabling/Systems) | Methodology | Completed | Prewiring of gantry and attaching CCTV poles assembly before installation off-site under a controlled environment. This will eliminate risks associated with working; in challenging terrain, at heights/near free edges, in extreme weather and in proximity to live traffic for this task. LUMS signs installed on the ground before lifting. CCTV and VMS (Variable message sign) installed after. Gantry leg boxes before or after gantry lift. | FSR Working at Heights FSR Cranes and Lifting | Completing the majority of the assembly work on the ground removes the requirement for workers to be at height for extended periods over active traffic zones. | Verify lifting plan. |  | Matthijs Klinkert
EBTA | EBTA419 | 2025-11-05 | NEL-STH-NSA-5300-CRF-REP-0001 | Design Report - B089 - 5300/5400/5500 - ITS and Comms (Cabling/Systems) | Design | Completed | Design has proposed for conduits in Infill between Barriers and Noise wall reducing the need for trenching. | FSR Excavation | Placing conduits in the infill completely removes the requirement for traditional trenching, eliminating associated risks of ground collapse and utility strikes. | Verify infill design detail. |  | Matthijs Klinkert
EBTA | EBTA420 | 2025-11-05 | NEL-STH-NSA-5200-CUS-REP-0001 | DESIGN REPORT - B022 – UTILITIES – SEWER S064 | Management | Closed | Digital engineering tools (iTwin) have been used to avoid clashes with other design elements, avoiding the potential need for change during construction. | FSR Utilities and Services FSR Excavation | Virtual clash detection identifies conflicts before construction, preventing dangerous unplanned rework and accidental damage to live assets. | Generate clash report. |  | Matthijs Klinkert
EBTA | EBTA421 | 2025-11-05 | NEL-STH-NSA-5200-CUS-REP-0001 | DESIGN REPORT - B022 – UTILITIES – SEWER S064 | Design | Closed | Development of alignment and space-proofing designs undertaken with input from the USPs to ensure constructability and maintainability. | FSR Utilities and Services | Ensuring adequate space for assets from the design phase ensures that future maintenance can be performed with safe clearances and access. | Review USP feedback logs. |  | Matthijs Klinkert
EBTA | EBTA422 | 2025-11-05 | NEL-STH-NSA-5200-CUS-REP-0001 | DESIGN REPORT - B022 – UTILITIES – SEWER S064 | Methodology | Closed | Elimination and removal of walk-in structure extension as a result of ongoing discussions with Melbourne Water mitigating high risk trenchless construction across a live freeway. | FSR Traffic Management FSR Excavation | Removing this extension eliminates the requirement for high-risk trenchless construction (tunneling/boring) across a live freeway. | Verify asset owner agreement. |  | Matthijs Klinkert
EBTA | EBTA424 | 2025-11-05 | NEL-STH-NSA-5500-CTW-REP-0001 | DESIGN REPORT - DONCASTER STAGE D1.0 – TEMPORARY TRAFFIC SIGNALS | Management | To be commenced | Review of FSRs based on SiD register of prelim design to be undertaken by design and construction team. From this review, the team will decide which FSRs can be eliminated and mitigated by design or construction method. | FSR Chain of Responsibility | Collaborative reviews ensure that critical risks are identified early and either eliminated by design or mitigated by specific construction methods. | Document SiD review outcomes. |  | Matthijs Klinkert
EBTA | EBTA425 | 2025-11-05 | NEL-STH-NSA-5500-CTW-REP-0001 | DESIGN REPORT - DONCASTER STAGE D1.0 – TEMPORARY TRAFFIC SIGNALS | Design | To be commenced | 4D model to be used as a communication and planning tool to ensure right first time build | FSR Chain of Responsibility | Using a shared digital tool ensures all teams have identical information, preventing the high-risk unplanned rework and field-level clashes that often lead to accidents. | Verify model coordination. |  | Matthijs Klinkert
EBTA | EBTA426 | 2025-11-05 | NEL-STH-NSA-5500-CTW-REP-0001 | DESIGN REPORT - DONCASTER STAGE D1.0 – TEMPORARY TRAFFIC SIGNALS | Design | Ongoing | Potential to omit ramp T1 (or make single bus lane) being investigated. On-going investigation with Traffic Modelling team | FSR Traffic Management | Omitting a ramp entirely removes a major permanent vehicle conflict point, significantly reducing the long-term risk of collisions between buses and other road users. | Review traffic model report. |  | Matthijs Klinkert
EBTA | EBTA427 | 2025-11-05 | NEL-STH-NSA-5300-CUW-REP-0001 | Design Report - YVW / MW - WATER - Estelle Street - W080 & W081 | Design | Implemented | Estelle Steet shared use path bridge has been re-orientated, Eastern Freeway levels raised, and bridging structures provided over existing watermains to remove direct need for immediate replacement of the existing watermains and ensure existing watermains will be operational during the interface construction works. | FSR Utilities and Services FSR Excavation | Bridging over the assets eliminates the requirement for deep, high-risk excavations to replace live watermains, protecting the workforce and asset integrity. | Verify bridge clearance. |  | Matthijs Klinkert
EBTA | EBTA428 | 2025-11-05 | NEL-STH-NSA-5300-CUW-REP-0001 | Design Report - YVW / MW - WATER - Estelle Street - W080 & W081 | Design | Implemented | Provision of sleeves in consideration of future pipe renewals or slip lining of the watermains. | FSR Utilities and Services | Providing sleeves allows for future repairs to be conducted without major excavation, reducing the risk profile for future maintenance crews. | Confirm sleeve locations. |  | Matthijs Klinkert
EBTA | EBTA429 | 2025-11-05 | NEL-STH-NSA-5300-CUW-REP-0001 | Design Report - YVW / MW - WATER - Estelle Street - W080 & W081 | Methodology | Implemented | Use of Sintalock Type 1 MSCL pipe joints mitigated the requirement of internal pipe welding, and testing of joints can be completed onsite prior to insertion of carrier pipes through the RC sleeves under Eastern Freeway. | FSR Confined Space | Using mechanical joints instead of welding completely removes fire risks and toxic fume hazards from the construction site and eliminates the need for entry into confined spaces for internal welding. | Verify joint testing results. |  | Matthijs Klinkert
EBTA | EBTA430 | 2025-11-05 | NEL-STH-NSA-5300-CUW-REP-0001 | Design Report - YVW / MW - WATER - Estelle Street - W080 & W081 | Methodology | Implemented | Provision of grated discharge pit for scouring of watermains adjacent to SUP considered the accessibility and feasibility for maintenance crew to safely conduct a visual check and a submersible dewatering pump, if required, to pump-out the residual water inside the discharge pit to the nearest stormwater drainage pit via a lay-flat flexible hose. | FSR Utilities and Services | Testing joints before insertion ensures the system is sound before being placed in inaccessible locations, preventing future leaks that could lead to ground instability under the freeway. | Review pipe QA records. |  | Matthijs Klinkert
EBTA | EBTA431 | 2025-11-05 | NEL-STH-NSA-5300-CUW-REP-0001 | Design Report - YVW / MW - WATER - Estelle Street - W080 & W081 | Design | Implemented | Watermain has been lifted to minimum cover to minimise excavation depths and minimise impacts to road users due to traffic disruptions. | FSR Excavation FSR Traffic Management | Raising the asset reduces the depth of trenching required, lowering the risk of soil collapse and reducing the time workers spend in excavations near live traffic. | Verify minimum cover compliance. |  | Matthijs Klinkert
EBTA | EBTA432 | 2025-11-05 | NEL-STH-NSA-5406-SBS-REP-0001 | DESIGN REPORT - B092 - BS401 HEYINGTON AVENUE SUP BRIDGE | Methodology | Adopted | Provide bolted splice connections to remove the need for on-site welding. Relevant FSRs: N/A Controls: Engineering Controls | NA | Using mechanical bolts instead of welding eliminates fire risks and toxic fume exposure in the field, simplifying the connection process. | Verify bolt torque specifications. |  | Matthijs Klinkert
EBTA | EBTA433 | 2025-11-05 | NEL-STH-NSA-5406-SBS-REP-0001 | DESIGN REPORT - B092 - BS401 HEYINGTON AVENUE SUP BRIDGE | Modularisation | Adopted | Use permanent formwork with panels kerb to remove the need for cast in place deck form, while minimising mass for major bridge lift. Furthermore, utilise light weight GRP deck form such as Permadec in lieu of Transfloor. Reduce risk level for lifting precast deck panels. Relevant FSRs: Cranes and Lifting Controls: Engineering Controls | FSR Cranes and Lifting | Reducing the dead weight of the bridge panels lowers the risk level for critical lifts and reduces the strain on lifting equipment. | Confirm GRP material supply. |  | Matthijs Klinkert
EBTA | EBTA434 | 2025-11-05 | NEL-STH-NSA-5406-SBS-REP-0001 | DESIGN REPORT - B092 - BS401 HEYINGTON AVENUE SUP BRIDGE | Modularisation | Adopted | Majority of bridge works and bridge furniture included in the module lift, minimising the number of elements required to be lifted and installed over the freeway. Reduces risk of working from heights, and allows more work to be done in a controlled environment, offline. Relevant FSRs: Cranes and Lifting, Working at Heights Controls: Engineering Controls | FSR Cranes and Lifting FSR Working at Heights | Pre-assembling components offline allows more work to be done in a controlled environment, significantly reducing the duration of high-risk work at heights over live traffic. | Verify integrated lift plan. |  | Matthijs Klinkert
EBTA | EBTA435 | 2025-11-05 | NEL-STH-NSA-5406-SBS-REP-0001 | DESIGN REPORT - B092 - BS401 HEYINGTON AVENUE SUP BRIDGE | Design | Adopted | Lifting of north abutment pile cap to FSL to minimise deep excavation, thus minimising risk the need for falling from heights, need for temporary ground retention since it's shallow excavation. Relevant FSRs: Excavation Controls: Engineering Controls | FSR Excavation | Elevating the foundation removes the need for deep trenching and temporary ground retention, eliminating associated fall risks and ground instability. | Verify pile cap FSL. |  | Matthijs Klinkert
EBTA | EBTA436 | 2025-11-05 | NEL-STH-NSA-5406-SBS-REP-0001 | DESIGN REPORT - B092 - BS401 HEYINGTON AVENUE SUP BRIDGE | Design | Adopted | Anti-climb prevention measures implemented for the length of the bridge and at the approaches such as fencing adjacent the approach on the north end as well as anti-throw screens for areas over the freeway. Relevant FSRs: N/A - Operation Controls: Engineering Controls | NA | Deterrent fencing and screens prevent unauthorized access to bridge edges and stop objects from being thrown onto the freeway below, protecting both pedestrians and motorists. | Inspect screen fixings. |  | Matthijs Klinkert
EBTA | EBTA437 | 2025-11-05 | NEL-STH-NSA-5406-SBS-REP-0001 | DESIGN REPORT - B092 - BS401 HEYINGTON AVENUE SUP BRIDGE | Management | Adopted | Develop highly detailed construction staging and lifting sequence to provide respective Contractor's ability to safely plan out associated works in a significant level of detail, thus minimising chance for errors in high risk work environment. This is especially important considering much of the activities are planned over the freeway (staging lane closures). Relevant FSRs: Cranes and Lifting, Traffic Management Controls: Administrative Controls | FSR Cranes and Lifting FSR Traffic Management | Detailed planning minimizes the chance for errors during complex activities over the freeway, protecting both workers and the public. | Review staging lane closures. |  | Matthijs Klinkert
EBTA | EBTA438 | 2025-11-05 | NEL-STH-NSA-5406-SBS-REP-0001 | DESIGN REPORT - B092 - BS401 HEYINGTON AVENUE SUP BRIDGE | Methodology | Adopted | Integrating temporary works with permanent works designs, thus ensuring global and local capacity and stability checks have been accounted for in a single design package. Clear load tables and diagrams are included primarily where elements are integral (ie. welded lifting points, temporary bracing elements, etc). Relevant FSRs: Cranes and Lifting Controls: Engineering Controls | FSR Cranes and Lifting | Clear load tables and diagrams for integral elements (e.g., welded lifting points) ensure that the structures remain stable during all phases of construction. | Verify integral element load tables. |  | Matthijs Klinkert
EBTA | EBTA439 | 2025-11-05 | NEL-STH-NSA-5406-SBS-REP-0001 | DESIGN REPORT - B092 - BS401 HEYINGTON AVENUE SUP BRIDGE | Methodology | Adopted | Pile reinforcement protruding straight without cogs to enable pile cropping or similar in lieu of manual jack hammering for pile break back. Manual jack hammering causes adverse harm to individual performing works, as well as creates significant dust and debris, of which pile cropping (or similar) alleviates. Relevant FSRs: Demolition Controls: Engineering Controls | FSR Demolition | Mechanical cropping eliminates the physical harm (vibration/strain) and significant dust and debris associated with prolonged manual jackhammering. | Confirm pile reinforcement detail. |  | Matthijs Klinkert
EBTA | EBTA440 | 2025-11-05 | NEL-STH-NSA-5406-SBS-REP-0001 | DESIGN REPORT - B092 - BS401 HEYINGTON AVENUE SUP BRIDGE | Material | Adopted | Balustrade panel thickness reduced to minimum and has been panelised to allow for lighter weight manual installation and future removal for maintenance. Potential alternative lighter weight materials may also being considered in the next design stage, if sufficient. Relevant FSRs: Cranes and Lifting Controls: Engineering Controls | FSR Cranes and Lifting | Lighter panels reduce the manual handling burden on workers, lowering the risk of musculoskeletal injuries during installation and maintenance. | Investigate alternative lighter materials. |  | Matthijs Klinkert
EBTA | EBTA441 | 2025-11-05 | NEL-STH-NSA-5406-SBS-REP-0001 | DESIGN REPORT - B092 - BS401 HEYINGTON AVENUE SUP BRIDGE | Design | Adopted | Earthing and Bonding lighting protection measures have been implemented in the design to reduce risk of electrocution of users in contact with the bridge during a lightning strike. Relevant FSRs: N/A Controls: Engineering Controls | NA | Proper bonding reduces the risk of electrocution for users in contact with the bridge during a lightning strike. | Verify bonding points on site. |  | Matthijs Klinkert
EBTA | EBTA442 | 2025-11-05 | NEL-STH-NSA-5406-SBS-REP-0001 | DESIGN REPORT - B092 - BS401 HEYINGTON AVENUE SUP BRIDGE | Design | Adopted | Introduce a steel covering at the balustrades where future maintenance access is required (ie. LUMS, JB's) to prevent dropping objects on live freeway during maintenances activities. Relevant FSRs: N/A - Operation & Maintenance Controls: Engineering Controls | NA | Prevents maintenance tools or debris from being dropped onto the live freeway below, protecting motorists from potentially fatal impacts. | Finalize maintenance access detail. |  | Matthijs Klinkert
EBTA | EBTA443 | 2025-11-05 | NEL-STH-NSA-5406-SBS-REP-0001 | DESIGN REPORT - B092 - BS401 HEYINGTON AVENUE SUP BRIDGE | Design | Adopted | Alignment has shifted to avoid existing sewer asset and to provide minimum clearance to respective asset. Reduces risk of striking major sewer line. Relevant FSRs: Utilities Controls: Engineering Controls | FSR Utilities and Services | Strategic realignment significantly reduces the risk of striking high-capacity sewer lines during foundation works, preventing environmental contamination and ground instability. | Verify minimum clearance on site. |  | Matthijs Klinkert
EBTA | EBTA444 | 2025-11-05 | NEL-STH-NSA-5117-SBR-REP-0001 | Design Report – B049 – BR105 - BULLEEN ROAD BRIDGE | Design | Implemented | Central Pier diaphragm in the widened structure has been optimised through design development and reduced to 4.0m to enable super t girders to be supported on temporary towers and cast insitu concrete diaphragm behind temporary barriers in the median avoiding works for this element over live traffic. | FSR Traffic Management | Designing for in-situ diaphragm casting behind physical barriers avoids high-risk heavy construction activities occurring directly over live freeway traffic. | Verify barrier setout in median. |  | Matthijs Klinkert
EBTA | EBTA445 | 2025-11-05 | NEL-STH-NSA-5117-SBR-REP-0001 | Design Report – B049 – BR105 - BULLEEN ROAD BRIDGE | Methodology | Implemented | West bridge barrier retained to avoid working at height, working and lifting over live traffic. | FSR Working at Heights FSR Traffic Management | Retaining the existing structure eliminates the need for workers to perform demolition and lifting tasks at height directly over active traffic lanes. | Confirm barrier condition. |  | Matthijs Klinkert
EBTA | EBTA446 | 2025-11-05 | NEL-STH-NSA-5117-SBR-REP-0001 | Design Report – B049 – BR105 - BULLEEN ROAD BRIDGE | Methodology | Implemented | Construction staging implemented to separate works amongst live by widening the structure, switching traffic onto widened structure and strengthening section of bridge. | FSR Traffic Management | Creating physical distance between the work zone and motorists through strategic traffic switches lowers the statistical likelihood of vehicle-worker collisions. | Verify traffic switch plan. |  | Matthijs Klinkert
EBTA | EBTA447 | 2025-11-05 | NEL-STH-NSA-5117-SBR-REP-0001 | Design Report – B049 – BR105 - BULLEEN ROAD BRIDGE | Design | Implemented | Halving joint bearings underneath approach slab removed at both new and existing bridge under post IFC DCN-000017 eliminating the need for future inspection access within constrained area. | FSR Confined Space | Removing these bearings completely eliminates the need for future maintenance personnel to enter highly constrained areas for inspections. | Verify post-IFC DCN-000017. |  | Matthijs Klinkert
EBTA | EBTA448 | 2025-11-05 | NEL-STH-NSA-5117-SBR-REP-0001 | Design Report – B049 – BR105 - BULLEEN ROAD BRIDGE | Methodology | Implemented | Vertical post tensioned stress bars method for shear strengthening changed to an alternate strengthening method with web concrete thickening via drill and fix reinforcing bars into existing webs eliminating the hazards for drilling operation and working from soffit over the Eastern Freeway. | FSR Working at Heights FSR Traffic Management | Eliminates high-risk drilling operations and manual handling tasks that would otherwise occur from the bridge soffit directly over the Eastern Freeway. | Verify web thickening detail. |  | Matthijs Klinkert
EBTA | EBTA449 | 2025-11-05 | NEL-STH-NSA-5100-SFW-REP-0001 | DESIGN REPORT - B061 – 5100 FLOOD WALLS | Modularisation | Implemented | Optimising frequency of lifts in precast design – precast units were designed to a maximum of 20t to optimise the frequency of lifting of heavy units. The double-sided architectural finish for these panels are intended to be precast as part of the primary units to avoid further lifting post-installation. | FSR Cranes and Lifting | Limiting unit weight and including finishes in the primary pour reduces the total number of critical lifts and eliminates the need for post-installation lifting at height. | Verify unit weight schedule. |  | Matthijs Klinkert
EBTA | EBTA450 | 2025-11-05 | NEL-STH-NSA-5100-SFW-REP-0001 | DESIGN REPORT - B061 – 5100 FLOOD WALLS | Design | Implemented | Prioritising Alternative Flood Mitigation Solutions – where possible, the design team has pushed for alternative means of flood mitigation via earthworks or integration as part of other structures to reduce amount of works as part of B061. This has been resulted in omission of SFW 005, 006 & 007. | FSR Excavation | Using earthworks instead of structural units eliminates the deep excavation and heavy lifting risks associated with installing dedicated flood mitigation assets. | Confirm omission of SFW 005/006/007. |  | Matthijs Klinkert
EBTA | EBTA451 | 2025-11-05 | NEL-STH-NSA-5400-CTW-REP-0001 | DESIGN REPORT - B192 – TEMPORARY SUP PACKAGE 2 (VALDA WETLANDS) | Design | Complete | The design basis for the temporary SUPs is to use as much of the permanent SUP alignment and construction specification as possible so that there is an opportunity that the temporary works can be left in place and adopted as the permanent works. Hence eliminating the need to 'build twice'. | FSR Traffic Management | Eliminating the "build twice" requirement reduces the total time construction plant and workers are active in public zones, lowering the risk of accidents. | Verify SUP construction specs. |  | Matthijs Klinkert
EBTA | EBTA452 | 2025-11-05 | NEL-STH-NSA-5400-CTW-REP-0001 | DESIGN REPORT - B192 – TEMPORARY SUP PACKAGE 2 (VALDA WETLANDS) | Design | Complete | User safety – signs and lines to assist way-finding. Desirable grades with clearance to obstacles selected. | FSR Traffic Management | Clear delineation and compliant grades prevent user confusion and collisions between pedestrians and cyclists in public areas. | Finalize signage and line marking. |  | Matthijs Klinkert
EBTA | EBTA453 | 2025-11-05 | NEL-STH-NSA-5400-CTW-REP-0001 | DESIGN REPORT - B192 – TEMPORARY SUP PACKAGE 2 (VALDA WETLANDS) | Digital | Complete | Utility avoidance – 3D utilities model used in coordination with SUP design model to avoid risk of clashes and associated fatal and severe risks. | FSR Utilities and Services FSR Excavation | virtual clash detection identifies conflicts before breaking ground, preventing dangerous utility strikes and potential fire, explosion, or electrocution. | Update federated utility model. |  | Matthijs Klinkert
EBTA | EBTA454 | 2025-11-05 | NEL-STH-NSA-5300-CUS-REP-0001 | Design Report - B025 - Utilities – Sewer S074, S079, S081, S082, S083, S086, S087, S088, S090 & S092 | Modularisation | Implemented | Introduction of GRP factory formed maintenance structure to reduce working time at depth and in confined space | FSR Confined Space FSR Excavation | Using lightweight, pre-formed structures allows for rapid installation, significantly reducing the duration workers spend in deep excavations and confined spaces. | Verify GRP structure dimensions. |  | Matthijs Klinkert
EBTA | EBTA455 | 2025-11-05 | NEL-STH-NSA-5300-CUS-REP-0001 | Design Report - B025 - Utilities – Sewer S074, S079, S081, S082, S083, S086, S087, S088, S090 & S092 | Methodology | Implemented | Adoption of pipe jacking installation technique to reduce the areas of open trenching minimising hazards to road users, pedestrians, local residents, and construction workers. Pipe jacking also reduces the risks of trench collapse and requirement of traffic management | FSR Excavation FSR Traffic Management | Minimizes the risk of trench collapse and significantly reduces the need for complex traffic management, protecting road users, pedestrians, and workers. | Verify pipe jacking alignment. |  | Matthijs Klinkert
EBTA | EBTA456 | 2025-11-05 | NEL-STH-NSA-5100-CRF-REP-0001 | DESIGN REPORT - B071 – 5100/5200 ITS AND COMMS (CABLING/SYSTEMS) | Design | Completed | ITS Roadside cabinet moved Off Freeway to SUP where possible to provide safety to maintenance person. Efforts were made to ensure cabinets were located behind noise walls where possible. Access to provide via SUP. A Maintenance Bay/vehicle hardstand have been provided to within 100m from ITS cabinets as per PRS requirement. This approach will minimize interactions with live traffic and to create safe work areas. | FSR Traffic Management | Moving assets away from the freeway allows maintenance personnel to work in protected areas with a dedicated hardstand, eliminating exposure to live traffic. | Verify cabinet locations. |  | Matthijs Klinkert
EBTA | EBTA457 | 2025-11-05 | NEL-STH-NSA-5100-CRF-REP-0001 | DESIGN REPORT - B071 – 5100/5200 ITS AND COMMS (CABLING/SYSTEMS) | Design | Completed | Optimizing support infrastructure by grouping devices together to minimise services and to enable multiple devices to be accessed from a single point. Includes optimizing number pole by combining AP and RPT with CCTV, Combining PMC on CCTV pole, Mounting LUMS onto SUP bridge BS106. Type 4 allows supplying both DTP ITS, Project Co ITS and DTP Lighting with separate metering systems E.g., West DB6. | FSR Working at Heights FSR Plant and Equipment | Minimizing the total number of support structures across the project directly reduces the amount of high-risk installation and maintenance activities required at heights. | Finalize pole device layouts. |  | Matthijs Klinkert
EBTA | EBTA458 | 2025-11-05 | NEL-STH-NSA-5100-CRF-REP-0001 | DESIGN REPORT - B071 – 5100/5200 ITS AND COMMS (CABLING/SYSTEMS) | Methodology | Completed | Design is to support prewiring of ITS Roadside cabinet and Pole mounted cabinet before installation off-site under a controlled environment. This will allow a secure and accessible location for pre-wired cabling to be connected to the wider cabling. Will eliminate risks associated with working in challenging terrain, in extreme weather and in proximity to live traffic for this task. | FSR Working at Heights FSR Traffic Management | Shifting complex wiring tasks to a controlled environment eliminates risks associated with challenging terrain, extreme weather, and proximity to live traffic. | Inspect pre-wired units. |  | Matthijs Klinkert
EBTA | EBTA459 | 2025-11-05 | NEL-STH-NSA-5100-CRF-REP-0001 | DESIGN REPORT - B071 – 5100/5200 ITS AND COMMS (CABLING/SYSTEMS) | Management | Completed | Design is to support installation of ITS devices during construction staging works behind the barriers and during day prior to traffic switch to avoid working next to life traffic and during night. | FSR Traffic Management | Scheduling high-precision tasks during the day and behind physical barriers avoids the increased risks of night works and working directly next to live traffic. | Review staging schedule. |  | Matthijs Klinkert
EBTA | EBTA460 | 2025-11-05 | NEL-STH-NSA-5100-CRF-REP-0001 | DESIGN REPORT - B071 – 5100/5200 ITS AND COMMS (CABLING/SYSTEMS) | Design | Completed | Design has proposed for conduits in Infill between Barriers and Noise wall reducing the need for trenching. | FSR Excavation | Placing conduits in the infill reduces the requirement for traditional trenching, eliminating associated risks of ground collapse and utility strikes | Verify infill design detail. |  | Matthijs Klinkert
EBTA | EBTA461 | 2025-11-05 | NEL-STH-NSA-5100-CUW-REP-0001 | Design Report - U003 - YVW - WATER - BULLEEN INTERCHANGE - W069, W077,078 | Design | Implemented – Closed | Placement of proposed main and appurtenances in accessible areas outside of SUP where possible in consideration of future maintenance and replacement | FSR Utilities and Services | Placing assets outside the SUP ensures that future maintenance and replacement activities can be conducted without obstructing public thoroughfares or putting workers in confined path zones. | Verify asset setout. |  | Matthijs Klinkert
EBTA | EBTA462 | 2025-11-05 | NEL-STH-NSA-5100-CUW-REP-0001 | Design Report - U003 - YVW - WATER - BULLEEN INTERCHANGE - W069, W077,078 | Design | Implemented – Closed | Space provision for water main thrust restraints | FSR Utilities and Services | Mechanical thrust restraints prevent pipe movement and joint failure under pressure, eliminating the risk of catastrophic water bursts and associated ground instability. | Verify restraint design. |  | Matthijs Klinkert
EBTA | EBTA463 | 2025-11-05 | NEL-STH-NSA-5100-CUW-REP-0001 | Design Report - U003 - YVW - WATER - BULLEEN INTERCHANGE - W069, W077,078 | Design | Implemented – Closed | Permanent water main to maintain sufficient clearances to existing and proposed services including electricity poles in accordance with MRWA guidelines and respective utility asset owners’ guidelines | FSR Utilities and Services | Maintaining strict clearances as per MRWA and utility owner guidelines prevents accidental strikes and dangerous interactions (e.g., arcing) with third-party assets. | Audit service clearances. |  | Matthijs Klinkert
EBTA | EBTA464 | 2025-11-05 | NEL-STH-NSA-5100-CUW-REP-0001 | Design Report - U003 - YVW - WATER - BULLEEN INTERCHANGE - W069, W077,078 | Design | Implemented – Closed | Incorporation of new valves at either end of the new works to assist with isolation, testing and commissioning process | FSR Utilities and Services | Strategically placed valves allow for safe, localized isolation of the system during testing and commissioning, preventing uncontrolled pressure releases. | Confirm valve locations. |  | Matthijs Klinkert
EBTA | EBTA465 | 2025-11-05 | NEL-STH-NSA-5100-CTW-REP-0016 | DESIGN REPORT - E018-5100-0016 - BULLEEN STAGE B3.1a TEMPORARY TRAFFIC SIGNALS (SITE 2827) | Management |  | Section 9 'Safety in Design' describes the Safety in Design (SiD) process: SiD workshops are undertaken for civil 2D alignment throughout detailed design. SiD risks, mitigation, residual risks, and risk owners are identified and captured for all packages with registers included in the design report. Temporary works and constructability are considered during the design process, with formal/informal meetings, design review, and input from BTA and VicRoads for road safety. Outcomes from SiD reviews will be documented in the design report if applicable. There is no specific table with the columns 'Number', 'Item', 'Status', and 'Design Stage' for engineered safety methods on these pages. | FSR Chain of Responsibility | Collaborative workshops ensure that risks are identified early and captured in design reports, allowing for engineering controls to be implemented before construction begins. | Document SiD review outcomes. |  | Matthijs Klinkert
EBTA | EBTA466 | 2025-11-05 | NEL-STH-NSA-5300-CRW-REP-0001 | Design Report - B076 – 5300 Alignment and Civils | Methodology | Adopted | Shifting retaining wall south at Ramp D3 and Ramp D4 to allow earlier and safer working with for mainline construction. Relevant FSRs: Excavation, Traffic Management. Controls: Engineering Controls | FSR Excavation FSR Traffic Management | Shifting the wall creates a larger work zone, allowing construction to occur earlier and with greater separation from live traffic, reducing the risk of vehicle-person strikes. | Verify wall alignment. |  | Matthijs Klinkert
EBTA | EBTA467 | 2025-11-05 | NEL-STH-NSA-5300-CRW-REP-0001 | Design Report - B076 – 5300 Alignment and Civils | Design | Adopted | Shifting streetlight poles from Ramp D3 and Ramp D4 verge levels down to mainline level to provide maintenance for streetlight pole's base plate connections and maximising offset for personnel working adjacent to a live traffic. Relevant FSRs: N/A. Controls: Engineering Controls | FSR Traffic Management | Relocating the base plate connections to the mainline level maximizes the offset for personnel, allowing them to perform maintenance entirely away from active ramp traffic. | Verify pole base connections. |  | Matthijs Klinkert
EBTA | EBTA468 | 2025-11-05 | NEL-STH-NSA-5300-CRW-REP-0001 | Design Report - B076 – 5300 Alignment and Civils | Design | Adopted | Construction of pavements and infill over existing BEBO structures – design checks and load rating assessments have been initiated (via design packages B102 and B103) to ensure various plant, equipment and haul roads etc. can be constructed without impacting the existing structure. Relevant FSRs: Plant, Cranes and Lifting. Controls: Engineering Controls | FSR Plant and Equipment FSR Cranes and Lifting | Rigorous load assessments ensure that heavy plant, equipment, and haul roads can operate over the structure without causing a catastrophic collapse. | Review B102 and B103 packages. |  | Matthijs Klinkert
EBTA | EBTA469 | 2025-11-05 | NEL-STH-NSA-5300-CRW-REP-0001 | Design Report - B076 – 5300 Alignment and Civils | Design | Adopted | Construction of drainage blanket at Doncaster Busway to mitigate future groundwater heave over FSL. Design details considered reducing construction duration for drainage blanket to minimise risk of groundwater heave during construction activity and dewatering requirements (risk of dewatering contaminated water). Relevant FSRs: Dewatering. Controls: Engineering Controls | FSR Work On, Over Or Adjacent to Water | Reducing construction duration for the blanket minimizes the requirement for prolonged dewatering and the associated risk of handling contaminated groundwater. | Verify drainage blanket detail. |  | Matthijs Klinkert
EBTA | EBTA470 | 2025-11-05 | NEL-STH-NSA-5300-CRW-REP-0001 | Design Report - B076 – 5300 Alignment and Civils | Design | Adopted | Design and consideration of heavy plant adjacent steep batters or existing/new retention systems. New slopes maintained at 3:1 maximum slopes in B076 design package. The design package has also considered construction staging (i.e. demolition sequence of existing structures, new retaining walls being constructed prior to mainline works etc) in the earthworks design. Details of this are captured in separate temporary works and permanent works design packages. Relevant FSRs: Excavation, Traffic Management. Controls: Engineering Controls | FSR Excavation FSR Traffic Management | Standardizing slopes at 3:1 ensures the stability of the ground for heavy machinery and reduces the risk of landslides or trench failure during staging. | Review B076 design package. |  | Matthijs Klinkert
EBTA | EBTA471 | 2025-11-05 | NEL-STH-NSA-5700-ULS-REP-0001 | DESIGN PACKAGE REPORT - B205 - LANDSCAPING ARCHITECTURE | [7 empty] | Matthijs Klinkert
EBTA | EBTA472 | 2025-11-05 | NEL-STH-NSA-5112-SBR-REP-0001 | Design Report - B055 - BR119 - SB NEL to Thompsons Rd Structure | Methodology | Implemented | Construction staging has been investigated and will be implemented by the Worksite Traffic Management Plan to delineate and minimize the duration/extent of high-risk activities working near live traffic with proposed temporary barrier works and associated signage. | FSR Traffic Management | Physical delineation and strategic staging significantly lower the statistical likelihood of vehicle-worker collisions in high-traffic zones. | Audit temporary barrier works. |  | Matthijs Klinkert
EBTA | EBTA473 | 2025-11-05 | NEL-STH-NSA-5112-SBR-REP-0001 | Design Report - B055 - BR119 - SB NEL to Thompsons Rd Structure | Design | Implemented | SPARK Central Preliminary Design updated from fabricated steel super structure to precast concrete super structure reducing structure whole of life maintenance activities. | FSR Working at Heights FSR Traffic Management | Concrete requires significantly less frequent maintenance than steel, reducing the future need for workers to access the bridge soffit at height over live traffic. | Archive maintenance schedule. |  | Matthijs Klinkert
EBTA | EBTA474 | 2025-11-05 | NEL-STH-NSA-5100-CUS-REP-0001 | DESIGN REPORT - B019 - UTILITIES - SEWER S072 | Management |  | No specific engineered safety initiatives were identified and included in Table 9-3 for this package. However, the report details that the package has been developed using Engineered Safety Principals and identifies general control measures for Fatal and Severe Risks (FSR) during construction, such as shoring for excavations, barriers and harnesses for working at heights, lift plans for crane and lifting, plant operating zones, traffic management plans, confined space permits and rescue plans, approval of temporary formwork, and GPP for utilities and services. | FSR Chain of Responsibility | Integrating core safety principles and formal permits (Confined Space, GPP) into the design phase ensuring that high-risk construction activities are controlled by standardized safety protocols. | Verify GPP for utilities. |  | Matthijs Klinkert
EBTA | EBTA475 | 2025-11-05 | NEL-STH-NSA-5900-CUW-REP-0002_REV 01 DCN 063 |  | Design | Implemented | Placement of proposed main and appurtenances in accessible areas where possible in consideration of future maintenance and replacement | FSR Utilities and Services | Strategic placement in accessible zones ensures that future maintenance and replacement can be conducted without workers entering high-risk, constrained, or difficult-to-reach locations. | Verify asset setout. |  | Matthijs Klinkert
EBTA | EBTA476 | 2025-11-05 | NEL-STH-NSA-5900-CUW-REP-0002_REV 01 DCN 063 |  | Design | Implemented | Permanent water main to maintain sufficient clearances to existing and proposed services, where feasible and practical, in accordance with MRWA guidelines and respective utility asset owners’ guidelines. Dispensations to be sought otherwise. | FSR Utilities and Services | Maintaining strict clearances prevents accidental strikes on third-party assets during installation and provides a safe working buffer for future utility repairs. | Audit service clearances. |  | Matthijs Klinkert
EBTA | EBTA477 | 2025-11-05 | NEL-STH-NSA-5900-CUW-REP-0002_REV 01 DCN 063 |  | Design | Implemented | Utilising MSCL pipe type mitigated the need for thrust restraints. | FSR Utilities and Services | Utilizing MSCL pipes removes the requirement for independent thrust restraints, simplifying the installation and reducing the number of high-risk tasks required in the trench. | Verify pipe material specs. |  | Matthijs Klinkert
EBTA | EBTA478 | 2025-11-05 | NEL-STH-NSA-5900-CUW-REP-0002_REV 01 DCN 063 |  | Design | Implemented | Permanent water main on Ayr Street and Timber Ridge has been located in the road instead of footpath to avoid clashes and working in and around existing utilities. | FSR Utilities and Services FSR Excavation | Siting the main in the road avoids complex interactions with existing utilities found under footpaths, reducing the risk of accidental strikes and manual handling injuries in crowded areas. | Verify road setout. |  | Matthijs Klinkert
EBTA | EBTA479 | 2025-11-05 | NEL-STH-NSA-5300-SRW-REP-0002 | DESIGN REPORT - B082 – 5300/5400/5500 RETAINING WALLS – EAST | Modularisation | Complete | Minimise frequency of precast lifting – The team has designed the panel widths of each precast wall type to achieve a maximum of approximately 20t units. This optimises the lifting frequency for precast walls while avoiding employing heavy duty cranes. The goal is to reduce exposure of site personnel hazards of lifting heavy loads and eliminate the risks associated to working with heavy machinery. | FSR Cranes and Lifting | Optimizing the size and frequency of lifts avoids the need for heavy-duty cranes and reduces the total duration site personnel are exposed to high-risk heavy-load lifting operations. | Verify panel weight schedule. |  | Matthijs Klinkert
EBTA | EBTA480 | 2025-11-05 | NEL-STH-NSA-5300-SRW-REP-0002 | DESIGN REPORT - B082 – 5300/5400/5500 RETAINING WALLS – EAST | Design | Complete | Minimise risk of striking critical utilities by omitting piled foundations – where appropriate, the design team has opted for the shallow foundations of the “L-wall” type or mechanically stabilised earth walls to minimise the risk of striking critical/hazardous utilities. | FSR Utilities and Services FSR Excavation | Using shallow foundations instead of deep piles significantly reduces the risk of striking critical or hazardous underground utilities. | Verify foundation types on IFC. |  | Matthijs Klinkert
EBTA | EBTA481 | 2025-11-05 | NEL-STH-NSA-5300-SRW-REP-0002 | DESIGN REPORT - B082 – 5300/5400/5500 RETAINING WALLS – EAST | Design | Complete | Minimise piled foundations – There was a design directive for Type 6 post and panel to adopt 3m post spacings (originally 2.4m) to achieve the same outcomes as per BTA-B081-ES02 and reduce working time on-site due to piling. | FSR Plant and Equipment | Increasing the span between posts reduces the total number of piles required, directly lowering the time personnel spend operating heavy piling machinery on-site. | Review B081-ES02 details. |  | Matthijs Klinkert
EBTA | EBTA482 | 2025-11-05 | NEL-STH-NSA-5300-SRW-REP-0002 | DESIGN REPORT - B082 – 5300/5400/5500 RETAINING WALLS – EAST | Design | Complete | Integration of Noise Walls to minimise piling – to achieve similar outcomes as per BTA-B081-ES02-03 in reduced piling and working time on-site, the design team has prioritised, if appropriate, a design where noise walls are supported on retaining walls. | FSR Plant and Equipment | Integrating these structures reduces the overall piling footprint and the associated high-risk construction time for separate foundations. | Verify wall integration detail. |  | Matthijs Klinkert
EBTA | EBTA483 | 2025-11-05 | NEL-STH-NSA-5300-SRW-REP-0002 | DESIGN REPORT - B082 – 5300/5400/5500 RETAINING WALLS – EAST | Methodology | Complete | Prioritising alternate means of retention - where appropriate, the use of earthworks solutions was prioritised as a retention system over wall structures to reduce working time on-site. | FSR Plant and Equipment | Utilizing natural earthworks instead of complex structural walls reduces the requirement for specialized high-risk construction plant and lowers on-site working time. | Review retention system plan. |  | Matthijs Klinkert
EBTA | EBTA484 | 2025-11-05 | NEL-STH-NSA-5300-SRW-REP-0002 | DESIGN REPORT - B082 – 5300/5400/5500 RETAINING WALLS – EAST | Management | Complete | Elimination of hazardous working conditions - SRW410 encroaches under a high-voltage overhead line. The design has prioritised a full elimination of working under an active high-voltage line by amending the design to work within shut-down periods. Changing wall types and relying on minimising lifting heights still presents a risk to personnel as the HV line is still active. | FSR General Electrical Satety | Amending the design to work exclusively within shut-down periods eliminates the risk of accidental contact or arcing with live HV lines. | Coordinate HV shut-down schedule. |  | Matthijs Klinkert
EBTA | EBTA485 | 2025-11-05 | NEL-STH-NSA-5200-CRW-REP-0001 | Design Report - B145 5200 MAINLINE ALIGNMENT AND CIVIL DESIGN | Methodology |  | Engineered Safety is the next generation of safety in design and looks to engineer out risk and engineer in health at every stage of a project lifecycle for our clients and product end user through trusted and collaborative partnerships within the alliance and our supply chain. With inclusivity and connectivity across functions, we listen to and learn from our people improving how we plan for and go to work every day. To achieve alignment with the Eastern Freeway – Burke to Tram Alliance latest initiative of ‘Rethinking safety through Inclusion + Wellbeing’ and one of its core pillars – Engineered Safety, there has been an increasing emphasis on ensuring that a more proactive and collaborative approach is undertaken by both design and construction teams to address risk/hazards and engineer out risk and engineer in health at every stage of a project lifecycle. Design optimization and refinements in construction staging have been investigated and implemented wherever applicable to minimize the duration/extention of high-risk activities including working near live traffic with proposed temporary barrier works and associated signage to be delivered by the Worksite Traffic Management Plan. Tier and gantry protection barriers have been optimised and slip form barriers are preferred to reduce delivery and lifting of precast concrete barriers by cranes and mobile plant. Temporary pavement design and staging is as close to permanent pavement design to minimize the extent/complexity of the works onsite to transition to permanent status. | FSR Traffic Management FSR Cranes and Lifting | Using slip form barriers instead of precast concrete units reduces the frequency of high-risk heavy lifting by cranes and mobile plant. | Confirm slip form equipment availability. |  | Matthijs Klinkert
FBA | FBA001 | 2025-10-24 |  | Temporary Works | Fabrication Programme | Implemented | Expanded "Fabrication" activities in P6 to cover shop drawings, order materials, fabrication, and delivery for more accurate tracking of required dates for TW design concept/100%/IFC and to ensure fabrication not proceeding without IFC | FSR Chain or Responsibility | Prevents the fabrication and use of unapproved structural elements, reducing the risk of temporary works failure due to design non-conformance. | Update P6 schedule baseline with new activity codes. |  | Josh Galvin
FBA | FBA002 | 2025-10-24 |  | Temporary Works | Audit Reporting | Implemented | Agreed new process for inspections accountability. FRIDAY: Emails to all TWCs with overdue inspections and upcoming inspections for the week. Who is responsible for closing them out? FRIDAY OR MONDAY: TW team to attend morning site meetings and get key inspections listed on the board with owner and date. Improve accountability for completion of inspections by individuals and teams each week | FSR Formwork & Falsework FSR Scaffolding | Ensures safety-critical inspections (e.g., pre-pour checks) are timely, preventing the loading of non-compliant or unsafe structures. | Archive weekly inspection reports. |  | Josh Galvin
FBA | FBA003 | 2025-10-24 |  | Temporary Works | Programme Systems | Abandoned | Establish Date in Service linking between P6 and Comply to reduce admin burden + improve reliability of Date in Service in Comply. Automatically reschedule control measures to suit. | FSR Chain or Responsibility |  |  |  | Josh Galvin | 1 person hr / week x 18 months remaining x 4 weeks per month x $150/person hr
FBA | FBA004 | 2025-10-24 |  | Temporary Works | Reporting | Implemented | Improve TW dashboards beyond default Comply dashboards + JG dashboards to provide more actionable information at a project, discipline, and individual level. Improved accountability and therefore quality, safety and schedule by ensuring critical actions are closed out. | FSR Chain or Responsibility | High-level visibility ensures that critical safety actions are not lost in administrative noise, ensuring accountability for safety close-outs. | Share dashboard snapshot in monthly report. |  | Josh Galvin
FBA | FBA005 | 2025-10-24 |  | Temporary Works | Procurement | Implemented | Early RFQs and award of remaining TW design scope to go to provide TW designers more certainty and enable commitment of resources to end of major design scopes. Reduced commercial team and supplier workload by combining VOs. Certainty of schedule guaranteed through early commitment. | FSR Chain or Responsibility | Avoids rushed designs. Allows sufficient time for safety reviews and the development of engineered solutions rather than ad-hoc on-site fixes. | Finalise remaining design packages. |  | Josh Galvin
FBA | FBA006 | 2025-10-24 |  | Temporary Works | Process Inspection | Implemented | Project-specific Inspection Guidelines to provide clarity on frequency of inspections, not requiring BW endorsement every time, to minimise workload for delivery team as well as effort to implement changes for TWM team. Critical thinking applied on purpose of each temporary works inspection, to focus on quality of inspections for highest impact items. | FSR Chain or Responsibility | Prevents "inspection fatigue" by ensuring supervisors focus on critical safety risks rather than administrative tick-boxing. | Distribute guidelines to site engineers. |  | Josh Galvin | See "Inspection Changes" register.
FBA | FBA007 | 2025-10-24 |  | Temporary Works |  | Implemented | Formalised TW design review process to provide clarity on who reviews what; time-bound review requests; clear direction to designers on when reviews are complete and when. Reviews now completed in Revizto; requested via Asite to external parties e.g. IV, DNOP, etc; and time bound with reminder and close out. | FSR Chain or Responsibility | Digital workflows ensure all safety comments are incorporated and verified before the design is released for construction. | Monitor review turnaround times. |  | Josh Galvin
FBA | FBA008 | 2025-10-24 |  | Temporary Works |  | Implemented | Responsibility matrix (RACI) for PW review of TW design. Clarity to PW designers on what they must approve and what is for information only. | FSR Chain or Responsibility | Eliminates assumptions about who has checked safety-critical interface calculations (e.g., loading on permanent structures). | Publish RACI matrix in Project Management Plan. |  | Josh Galvin
FBA | FBA009 | 2025-10-24 |  | Digital |  | Implemented | TW clash detection now incorporated into the work process at model review. Identify issues with install and removal in a 3D space and mitigate ahead of time. 4WLAH used to identify next TW to be clash detected. | FSR Plant and Equipment FSR Formwork & Falsework | Identifies clashes virtually, preventing the physical hazard of needing to make unsafe modifications (e.g., cutting falsework) on site. | Run weekly clash detection reports. |  | Josh Galvin | 1/2 day downtime of crew per instance.
FBA | FBA010 | 2025-10-24 |  | Temporary Works |  | Implemented | Updated TWDB template with more detailed deliverables list and specific activities. Increased clarity and therefore certainty for TW design panel when quoting for new works. | FSR Chain or Responsibility | Ensures temporary works designs include all necessary safety information (erection sequences, exclusion zones) every time. | Roll out new template to design suppliers. |  | Josh Galvin
FBA | FBA011 | 2025-10-24 |  | Temporary Works |  | Implemented | Empower TW designers and scaffolders to liaise directly with each other and with reinforcement modelling consultant, removing the coordination effort required by FBA and ensuring changes between two parties are coordinated almost in real time. E.g. CaSE for slice and cage weld design, Hawkins for sacrificial jig design (both interfacing with Hoffcon). | FSR Scaffolding | Direct communication ensures scaffold designs are practically buildable around complex reinforcement, reducing modification risks during erection. | Document coordination meetings. |  | Josh Galvin | 3 person hr / week (during critical TW design stages) x 9 months x 4 weeks per month x $150/person hr
FBA | FBA012 | 2025-10-24 |  | Digital | Digital | In Progress | Using VR in Revizto for assessing suitability and informing design decision making for critical temporary works - Jump Form | FSR Formwork & Falsework FSR Working at Heights | Allows teams to identify access issues, entrapment risks, and ergonomic hazards inside the jump form before it is physically built. | Schedule VR walkthrough with superintendents. |  | Josh Galvin | 1 week x $X for FRP crew (jump form headroom issue)
FBA | FBA013 | 2025-10-24 |  | Digital | Digital | In Progress | Using VR in Revizto for assessing suitability and informing design decision making for critical temporary works - Hanging Scaffold | FSR Scaffolding FSR Working at Heights | Verifies that hanging scaffolds allow for safe worker egress and emergency rescue access in complex geometries. | Save VR review comments to design folder. |  | Josh Galvin | 1 week x $X for stitch form FRP and associated scaffold crew
FBA | FBA014 | 2025-10-24 |  | Temporary Works | Digital | Implemented | Utilise subcontractor's scaffold management system to reduce admin and double handling via Comply. | FSR Scaffolding | Frees up supervision time from double-handling paperwork, allowing more time for physical safety verification in the field. | Audit subcontractor system monthly. |  | Josh Galvin
FBA | FBA015 | 2025-10-24 |  | Digital | Digital | Implemented | Grillage clash with SW jetty walkway identified ~2 weeks ahead of construction - enabled change to methodology and temp works arrangement and negated potential productivity loss of ~0.5 days. Similar clash noted on the NW jetty walkway, negated potential productivity loss of ~0.5 days. | FSR Formwork & Falsework FSR Work On, Over Or Adjacent to Water | Prevented a physical clash over water, which would have required high-risk remedial work from barges or workboats. | Record as a "Digital Save" case study. |  | Josh Galvin
FBA | FBA016 | 2025-10-24 |  | Temporary Works | Digital | In Progress | Walkways in stairtower noted as being too narrow for stretcher access ~1 week prior to start of stage 1 installation. Negate likely late changes in design, reduce risk of unmanaged site design changes. Negate potential productivity loss | FSR Scaffolding | Ensuring stretcher access is viable in the design phase guarantees injured workers can be safely evacuated without delay. | Issue design change instruction for wider stairs. |  | Josh Galvin
FBA | FBA017 | 2025-10-24 |  | Design | Design | Implemented | Deviate from project-wide requirement to have all drawings on FBA/MRWA title blocks, specifically for shop drawings. Avoid additional unnecessary drafting time adding no value. | FSR Chain or Responsibility | Reduces administrative fatigue, allowing drafters and engineers to focus energy on safety-critical design details rather than formatting compliance. | Update Drafting Standard Document. |  | Josh Galvin
FBA | FBA018 | 2025-10-24 |  | Temporary Works | Management | Implemented | Rationalise scaffolding inspection requirements. Move away from requirement to complete monthly scaffolding inspection checklist for every scaffold, instead relying on scaffold subcontractor's competent personnel and systems to manage inspections and implementing monthly audits at a project level. Reduce additional workload for subcontractor as well as administrative workload for our engineers. | FSR Scaffolding | Prevents "inspection fatigue." Ensures audits are meaningful and deep-dive rather than a tick-box exercise, improving actual hazard detection. | Archive audit results in safety folder. |  | Josh Galvin | 30min admin work / month x $150/person hr x 18 months remaining
FBA | FBA019 | 2025-10-24 |  | Digital | Digital | Implemented | Clash detection carried out location-by-location and stage-by-stage on stair towers. External bracing determined to clash with falsework towers. Change made in design and on site before install, likely saving ~2 days on critical path (1 day to resolve design and 1 day to implement changes). | FSR Scaffolding FSR Formwork & Falsework | Prevents the high-risk scenario of discovering a clash at height, which would require dangerous ad-hoc cutting or modification of structural elements under load. | Record "Digital Save" in monthly report. |  | Josh Galvin | Verify avoided stand down with Wade
FBA | FBA020 | 2025-10-24 |  | Design | Management | Implemented | RFI review sessions refreshed and dashboards updated to allow filtering by discipline. Driving meetings from dashboards allows decisions on priorities to be driven by metrics and clarity of action to be achieved. | FSR Chain or Responsibility | Ensures safety-critical RFIs are prioritized and closed out efficiently, preventing delays that lead to rushed (and potentially unsafe) works. | Distribute dashboard link to leads. |  | Josh Galvin
FBA | FBA021 | 2025-10-24 |  | Temporary Works | Management | Implemented | TW Permit guideline document written. Provides clarity on purpose and implementation of permits to access, load and unload, and enables a mechanism for specific deviations to be endorsed and approved at a project and Hub level. Written to be scalable to Hub level; TW Technical Specialist has confirmed intention to tweak and issue via iGMS. | FSR Chain of Responsibility FSR Crane and Lifting | Establishes strict control over high-risk zones (loading/unloading), preventing unauthorized personnel from entering drop zones or exclusion areas. | Publish Guideline on iGMS. |  | Josh Galvin
FBA | FBA022 | 2025-10-24 |  | Digital | Digital | Implemented | Redline mark up process using Asite and Revizto standardised and rolled out to project. Standardised approach provides clarity to team on what must be in redlines and what can be omitted, improving efficiency and allowing progressive close out. | FSR Chain of Responsibility | Ensures the final structure accurately reflects safety changes on site, preventing future maintenance hazards due to incorrect records. | Train site engineers on RLMU workflow. |  | Josh Galvin
FBA | FBA023 | 2025-10-24 |  | Temporary Works | Design |  | Jetty Calculation Sheet developed by TWD | FSR Chain of Responsibility | Verified calculations for works over water prevent catastrophic collapse or overloading of the jetty structure. | Verify calculations with Independent Verifier. |  | Josh Galvin | 50 non-standard lifts x $2000/lift less $25k for calculator
FBA | FBA024 | 2025-10-24 |  | Engineered Safety | Management |  | Engineered Safety FSR Rating Workshop | FSR Chain of Responsibility | Ensures the entire management team has a consistent understanding of Fatal Risk Standards, ensuring uniform application of controls. | Share workshop minutes. |  | Josh Galvin
FBA | FBA025 | 2025-10-24 |  | Temporary Works | Methodology |  | Temporary Works Activity Toolboxes - run through of TW obligations including permits, inspections, checklists for key activities to provide greater clarity and certainty to the delivery team. | FSR Chain of Responsibility | Ensures work crews act as the final line of defense, understanding exactly what permits and checks are required before work starts. | Schedule recurring toolbox talks |  | Josh Galvin | Est. 2 day prelims substructure + 2 day prelims superstructure + 1 day prelims civils
FBA | FBA026 | 2025-10-24 |  | Temporary Works | Plant |  | Rolled out "Concrete Pump Setup Checklist" for greater certainty and safety when using mobile pumps on site. | FSR Plant and Equipment | Systematically verifies outrigger setup and ground conditions, preventing pump rollover incidents. | Mandate checklist for all pump pours. |  | Josh Galvin
FBA | FBA027 | 2025-10-24 |  | Temporary Works | Management |  | Engage SME to develop specific VOC package for the Segment Lifting Beam, to ensure operators are appropriately qualified and competent prior to installation. Increased certainty in delivery and safer operations. | FSR Crane and Lifting | Ensures only verified, competent operators handle the specialized lifting beam, preventing dropped loads due to human error. | Update training matrix. |  | Josh Galvin
FBA | FBA028 | 2025-10-24 |  | Temporary Works | Plant | Implemented | Observed significant use of ladders on site and adopted SafeSmart AdjustaStairs - safer access for site personnel where space permits. | FSR Working at Heights | Replaces vertical ladders with stairs, significantly reducing fall risks and improving ergonomics for workers carrying tools. | Procure additional units for new fronts. |  | Josh Galvin
FBA | FBA029 | 2025-10-24 |  | Temporary Works | Methodology | In Progress | SimOps/Productivity - use of crash deck - Engineered Safety |  |  |  |  | Josh Galvin
FBA | FBA030 | 2025-10-24 |  | Temporary Works | Methodology | Implemented | Methodology for assembly of falsework - assembled as much as possible horizontally to minimise working at heights. Once pitched to vertical, finishing works all completed from EWP so no access to falsework required. Falsework not accessed until installed and bolted into position, guaranteeing stability and ensuring the safety of workers | FSR Formwork & Falsework FSR Working at Heights | Moves complex assembly tasks from height to ground level. Workers do not need to climb the structure until it is fully secured. | Standardise in SWMS. |  | Josh Galvin
FBA | FBA031 | 2025-10-24 |  | Temporary Works | Precast | Implemented | Prefabrication of slices for Segment 0. Reduction of manual handling risk, reduction of steel fixing insitu / at height / over water, reduction of total # crane lifts | FSR Working at Heights FSR Work On, Over Or Adjacent to Water | Shifts steel fixing from high-risk environments (over water/at height) to a controlled factory setting. | Monitor delivery quality. |  | Josh Galvin
FBA | FBA032 | 2025-10-24 |  | Temporary Works | Methodology | Implemented | Use 1800 high handrails around falsework, Segment 0, climbing formwork | FSR Working at Heights | Higher rails provide superior containment, preventing falls even if workers are standing on platforms or reaching overhead. | Update edge protection standard details. |  | Josh Galvin
FBA | FBA033 | 2025-10-24 |  |  | Digital | Identified | Crane pad boundaries into GIS and Model | FSR Crane and Lifting | Visualizes crane footprints in the model to prevent setup on uncertified ground or clashes with other plant/structures. | Import GIS layers to Navisworks. |  | Josh Galvin
FBA | FBA034 | 2025-10-24 |  |  |  | Identified | SimOps identification and analysis - what in P6 is not currently linked to the model? |  |  |  |  | Josh Galvin
FBA | FBA035 | 2025-10-24 |  | Temporary Works | Material | Identified | Reuse of lower tower formwork steel for fabrication of barrier formwork. Required for architectural finish. Reduced raw material cost and environmental impact. | FSR Formwork & Falsework | Reuse eliminates the logistics, unloading, and handling risks associated with bringing raw materials to site. Reduces environmental impact. | Verify steel integrity before fabrication. |  | Josh Galvin
FBA | FBA036 | 2025-10-24 |  |  | Design | Implemented | Development of custom made edge protection to suit project requirement. This system is extremely simple | FSR Working at Heights | Simplifying the system reduces installation errors and ensures the edge protection is actually used correctly, minimising fall risks. | Archive the design certification. |  | Josh Galvin
FBA | FBA037 | 2025-10-24 |  |  | Plant | Implemented | Development of segment lifting beam with external flippers to prevent penetration in the segment top slab (typical clamping method). This help with the rebar congestion in the segment and also reduce the patching requirement of 4 holesx166 segment : 664 holes | FSR Crane and Lifting FSR Plant and Equipment | Eliminating 664 pathcing holes removes substantial exposure to silica dust (drilling/scabbling) noise, and repetitive strain injuries from manual repair work. | Inspect flippers for weaer weekly. |  | Josh Galvin
FBA | FBA038 | 2025-10-24 |  |  | Digital | Implemented | Adjustment of duct in segment 0 carried out based on 3D scanning on +1 segment to reduce misalignment risk. | FSR Precast and Tilt up Concrete | Digital alignment prevents misalignment issues that would otherwise require high-risk remedial drilling or cutting in confined spaces. | Schedule scan for next segment. |  | Josh Galvin
FBA | FBA039 | 2025-10-24 |  |  | Material | Implemented | Use of GRP panel instead of concrete plank in top slab to reduce overall weight, concrete slab thickness (reduce 50 mm), reduce rebar qty (reduce 150T) and carbon footprint. | FSR Crane and Lifting | Glass Reinforced Polymer (GRP) is significantly lighter than concrete, reducing the load on cranes and the manual handling strain on workers during installation. | Confirm fire rating compliance for GRP. |  | Josh Galvin
FBA | FBA040 | 2025-10-24 |  |  | Digital | Implemented | Redline markup process revised - design team completing RLMUs in Revizto instead of delivery team. Reduces burden on delivery team to track complete vs incomplete RLMUs from RFIs and provides assurance that RLMUs are accurate. | FSR Chain of Responsibility | Reduces the administrative burden on the site delivery team, allowing them to focus on field safety and preventing fatigue-induced errors. | Audit a sample of RLMUs for accuracy. |  | Josh Galvin
FBA | FBA041 | 2025-10-24 |  |  |  |  | Concrete mix design to meet constructability requirements | FSR Plant and Equipment |  |  |  | Josh Galvin
FBA | FBA042 | 2025-10-24 |  |  |  |  | Jetty |  |  |  |  | Josh Galvin
FBA | FBA043 | 2025-10-24 |  |  |  |  | Pile cap shells |  |  |  |  | Josh Galvin
FBA | FBA044 | 2025-10-24 |  |  |  |  | Prefab of rebar - split by activity |  |  |  |  | Josh Galvin
FBA | FBA045 | 2025-10-24 |  |  |  |  | Trial Pours and Assemblies |  |  |  |  | Josh Galvin
FBA | FBA046 | 2025-10-24 |  |  |  |  | SME involvement in PERI challenge |  |  |  |  | Josh Galvin
FBA | FBA047 | 2025-10-24 |  |  |  |  | Literature review and lessons learned session on structural bolts |  |  |  |  | Josh Galvin
FBA | FBA048 | 2025-10-24 |  |  | Design |  | Temporary CCTV solution developed specific for FBA, now approved by MRWA for use across the network. Can be adopted on future projects and has saved the Alliance the cost of 9 otherwise permanent CCTV installations. | FSR Traffic Management FSR Utilities and Services FSR Chain of Responsibility | voiding permanent installations removes the high-risk activities associated with them: specifically trenching for power/comms (utility strikes), working at heights to install permanent poles, and prolonged exposure to live traffic during construction. | Archive the MRWA approval documentation and technical specifications for adoption on future projects. |  | Josh Galvin
FBA | FBA049 | 2025-10-24 |  |  | Digital | Identified | Comply-Revizto Linking | FSR Chain of Responsibility | Ensures safety-critical defects identified in the field (Comply) are visually mapped to the model (Revizto), preventing hazards from being overlooked due to administrative disconnection. | Audit the sync logs weekly. |  | Josh Galvin
FBA | FBA050 | 2025-10-24 |  |  | Digital |  | 4D sequencing for tying of rebar has assisted with planning and avoided delays or reworks on site | FSR Plant and Equipment FSR Manual Handling | Visualizing the rebar sequence prevents overcrowding in the steel cage, reducing the risk of impalement, pinch points, and clashes between workers and crane loads. | Archive the 4D simulation video. |  | Josh Galvin
FBA | FBA051 | 2025-10-24 |  |  | Methodology |  | Use of slice table for Segment 0 stemming from similar methodology in Precast Yard | FSR Working at Heights FSR Formwork & Falsework | Optimizes the working height for steel fixers and form workers, reducing the need for ladders or awkward reaching, thereby lowering musculoskeletal strain risks. | Verify table load rating. |  | Josh Galvin
FBA | FBA052 | 2025-10-24 |  |  | Management |  | Project-specific forms | FSR Chain of Responsibility | Removes irrelevant generic checkpoints, ensuring the workforce focuses entirely on the specific hazards and controls relevant to the current site conditions. | Review form usage rates. |  | Josh Galvin
FBA | FBA053 | 2025-10-24 |  |  | Digital |  | Steelfixers using 3d model in the field | FSR Chain of Responsibility | Direct access to the model eliminates ambiguity in complex bar arrangements. This prevents the high-risk "rework cycle" of cutting and re-tying steel under time pressure. | Ensure tablets have latest model sync. |  | Josh Galvin
QR SAUP | QR001 | 2023-06-14 |  | Rail Interface | Platform extension structure | Under construction | Working in close proximity to live rail traffic Redesign platform extension structure so majority of structure can be installed safely behind a barrier outside of a SCAS. Portion installed during SCAS changed from in-situ to precast concrete or offset the blockwork wall to allow construction during an SCA. | FSR Rail Operations | Moving the majority of the work outside of high-pressure SCAs and behind physical barriers significantly reduces the time workers spend exposed to live rail environments. | Verify barrier setout. |  | Derek Greenough | Currently being implemented within the construction.
QR SAUP | QR002 | 2023-10-07 |  | Rail Interface | Platform retaining walls | Under construction | Working in close proximity to live rail traffic Working near open drainage channels (i.e. swale) Modification of retaining walls at Lindum from reference design so that it is "heel in" rather than "toe out". This will moving the excavation away from the adjacent freight line into the existing platform area. Alternative platform option. Post and panel or culvert | FSR Rail Operations | Shifting the excavation footprint into the existing platform area protects the structural integrity of the active freight line and prevents accidental strikes on rail infrastructure. | Review Lindum wall design. |  | Derek Greenough | Currently being implemented within the construction.
QR SAUP | QR003 | 2023-10-07 |  | Rail Interface | Precast platform copings (raising and extension areas) | Under construction | Working in close proximity to live rail traffic Working during SCAS (time pressure) Manual handling The reference designs for Banyo and Lindum Station included in-situ concrete platform slabs out to the edge of the coping. We are replacing the in-situ concrete coping area of the slab with precast concrete so it can be installed quickly and safely during SCAS weekends. Ferrules to be in place at the back of the cope instead of insitu reo, pouring the blinding slab improved the install and removed the issue of sinking copes. Grout mix design to be TMR and approved to pump on site in lieu of bag mix. The movement joints to be at more regular intervals. | FSR Rail Operations | Using precast elements instead of complex in-situ pours reduces time pressure during critical track closures and eliminates the need for manual handling of wet reinforcement and formwork near the track edge. | Approve precast coping units. |  | Derek Greenough | Currently being implemented within the construction.Cope design did not prevent eccentric rotation. Cope design initially balanced cope with rotational moment towards rear of platform and supported by platform structure. Subsequent requirement for infill plates added weight to front of cope and changed rotational moment towards the from of the platform in direction that was not supported by the structure. Security of cope is only achieved by bolt fixings from underside until final platform slab is poured to interlock with cope starter bars. This is to be consider in the design of copes going forward.
QR SAUP | QR004 | 2023-10-07 |  | Rail Interface | Railway corridor barrier in platform raising areas - Adaptapanel (2050mm min clearance but relaxation required up to 1700mm, confirm the HD and RL) Attach a cross section of what was approved. | Under construction | Working in close proximity to live rail traffic Platform raising barrier solution. The transition of removal when copes are being installed. The install of the panel in the centre and remove the grout tube from the centre to avoid the clash. Ferrules or socket to be placed into the precast. Consider the signal sighting and kinematic envelope during development of the design. | FSR Rail Operations | Pre-integrated sockets and centered grout tubes prevent mechanical clashes with the rail kinematic envelope and ensure a secure, fast-install barrier to protect workers from passing trains. | Verify signal sighting clearance. |  | Seb Alvarez | Currently being implemented within the construction.
QR SAUP | QR005 | 2023-10-07 |  | WAH | Footbridge piers | Under construction | Working in close proximity to live rail traffic Working at heights Redesign footbridge piers to eliminate need to concrete infill piers on site. Additional steel stiffeners are introduced. For future projects review if this change is required, look to reduce the stiffeners and concrete infill. | FSR Working at heights | Introducing steel stiffeners instead of concrete infill removes the high-risk task of handling and pouring wet concrete in elevated positions near active rail lines. | Review stiffener design for future projects. |  | Derek Greenough | Currently being implemented within the construction.
QR SAUP | QR006 | 2023-10-07 |  | Rail Interface | Platform extension areas at Morningside and Lindum Station | Under construction | Working in close proximity to live rail traffic Platform extension hard barrier solution (concrete with antigauk), vortok and pecker form was used due to geotech conditions. | FSR Rail Operations | Utilizing robust physical barriers and specialized formwork protects workers from passing trains and maintains the structural integrity of the platform edge during construction. | Verify geotech conditions for barrier. |  | Seb Alvarez | Currently being implemented within the construction.
QR SAUP | QR007 | 2023-10-07 |  | WAH | Footbridge superstructure, envelope and stairs | Under construction | Working at heights Working in close proximity to live rail traffic Prefabricated/ fitout bridge & stair modules, look for an offsite fabrication area to manage interfaces better, communicate the requirement with the subbies in more detail prior to contract award. Hollow sections not to be used, I sections all the way! RC connection support was not installed by QR as they were expecting to attach a connection to the I beam! QR missing design co-ordination. | FSR Working at heights | Offsite fabrication significantly reduces the time workers spend at height and near live tracks, moving high-risk activities into a controlled environment. | Communicate requirements with subcontractors. |  | Seb Alvarez | Currently being implemented within the construction.
QR SAUP | QR008 | 2023-10-07 |  | WAH | Platform canopy structure and roofing | Under construction | Working at heights Working in close proximity to live rail traffic Platform canopy prefabrication, tapped threads were cleaned post gal. This should change for future connections. Install of the sheets to be 3m offset. | FSR Working at heights | Pre-galvanizing and cleaning threads post-galvanization offsite ensures faster, safer assembly at height, while the 3m offset reduces the risk of objects falling onto the tracks. | Verify post-galvanization thread cleaning. |  | Seb Alvarez | Pacakge awarded and the methodology is being developed with the subcontractor
QR SAUP | QR009 | 2023-10-07 |  | Other | Foundation and column reinforcement | Under construction | Working in close proximity to live rail traffic Manual handling Prefabrication of reinforcement | FSR Rail Operations | Moving reinforcement assembly to an offsite facility eliminates the high-risk manual handling and repetitive strain of tying rebar in constrained trackside environments. | Coordinate offsite fabrication area. |  | Seb Alvarez | Currently being implented in construction
QR SAUP | QR010 | 2023-10-07 |  | Other | Platform 1 retaining wall | Under construction | Working in close proximity to live rail traffic Manual handling Replacement of blockwork walls with precast concrete | FSR Rail Operations | Replacing manual block-laying with rapid-install precast units reduces the duration of exposure to rail traffic and eliminates the musculoskeletal risks of lifting individual blocks. | Approve precast wall design. |  | Seb Alvarez | Currently being implemented in construction
QR SAUP | QR011 | 2023-10-07 |  | Other | Platform 2 extension steelwork support for Bondek slab | Under construction | Awkward/ restricted access underneath platforms Steelwork support for Bondek behind MSD Platform 2 | FSR Rail Operations | Providing dedicated structural support allows for safer material handling and installation in the awkward and restricted access zones underneath platforms. | Verify support dimensions on site. |  | Derek Greenough | Currently being implented in construction
QR SAUP | QR012 | 2023-10-07 |  | Rail Interface | General- use of plant and equipment adjacent to rail corridor | Under construction | Working in close proximity to live rail traffic Blindsight for working adjacent to rail corridor | FSR Rail Operations | Identifying and managing blind spots ensures that workers and plant operators maintain high situational awareness, reducing the risk of strikes from passing rail traffic. | Review site spotter protocols. |  | Seb Alvarez | Not being used on site.
QR SAUP | QR013 | 2023-10-07 |  | WAH | Platform canopy structure and roofing | IFC | Working in close proximity to live rail traffic Working at heights Platform canopy stick build out of EWP | FSR Working at heights | Utilizing EWPs instead of traditional ladders or scaffolding provides a stable, guarded platform for workers at height, significantly reducing fall risks. | Confirm EWP operator certifications. |  | Seb Alvarez | Currently being implented in construction
QR SAUP | QR014 | 2023-10-07 |  | Underground Services | All existing and new underground services | Under construction | Live underground services 3D underground services models | FSR Utilities and Services | Visualizing underground assets in 3D allows for precise planning to avoid accidental strikes during excavation, preventing potential electrocution or gas/water bursts. | Update federated utility model. |  | Seb Alvarez | Currently being implemented in construction
QR SAUP | QR015 | 2023-10-07 |  | WAH | Lift shaft structure and envelope (louvres, glazing, roof slabs) | Under construction | Working at heights Working in close proximity to live rail traffic Lift shaft evelope prefabrication, use of 2T siccor lift used to fit out internally. Scaffold landing placed inside the pit to enable the use of the lift instead of scaffolding. | FSR Working at heights | Placing a scaffold landing inside the pit to enable scissor lift use instead of complex scaffolding eliminates the high-risk task of erecting/stripping scaffold in a confined shaft. | Verify scissor lift capacity in shaft. |  | Seb Alvarez | Currently being implented in construction
QR SAUP | QR016 | 2023-10-07 |  | Logistics | SCAS activites | Under construction | Lifting operations and plant/ people interaction Construction Sequencing and Staging (4D) for SCAS | FSR Cranes and Lifting | 4D modeling identifies potential plant/people interactions and lifting clashes before they occur, allowing for safer scheduling during time-pressured rail closures. | Review 4D simulation for next SCA. |  | Seb Alvarez | Currently being implemented in construction
QR SAUP | QR017 | 2023-08-20 |  | Other | Pile breakback to cutoff levels | Installed on site | Respirable dust exposure HAVS Pile cropping | FSR Piling | Mechanical cropping significantly reduces the volume of airborne respirable crystalline silica (RCS) compared to manual jackhammering, protecting workers from long-term lung disease. | Monitor dust suppression during cropping. |  | Seb Alvarez | Works complete
QR SAUP | QR018 | 2023-08-20 |  | Other | Polymer/ bitumen based emulsion for dust supression | Installed on site | Dust exposure (amenity to nearby residents and businesses) Dust management during civil works - speak to Lara. | NA | Active suppression and management minimize the migration of dust to sensitive receptors, maintaining local air quality and community health. | Consult with Lara regarding civil works plan. |  | Lara Brunner | Currently being managed on site.
QR SAUP | QR019 | 2023-08-20 |  | Other | Working in sun (UV exposure) | Under construction | UV radiation Working in sun- how we protect workers during construction | NA | Proactive management of sun exposure prevents heat stress, dehydration, and long-term skin damage from UV radiation. | Distribute sun safety PPE. |  | Seb Alvarez | Currently being managed on site.
QR SAUP | QR020 | 2023-08-20 |  | Rail Interface | General-efficient material movement and logistics | Under construction | Plant and equipment movement Manual handling Logistics- material movement and laydown area setup | NA | A well-planned logistics layout reduces the number of high-risk interactions between heavy plant and personnel and minimizes the need for excessive manual handling. | Audit laydown area zoning. |  | Seb Alvarez | Currently being implented in construction
QR SAUP | QR021 | 2023-08-20 |  | Other | Above ground electrical services terminations | IFC | Working at heights Wago services / electrical connections - plug and play. No requirement for termination of fittings for extended durations at heights. | FSR Working at heights | Eliminating the requirement for the termination of fittings at height allows for faster installation, significantly reducing the duration workers spend in elevated positions. | Verify Wago connector stock. |  | Claire Lendrum | Currently being managed on site.
QR SAUP | QR022 | 2023-08-20 |  | Other | Lighting fixtures | IFC | Working at heights Wall mounted lighting where possible (stations/walkways) – not accessible to general public but accessible from low step ladder | FSR General Electrical Satety | Placing lighting at lower, easily accessible heights ensures that future maintenance can be performed safely from a step ladder, avoiding the need for high-risk elevated work platforms. | Verify light mounting heights. |  | Nino Valmadre | Currently being implented in construction
QR SAUP | QR023 | 2023-08-20 |  | Other | Lighting poles | IFC | Working at heights Droppable carpark light poles | FSR General Electrical Satety | Hinged poles allow maintenance to be performed at ground level, completely removing the requirement for workers to use ladders or elevated platforms for light servicing. | Verify pole base plate design. |  | Nino Valmadre | Currently being implented in construction
QR SAUP | QR024 | 2023-08-20 |  | Other | Lift shaft services reticulation | Under construction | Working at heights Core holes in precast prior to mob to site for service routes (assuming lifts & services running to overpass via lift shaft) – reduced time working at heights coring at high levels | FSR Working at heights | Factory-integrated holes eliminate the need for high-level coring at the site, reducing time spent at height and removing onsite exposure to respirable silica dust. | Verify lift shaft service layout. |  | Nino Valmadre | Currently being implented in construction
QR SAUP | QR025 | 2023-08-20 |  | Other | Above ground services reticulation through structures | IFC | Working at heights Circuit routes on structures prior to install – reduced working at heights and drives development of subcircuits and detailed design | FSR Working at heights | Defining routes early reduces the duration and complexity of high-level electrical installation, minimizing the time workers are exposed to fall hazards. | Review subcircuit detailed design. |  | Nino Valmadre | Works are being planned with the relevant subcontractors.
QR SAUP | QR026 | 2024-07-18 |  | Other | Use of cast in ferrules in lieu of post fixing | Under construction | Respirable dust exposure HAVS Ferrules are to be placed within precast elements to post fixing of lift support brackets | NA | Using pre-cast ferrules instead of post-drilling for brackets eliminates the risk of Hand-Arm Vibration Syndrome (HAVS) and significantly reduces crystalline silica dust exposure. | Confirm ferrule placement accuracy. |  | Claire Lendrum | Works are being planned with the relevant subcontractors. 02/06 communication and co-ordination between the subcontractors to be managed and tolerances to align to the highest level of tolerance required.
QR SAUP | QR027 | 2024-05-04 |  | Logistics | Footbridge insallation sequence | Under construction | Revise the sequence of the installation of the footbridge at morningside The sequence of the installation revised to improved effiencies | NA | A more efficient installation sequence reduces the total "window" of high-risk work at height, lowering the statistical likelihood of an incident occurring during assembly. | Verify revised Morningside lift plan. |  | Claire Lendrum | Currently being implented in construction
QR SAUP | QR028 | 2023-08-20 |  | Other | Bored pile excavations | Installed on site | Working at heights Pile hole protection | FSR Piling | Proactive protection for structural openings ensures that temporary fall hazards are secured immediately, preventing personnel from accidentally falling through levels. | Audit floor opening covers. |  | Seb Alvarez | Works complete
QR SAUP | QR029 | 2024-09-05 |  |  | Overpour of concrete to reduce formwork install and removals in a confined space | Under construction | Reduce physical labour and time Overpour to excavation width | FSR Formwork and Falsework | Overpouring to the width of the trench eliminates the need for workers to enter confined excavations for manual formwork stripping and detailed hand-leveling, reducing repetitive strain. | Verify excavation width specs. |  | Other
QR SAUP | QR030 | 2024-05-04 |  |  | Improved effiencies in welding to reduce addition works | Under construction | Through the shop drawing review process improve on the existing design Reduce the amount of welding time | NA | Streamlining the design to reduce on-site welding requirements minimizes worker exposure to toxic fumes, fire risks, and prolonged awkward postures. | Review shop drawing logs. |  | Logistics
QR SAUP | QR031 | 2024-07-24 |  |  | Design of the cope to improve the installation going forward | Under construction | Working close to the rain corridor Reduce the time working on the SCAS | FSR Rail Operations | Reducing the duration of works during high-pressure SCAs minimizes the time personnel are exposed to the unique hazards of the rail environment and time-pressured fatigue. | Audit next SCA schedule. |  | Logistics | Yes
QR SAUP | QR032 | 2024-05-04 |  |  | Coping stones, additional steel plate pre-installed on coping stone which impacts the rotational movement towards the trackside | Under construction | Through the design and construction review process, it was shown to benefit the program to install the steel plate prior to install, however the impact to the eccentric rotation was not reviewed in detail to update the location of the lifting points Review the design and weight distribution of the load to prevent the rotation of the copes towards the track. | NA | Reviewing load distribution ensures that platform copes remain stable during lifting and installation, preventing accidental rotation and strikes against active rail infrastructure. | Review lifting point locations. |  | Rail Interface | No
QR SAUP | QR033 | 2024-11-01 |  |  | Replacement of turf with gravel in Platform 1 demolition area | Under construction | Excavation within an existing platform introduces hazzard Reduce excavation and extent of the works | FSR Demolition | Minimizing the excavation footprint on an active platform reduces the risk of ground instability near tracks and limits public exposure to open hazards. | Simplify steel schedule. |  | Rail Interface | Yes
QR SAUP | QR034 | 2024-01-10 |  |  | Cast in situ slab | Under construction | Review the design to simplify the scheduling and installation of steel. The amount of profiling of the thickening slabs instead of a consistent thicker slab. Large volumes of heavy lifting were required in a confined space. Emercency access restricted due to the size of existing platforms and reo required for the works. Simplify the design to enable quick schedule of reo and reduce confusion for the works on site. More details were required to provide clarity on the design intent post IFC. Introduce more regular movement joints to reduce the required joint width and reduce surface cracking and program the works to allow for this additional time. | FSR Rail Operations | Simplifying the slab design enables a faster rebar schedule, reduces the volume of heavy lifting in confined spaces, and prevents surface cracking, ensuring long-term asset and public safety. | Verify movement joint spacing. |  | Rail Interface | No
QR SAUP | QR035 | 2024-01-10 |  |  | Pits | Under construction | Review the design to simplify the scheduling and installation of drainage. Hydraulics eng would not reduce the pit size, pits in extended platform area requires extra detail. Strip drain to suit on susponded bucker rod to allow adjustment during slab construction. Allow for drainage hole in elec and comms pits. | FSR Rail Operations | Simplifying the drainage layout and allowing for pre-drilled holes in pits reduces the duration of manual handling tasks and the time workers spend in open excavations. | Review hydraulics eng pit details. |  | Rail Interface | No
QR SAUP | QR036 | 2025-10-01 |  |  | Bridge install and fit out | Under construction | Engineered Safety Register to explore opportunities to engineer out HSE risk for work that is not able to be performed at ground level (connections between structures etc), e.g. avoiding clashes between lifting points and landings Restricted access to areas when works that were planned to be completed on the ground were not done so. Programme review to confirm the impact of delaying the install to maintain min working WAH after the bridge is installed, impact to accessing the roof. Install temp edge protection or anchors for works to be completed at height. Alternative full height barriers to be considered. Roof sheeting design and procurement to allow deck sets or alternative to be installed. Engineering review of the bridge to close all openings on the SCAS where time permits. Procurement to consider interface of work groups and bridge installer to allow for closing al openings. Contract was let late and put pressure on the programme. Diversity of procurement to release pressure on the works and domino affect when Morningside Bridge ran later. Lifting points to be on the outside to close more areas prior to lifting. There were a large number of RFI's to complete the shop drawings. Communicate the impact of ignoring safety guidelines and controls and provide suitable consequences. Bridge design to consider additional steel to the underside of the bridge, to remove the potential of falling. | FSR Working at heights | By identifying connection risks early, the team can design out clashes between lifting points and landings, removing the need for workers to perform complex remedial work at height. | Audit structural connection designs. |  | WAH | Yes
QR SAUP | QR037 | 2025-05-29 |  |  | Roofing system within proximity to the rail corridor | Complete | Complicated proceed to install the roof, lots of parts and layers, working at heights in hard to reach areas, not all work could be completedd on the ground Design - Simplified systems can be considered but they will also change the look of the finish. 2) Access - Rail Corridor and General - Sequencing of the steel erection to be considered allowing the progressive install of roof before steel is above if possible. Allowing better access for EWP etc. - Access to more closures without trains would allow for more continuous work to be performed. - Consider extending of adapta pannel to a greater height to act as an approved barrier for work to be performed behind not requiring an SCA. - Consider Edge Protection (preinstalled or designed for it to be easily installed) to allow work from the roof. | FSR Working at heights | Revising the sequence to install the roof progressively before all steel is in place improves access for Elevated Work Platforms (EWPs) and reduces the time workers are exposed to height hazards over the rail corridor. | Review bridge closing opening plan. |  | WAH | No
Croydon LXRP | CRO001 | 2025-05-11 | CSR | CSR | Hangers | Complete | Hangers installed on precast viaduct prior to viaduct being installed. This reduced the amount of working at heights by 90% and being able to work on the ground instead | FSR Working at Height | Eliminating working at heights | No action | 2025-05-11 | Paul Dally
MLCX | MEL001 | 2025-10-30 | Track Construction | Track | Turnouts | Identified | Ensuring full consolidation of ballast under all in-bearer of the turnout - completely filling the voids and weep holes are full | FSR Turnout Construction | Eliminate the manaul handling task of returning to hand tamp on a frequent basis | Secured track possessions to implement hand tamping activities of affected in-bearers | 2025-10-06 | James Rees | Ammend line item in ITR to a hold point to be signed off by both Client PE and Supplier SRE
BRE and MEL | BRE094 | 2025-11-04 | Track Welding | Track | Welding | Identified | Lot of re-work involved in both BRE and MEL using spray paint to re-spray all AT and Flashbutt welds. QR code stickers can be used instead of Rail Weld Stencling. This QR code can link to a register to store all weld info | SER - Dangerous Goods and Chemical Management | Eliminate using spray paint | Nil |  | Sandeep Yalamanchili
BRE | BRE095 | 2025-05-11 | Earthing and Bonding | OLE | Bonding | Identified | Handrails and lighting SPS requiring bonding identified at the end of the project while on site. Insufficient communication from other teams regarding installation of these SPS components that required to be bonded. | FSR General Electrical Safety | Eliminate risk of components not being bonded in the rail corridor | All bonding required completed during the last BRE shutdown | N/A | Jennifer Gillespie | Relevent QA updated and attached with EIS forms to PTA.
BRE and MEL | BRE096 | 2025-11-05 | General | Track | Housekeeping | Identified | A designated person to manage onsite tools and oversee on-site deliveries | FSR General Electrical Safety | Reduces the risk of having untagged/out of date electrical equipment being taken to site or used on site | Nil | N/A | Tashi Dorji
SEPA | SEPA001 |  |  |  | Methodology | Incorporated | Reduce exposure to contaminated spoil Change existing practice: New type-approval on V/Line network to use shallow recessed CSR system to avoid deep excavation into contaminated soil | FSR Excavation | Using a shallow system avoids deep excavation into contaminated soil, protecting workers from exposure to harmful spoils and reducing the risk of trench collapse. | Verify V/Line type-approval. |  | David Hardy
SEPA | SEPA002 |  | South Dynon Stage 2 |  | Design | Incorporated | Indoor air quality / workplace environment Change existing practice: Diesel-powered pressure washers in existing facilities. New facility to have centralised heat pumps to heat and pressurise the water to the lances. | NA | Moving to centralised heat pumps eliminates diesel fumes in existing facilities, significantly improving indoor air quality and the general workplace environment. | Finalise facility pump layout. |  | David Hardy
SEPA | SEPA003 |  |  |  | Management | Progressing | Digital Build & Digital Shop drawing reviews (DCFD) Circa 60 Pre IFC RFI's Closed out by launching digital build at FD for concrete geometry verification | NA | Closing out approximately 60 pre-IFC RFIs via digital verification ensures "right first time" construction, preventing the high-risk unplanned rework often associated with geometric errors. | Close out remaining RFIs. |  | David Hardy
SEPA | SEPA004 |  |  |  | Methodology |  | Pile Breakback Chosen Methodology – Hydraulic Multi Bar Cropper ​ - Pile to be ground down to 300mm above Cut Off Level, then hand breaker 300mm ​ -Additional dust suppression to be used to reduced airbourne dust | NA | Utilizing a mechanical cropper and additional dust suppression significantly reduces airborne dust compared to traditional jackhammering, protecting workers from silica exposure. | Monitor dust suppression levels. |  | David Hardy | Key Benefits​ - Reduction in HAVS​ -Reduction in Airbourne Silica Dust ​ -Reduction in noise ​ -Programme benefit​ -FRP Subcontractor not yet contracted ​ Key Limitations​ - Non-standard pile breakback methodology​ -Occupational risks still remain despite significantly reduced​ -Increase in cost for the methodology​ -Removal of precast pile requires plant
SEPA | SEPA005 |  |  |  | Design |  | Sacrificial Formwork Phreatic Surface anticipated to be 1.7-1.9m. Pile cut of level around on average 1.8m below E.S.L response: Reduction in open excavations | FSR Excavation | Leaving the formwork in place reduces the time workers spend in open excavations near groundwater, minimizing exposure to potential cave-ins or unstable soil. | Verify pile cut-off levels. |  | David Hardy
SEPA | SEPA006 |  |  |  | Management |  | Sacrificial Formwork Spoil heavily contaminated response: Reduce off site spoil/ reuse where applicable | FSR Formwork and Falsework | Reducing the volume of off-site spoil transport minimizes the handling of hazardous materials and the associated environmental and public safety risks of moving contaminated soil. | Finalise spoil reuse plan. |  | David Hardy
SEPA | SEPA007 |  |  |  | Design |  | Sacrificial Formwork: Working around existing structures response: Reduce craneage and potential for damage to existing structure | FSR Formwork and Falsework | Leaving formwork in place reduces the total requirement for craneage and eliminates the potential for damaging existing structures during formwork removal. | Verify sacrificial formwork specs. |  | David Hardy
SEPA | SEPA008 |  |  |  | Modularisation | Progressing | Prefabricated lift shaft Early coordination with design partner to understand off site manufactured approach -> engage lift, structural steel contractor and roofing & cladding contractors early -> feedback into design and align design | FSR Working at Heights | Engaging structural steel and cladding contractors early to align on off-site manufacturing reduces high-risk on-site assembly tasks at height. | Align design with lift contractor. |  | David Hardy
SEPA | SEPA009 |  |  |  | Design | Seeking solution | Biowash & wheel lathe pit handrailing Typical handrailing sits on the top of the sheets – strive is to seek an alternative in the market which can accommodate the 500mm cut below the top of the sheet | FSR Working at Heights | Utilizing a specialized handrail system ensures continuous protection for workers around deep pits where typical top-mounted railings are not feasible. | Source alternative railing. |  | David Hardy
SEPA | SEPA010 |  |  |  | Design | Progressing | Biowash & Wheel Lathe Pit Handrailing Sheet Pile to Non Drill handrailing Base adaptation | NA | Using a non-drill adaptation eliminates the requirement for mechanical drilling into piles, removing the risks of Hand-Arm Vibration Syndrome and silica dust exposure. | Verify base adaptation detail. |  | David Hardy
SEPA | SEPA011 |  |  |  | Modularisation | Seeking solution | Roofing & Cladding Modularisation 1 - Purlin/Girt Frame arrives to site prefabricated 2 - Roofing contractor to install product and build up on the prefabricated substrate & permanent roof access points 3 - Crane lift following quality Hold Points, CRITICAL CONTROL checklist and test lift | FSR Working at Heights FSR Cranes and Lifting | Delivering prefabricated substrates with integrated access points minimizes the duration workers spend at height and ensures safe access is available immediately. | Verify test lift checklist. |  | David Hardy
SEPA | SEPA012 |  |  |  | Methodology | Progressing | Prefabricated turnouts installed with Panel lifters Panel lifter solution: The team explored the use of cranes and PEM-LEMS, however space constraints and multiple track gauges meant these solutions were not possible. Panel lifters provide the flexibility we require on this site | FSR Plant and Equipment FSR Cranes and Lifting | Utilizing panel lifters provides the necessary flexibility for complex rail turnouts in constrained spaces where cranes or PEM-LEMS are not viable. | Verify panel lifter capacity. |  | David Hardy
SEPA | SEPA013 |  |  |  | Methodology | Progressing | CM Builder - Methodology study - bulk excavation Confirming subcontractors choice of excavator by using pre detailed excavators to plan reach & logistics. Methodology check has shown that the initial methodology of a 30t excavator can't reach the northern face of the excavation. Decision to bring in small excavator to crop piles and carry out detailed excavation being worked through | FSR Plant and Equipment FSR Excavation | Digital modeling identified that the planned 30t excavator could not reach the northern face, preventing a high-risk on-site "workaround" that could lead to plant instability or trench collapse. | Finalize small excavator logistics for pile cropping. |  | David Hardy
SRL I&EW | J21001 |  | Site Establishment | Civil | Temporary Fencing | Implemented | Introduced Fortawall at BXHG as a safer, wind-resistant alternative to traditional temporary fencing. With fewer components to assemble, Fortawall reduces installation and demobilisation time by up to 70%, and can be easily relocated and assembled on site. | FSR Plant & Equipment | Minimises the risk of manual-handling injuries associated with traditional temporary fence blocks | Shared across the SRL project during the Innovation Workshop, with endorsement from the client. |  | Alfredo Sandoval | Following successful implementation, the Fortawall was adopted across the SRL project wherever practicable.
SRL I&EW | J21002 |  | Tunnell Access Shaft | Civil | Diaphragm wall panels | Implemented | The zero-trim method was applied to diaphragm wall panels to eliminate exposure to manual jackhammering hazards. Fresh concrete overpour was removed using a Non-Destructive Digging (NDD) truck, ensuring a safer and more efficient process. | FSR Piling FSR Plant & Equipment | Reduces the exposure of pile break back crews to silica dust, vibration and noise by 80%. | Michael Beecham presented engineered safety knowledge share |  | Michael Beecham | Alternative pile break-back methods were investigated during the planning phase.
SRL I&EW | J21003 |  | Tunnell Access Shaft | Structures | Scaffolding | Implemented | Hanging scaffold was implemented to provide safe access into Tunnel Access Shafts (TAS) while minimising operational impact. This approach significantly reduced downtime and eliminated disruptions typically caused by traditional ground-supported scaffolding | FSR Scaffolding FSR Plant and Equipment | Reduced manual handling risks by streamlining scaffold setup and removal. | Shared across the SRL project during the Innovation Workshop |  | Brenton Keast | Mitigated downtime and disruption associated with traditional ground-supported scaffold
Bridge Inn Road/ J-19 |  |  |  |  | Design |  | Idea: eliminating working at height The experiment: In the initial planning stage for the Plenty River Bridge construction, it was determined that by constructing the piling platform / hardstand at a higher level, that it would contribute to eliminating the need for working at height by the raising of the platform above the pile cut off levels by 300mm. This was proven to have been a successful implementation for the Bridge Inn Road project | FSR Working at Heights | This adjustment ensured that piling and beam installation could be carried out safely from ground level without the requirement for any Elevated Work Platforms (EWPs) to be used during these high-risk activities. ​ Furthermore, it enabled the workers to operate at a safe distance from the live water body (Plenty River) and which varies in flow rate and depths. | Verify platform FSL. |  | Muhammad Asad
Melbourne Airport Rail - Early Works (J34) |  |  |  |  | Design |  | Idea: Standardise Launch Shaft design & temp works during Design Phase The experiment: Addressed one of the project’s biggest risks with under boring numerous different services underneath the rail corridor & ExxonMobil fuel pipeline​ Temporary Work Designer embedded in team on hourly rates to work with designers, subcontract supply chain and construction delivery team​ INNOVATION - Non contestable utilities were involved with drawing in temporary construction shaft dimensions and locations on their designs​ ACCURATE - Site investigations data of actual service locations fed into shaft location | FSR Utilities and Services FSR Excavation | ENGINEERED SAFETY – Best for project standardised shaft shoring system was selected, designed, signed off and procured through Select prior to Delivery Phase works commencing​ ENGINEERED CERTAINTY - All shaft dimensions already confirmed to suit TBM, clash detection with all current and future services completed | Finalise shaft dimensions. |  | Glen Preema
Melbourne Airport Rail - Early Works (J34) |  |  |  |  | Methodology |  | Idea: Use of Hydraulic Slide-Rail Lifter to lift and remove shaft shoring components The experiment: Shaft shoring was standardised and cross hired through Select from Coates​ The removal of the sliderails upon completion required lift via crane or excavator​ The team investigated engineering solutions and discovered a German designed specialised system that could safely apply 100 tonnes of vertical lifting pressure​ The MAR Early Works team mobilised this system to site. The first time this had been used in Victoria | FSR Crane and Lifting | ENGINEERED SAFETY – Best for project standardised shaft shoring system​ Minimises any crane or excavator jerking motions and instability​ ENGINEERED CERTAINTY - avoided delays in demobilising shaft due to panels sticking or not freely releasing ​ General reduction in lifting operations within confined work sites and areas of varying ground quality | Monitor lifter mobilisation. |  | Glen Preema
Suburban Rail Loop I&EW | SRL001 |  |  |  | Methodology |  | Idea: Zero trim method applied to diaphragm wall panels to reduce the exposure to manual jack hammering hazards The experiment: Utilising an NDD truck instead of labourers with air driven jack hammers​ Coordination with Design to ensure that the quality of the diaphragm wall is not compromised​ Engaging with NDD suppliers to ensure the plant is fit for purpose | NA | Adoption of higher order engineering controls e.g. elimination control​ Reduced worker exposure to:​ Silica dust produced by manual break back​ Noise produced by air driven jack hammers ​ Vibration during jack hammer use​ Eliminate fatigue issue by all jack hammer users​ Shorter duration to complete the pile break back scope | Monitor NDD plant fitness. |  | Michael Beecham
SRL | SRL002 |  |  |  | Management |  | Action: Checked D-walls and as-builts against design to see if Walter and Strut would fit or clash Outcome: PointCloud Scan of the entire perimeter of the wall was conducted (inside and outside) | NA | Potensial savings of up to $175000 in labour hours otherwise used to assess manually | Review PointCloud Scan data. |  | Mike Silvester
SRL | SRL003 |  |  |  | Management |  | Action: Challenged and change the outdated process resulting in changing our Prism Monitoring for Tilt Meter Monitoring Outcome: DJV and SRLA approved the change and tilt meters installed on BUW and SSY TAS portals for 24/7 monitoring | NA | Increased survey safety and cost reduction | Verify tilt meter calibration. |  | Mike Silvester
SRL | SRL004 |  |  |  | Design |  | Action: Developed a solution to minimise greenhouse emissions within structural concrete contained within D-walls Outcome: Incorporated 70% Supplementary Cementitious Materials (SCM) concrete resulting in a significantly reduced amount of cement | NA | • Prevented an equivalent of 1935.56 tonnes of CO2 emissions otherwise generated through the production of cement • 59.10% emissions reduction • 9615.48T of recycled materials used (Flyash – 70% of the total concrete amount) | Confirm SCM concrete mix design |  | Alanah Alsop & Mat Boomsma
SRL | SRL005 |  |  |  | Methodology |  | Action: Assessed how we could re-use the water after dewatering the TAS to lower the groundwater table with no trade waste/sewer option available for water discharge Outcome: Water treatment plan installed on site to enable water- reuse | NA | >150,000L reused on site for dust suppression, wheel washes and filling water barriers •Excess water able to be discharged to Clayton South Drain, improving the flow regime of the waterway | Monitor water quality levels. |  | Nick Wybo
SRL | SRL006 |  |  |  | Management |  | Action: assessment of options was undertaken after two events involved load slippage resulting in injury and property damage Outcome: Magnetic fork covers were discovered to use on the forklift tines | FSR Plant and Equipment | The covers prevent metal on metal contact, therefore preventing sliippage of load on the tines | Audit magnetic cover usage. |  | John Price
SRL | SRL007 |  |  |  | Management |  | Action: Underground services high voltage cable contact lessons learnt and knowledge sharing Outcome: Development of PC1 digital learning tool to be shared across the business | FSR Utilities and Services | Video animation to promote learnings from key events and prevent reoccurence across the business | Roll out digital tool to site teams. |  | Mark O'Brien
SRL | SRL008 |  |  |  | Methodology |  | Action: Revised labour inefficiencies on-site Outcome: Implemented Wallop Water units | NA | Reduce labout in disposing of plastic bottles, minimised cost and environmental impact in disposing of plastic bottles | Verify Wallop unit locations. |  | Jock Scott
SRL | SRL009 |  |  |  | Management |  | Action: Melbourne Water required 6m depth of conduit which would have required interruption to Monash Uni car park Outcome: Liaised with multiple subcontractors and Melbourne Water to come up with an alternate alignment of conduit | FSR Utilities and Services FSR Excavation | Able to complete works without digging under Monash Uni car park | Finalise alternate alignment design. |  | Kirtiraj Kadam
SRL | SRL010 |  |  |  | Management |  | Action: Detailed survey pick up of secant pile wall at drop 2 to forecast actual position of wall at drops 3 and 4 for steel installation Outcome: Identified piles were in tolerance but highlighted potential issues for connecting steel during future installations (up to 100mm) | FSR Cranes and Lifting | Allowed the team to organise solution to modify brackets to account for pile tolerance prior to installation of S3 steel | Modify steel brackets. |  | Brenton Keast
SRL | SRL011 |  |  |  | Management |  | Action: Utilise pre-existing features within Aphex Outcome: Created a digital whiteboard and provided access to all team members concurrently | FSR Chain of Responsibility | Fills the role of the 2WLA on site whiteboard which is widely accessible and can be viewed remotely | Monitor Aphex usage. |  | Alfredo Sandoval
SRL | SRL012 |  |  |  | Methodology |  | Action: Identify sustainability opportunities at Box Hill Gardens reinstatement Outcome: Found recycled rubber as alternative products for running track | NA | Avoided creating new material for the gardens reinstatement and recycling scrap rubber for a better purpose | Finalize reinstatement plan. |  | Alfredo Sandoval
SRL | SRL013 |  |  |  | Methodology |  | Action: Monitor track movement while boring underground Outcome: Sensors installed to monitor track movement | NA | Eliminated the use of TFPCs or occupations to do physical survey measurements, mitigates safety risks that could impact train running and confirms the theoretical track settlement value is not exceeded | Verify sensor data feed. |  | Alfredo Sandoval
SRL | SRL014 |  |  |  | Management |  | Action: Integrating instrumentation and monitoring into Sixense scope and have Sixense manage data directly Outcome: All data relating to groundwater levels and D-wall movements consolidated to one date management system | NA | All data is in one place and can be viewed in real time by SRLA, LOR and the Subcontractor | Verify data feed stability. |  | Linn Sundstroem
SRL | SRL015 |  |  |  | Design |  | Action: Developed a Horizontal Directional Drilling (HDD) profile using Excel to evacuate and confirm clearance from underground services Outcome: Provides flexibility to adjust and plan the boring profile | FSR Utilities and Services | Improves the ability to plan and visualise the boring profile, enhancing risk identification and assessment | Review boring profile. |  | Patrick Toon
SRL | SRL016 |  |  |  | Methodology |  | Action: • Collaborative LOR/SRLA/SMEs review process built into iPIMS (rapid software customisation and deployment) • Process ‘control layer’ on top of SharePoint Outcome: Rapid documentation review, re-submissions and client acceptance. • On-time completion of zones. • Transmittal of pre-approved documents (one-time only) | FSR Chain of Responsibility | • Significant reduction (50 - 80%) in document control effort for both LOR and SRLA • Rapid review & approval (sometimes multiple cycles within same day) • 100% visibility of progress and any stoppages to be resolved | Monitor review cycle times. |  | Nick Wybo
SRL | SRL017 |  |  |  | Management |  | Action: Implement a safety initiative that will compliment the LOR existing safety assurance process Outcome: Increase safety participation by all team members on the project to ensure we finish strong | FSR Chain of Responsibility | Increase in safety assurances being completed each month which results in a reduction of events and injuries on the Project | Audit safety participation logs. |  | Nick Wybo
SRL | SRL018 |  |  |  | Management |  | Action: Required access to emergency response suppplies on site Outcome: Emergency Station installed at the TAS in SSY and Burwood | NA | A one-stop shop, able to be picked up by forklift or crane and contains the products potentially required in an emergency. De-fib, trauma bag, information board, fire extinguisher/s, spill kit | Verify station inventory. |  | Nick Wybo
SRL | SRL019 |  |  |  | Methodology |  | Action: Replaced traditional plywood coverings with engineered, reusable polypropylene safety covers for open excavations Outcome: Reduces the risk of falls and non-compliance with WH&S regulations | FSR Excavation FSR Working at Heights | Improved worker safety, reduced waste and costs with a durable high-visibility solution | Audit high-visibility covers. |  | Nick Wybo

## References
https://lorhsems.com/safety_category/fatal-severe-risks-fsrs/
FSR | Link
FSR Asbestos | https://lorhsems.com/safety/fsr-asbestos/
FSR Chain of Responsibility | https://lorhsems.com/safety/fsr-chain-of-responsibility-2/
FSR Crane and Lifting | https://lorhsems.com/safety/fsr-crane-and-lifting/
FSR Confined Space | https://lorhsems.com/safety/fsr-confined-spaces/
FSR Demolition | https://lorhsems.com/safety/fsr-demolition/
FSR Excavation | https://lorhsems.com/safety/fsr-excavation/
FSR Formwork & Falsework | https://lorhsems.com/safety/fsr-formwork/
FSR General Electrical Satety | https://lorhsems.com/safety/fsr-electrical-safety-2/
FSR Plant and Equipment | https://lorhsems.com/safety/fsr-plant-and-equipment/
FSR Plant and equipment Isolations and Lockouts | https://lorhsems.com/safety/fsr-plant-and-equipment-isolations-and-lockouts/
FSR Piling | https://lorhsems.com/safety/fsr-piling/
FSR Precast and Tilt up Concrete | https://lorhsems.com/safety/fsr-precast-and-tilt-up-concrete/
FSR Railway Operations | https://lorhsems.com/safety/fsr-14-rail-operations/
FSR Scaffolding | https://lorhsems.com/safety/fsr-scaffolding/
FSR Traffic Management | https://lorhsems.com/safety/fsr-traffic-management/
FSR Utilities and Services | https://lorhsems.com/safety/fsr-utilities-and-services/
FSR Work On, Over Or Adjacent to Water | https://lorhsems.com/safety/fsr-work-over-water/
FSR Working at Heights | https://lorhsems.com/safety/fsr-work-over-water/
Identified | Solution has been raised
Concept | Solution requires more detail on concept for project review
In Progress | Solution is in progress of being implemented
Unfeasable | Solution has been reviewed and not feasable on the project
Implemented | Solution has been Implemented